## DF_Standard_Project_Export
PROJECT ID | NUMBER ALT | PROJECT NAME | BUILDING NAME | BUILDING ADDRESS | BUILDING CITY | BUILDING STATE | BUILDING ZIP | ASSIGNED TO | TYPE | SUBTYPE | STATUS | STATUS DATE | WHO CREATED | DATE CREATED | DATE MODIFIED | WHO MODIFIED | BID AMOUNT | ORIGINAL CONTRACT AMOUNT | REVISED CONTRACT AMOUNT | OUTSTANDING CONTRACT AMOUNT | GROSS PROFIT MARGIN PRCNT | NOTES | ACTUAL PROJECT COST | ACTUAL PROJECT COST WHO | ACTUAL PROJECT COST DATE | SOURCE | BUDGET AMOUNT | BUDGET NOTES | BUDGET_DATE | CONTRACT WITH OBJECT | CONTRACT WITH NAME | CONTRACT WITH OFFICE NAME | SALES PERSON NAME | CONTRACT TERMS | CONTRACT TERMS NOTES | DIVISION | REFERNCE | SUBSOURCE | CLIENT PO NUMBER | LOCAL UNION | CONSTRUCTION CAPACITY | EXCLUSIONS | SPECIAL INSTRUCTIONS | CONTRACT DATE | HIDE DAILY WORK CREW | RUNNING NOTES | REFERENCE NOTES | SERIAL NUMBER | PRODUCTION STATUS | CONTRACT STATUS | CONTRACT STATUS DATE OPEN | CONTRACT STATUS DATE COMPLETED | CONTRACT STATUS DATE CLOSED | CONTRACT STATUS WHO OPEN | CONTRACT STATUS WHO COMPLETED | CONTRACT STATUS WHO CLOSED | PRODUCTION STATUS DATE | STATUS WHO | PRODUCTION STATUS WHO | CONTACT NAME | CONTACT PHONE NUMBER | CONTACT EMAIL
8100 | R2674 | Davis, Neil Residence | Davis, Neil Residence | 416 Wichita | McAllen | TX | 78503 | kelizondo | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract; E. Special Order | (09) IN PRODUCTION | 2021-11-23 | rcantu | 2021-11-23 | 2021-11-23 | lteniente |  | 850 | 850 | 425 | 100 |  | 0 |  | 2021-11-23 | Repeat | 850 |  |  | contact | Neil Davis |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-11-23 |  |  |  |  | (12) Ready to Invoice (Crystal) | Open | 2021-11-23 |  |  | lteniente |  |  | 2021-11-23 | lteniente | lteniente | Neil Davis | (832) 654-3831 | will provide at the appointment
8092 | C2961 | Green Gate Grove | Green Gate Grove | 700 N. Bentsen Palm Dr. | Palmview | TX | 78572 | jestrada | Exterior | Woodwork | (09) IN PRODUCTION | 2021-11-23 | jestrada | 2021-11-22 | 2021-11-24 | lteniente |  | 16237.5 | 16237.5 | 8737.5 | 100 | Paint entire building to color Almond. | 0 |  | 2021-11-23 | Self Generated | 0 |  |  | company | Green Gate Grove | Palmview , TX Office | Juan Estrada |  |  | Commercial | n | [6 empty] | 2021-11-23 |  |  |  |  | (02) Create Material List (Gary) | Open | 2021-11-23 |  |  | lteniente |  |  | 2021-11-24 | lteniente | lteniente
8091 | C2962 | Green Gate Grove | Green Gate Grove | 700 N. Bentsen Palm Dr. | Palmview | TX | 78572 | jestrada | Exterior | Gutters | (09) IN PRODUCTION | 2021-11-23 | jestrada | 2021-11-22 | 2021-11-24 | lteniente |  | 9195.84 | 9195.84 | 4948.34 | 100 | Replace Rake trim on gables. Install seamless gutters on back of building. | 0 |  | 2021-11-23 | Self Generated | 0 |  |  | company | Green Gate Grove | Palmview , TX Office | Juan Estrada |  |  | Commercial | n | [6 empty] | 2021-11-23 |  |  |  |  | (02) Create Material List (Gary) | Open | 2021-11-23 |  |  | lteniente |  |  | 2021-11-24 | lteniente | lteniente
8034 | C2959 | Family Dollar 3913 Jaime Zapata | Family Dollar 3913 Jaime Zapata | 3913 TX-20 Loop | Laredo | TX | 78043 | dvazquez | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-11-17 | dvazquez | 2021-11-15 | 2021-11-22 | egomez | 1200 | 1200 | 1200 | 1200 | 100 | Project Manager performed inspection. | 0 |  | 2021-11-17 | Google | 739.17 | Hutton- 3913 TX-20 Loop, Laredo Squares 2.5 LF 250 PRJ # 8034 Materials Silicone Mastic 1 $200 Ceiling Tiles Pack of 8 of 2 x 4 1 $38.61 Rags 1 $5.00 Putty Knife 2x$8.97 = $17.94 Mineral Spirits 1 $20.00 Fasteners 1 Small box of 20 1 $25.00 Drill Bits 1 $6.77 SUBTOTAL $313.32 + Tax (8.25%) $25.85 =$339.17 Labor Labor $400/Day/2 person X 1 = $400 Expenses Total $ 739.17 Profit Margin 0.615975= $1200 | 2021-11-17 | company | Hutton | Hutton | Ed Vazquez |  |  | Commercial | n | [6 empty] | 2021-11-17 |  | Talked to Ed he has Primo on this job Thursday/Friday. (11/18/2021 08:48 AM - bbuffamonte) |  |  | (10) Completed need to inspect ( PM, OC) | Open | 2021-11-17 |  |  | lteniente |  |  | 2021-11-22 | lteniente | egomez | Jared Childress | (423) 771-0312 | JChildress@Hutton.Build
8033 | C2958 | O'Hanlon Law Firm 2 | O'Hanlon Law Firm | 426 West Caffery Ave. | Pharr | TX | 78577 | kelizondo | Steep Slope Roof Systems | A. Metal ; B. Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-11-17 | wmitchell | 2021-11-12 | 2021-11-18 | gsolis | 4729.42 | 5119.6 | 5119.6 | 5119.6 | 100 | Repairs metal roof | 0 |  | 2021-11-17 | Google | 0 |  |  | company | O'Hanlon Law Firm | Pharr, TX Office | Will Mitchell |  |  | Commercial | n | [6 empty] | 2021-11-17 |  |  |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-11-17 |  |  | lteniente |  |  | 2021-11-18 | lteniente | gsolis | Sammy "Gonzalez " | (956) 318-0555 | sgonzalez@808west.com
8019 | C2957 | SOUTHEASTERN FREIGHT LINES: RYAN KORTHAUER | SOUTHEASTERN FREIGHT LINES: RYAN KORTHAUER | 1800 VOTECH DRIVE | WESLACO | TX | 78596 | kelizondo | Exterior | Gutters | (09) IN PRODUCTION | 2021-11-17 | kelizondo | 2021-11-10 | 2021-11-17 | gsolis | 1867.49 | 2021.56 | 2021.56 | 1010.77 | 100 | 1800 VOTECH DRIVE Address 2: City: WESLACO State: TX Zip Code: 78596 Job Details: I passed the email with all the details. May I ask how you heard about us?: Repeat May I have the name of the commercial building please?: SOUTHEASTERN FREIGHT LINES | 0 |  | 2021-11-17 | Repeat | 0 |  |  | company | SOUTHEASTERN FREIGHT LINES: RYAN KORTHAUER | WESLACO, TX Office | Will Mitchell |  |  | Commercial | n | [6 empty] | 2021-11-17 |  |  |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-11-17 |  |  | lteniente |  |  | 2021-11-17 | lteniente | gsolis
7997 | C2953 | Jehovah Witness Alton | Jehovah Witness Alton | 2613 W Main Ave | Alton | TX | 78573 | gsolis | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) IN PRODUCTION | 2021-11-08 | gsolis | 2021-11-08 | 2021-11-21 | srivas |  | 37290 | 37290 | 37290 | 100 |  | 0 | lteniente | 2021-11-08 | Repeat | 0 |  |  | contact | Melodie Garner |  | Gary Solis |  |  | Commercial | n | [6 empty] | 2021-11-08 |  | Material P.O is ready to be sent and crew is ready. Gary told me to wait till we get the anchors ordered. (11/21/2021 08:36 PM - srivas) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-11-08 |  |  | lteniente |  |  | 2021-11-21 | lteniente | srivas | Melodie Garner | (845) 744-9834 | mgarner@bethel.jw.org
7996 | R2672 | Gonzalez, Mario Residence | Gonzalez, Mario Residence | 2804 Seve Ln | Laredo | TX | 78045 | jestrada | Exterior | Gutters | (09) IN PRODUCTION | 2021-11-19 | jestrada | 2021-11-08 | 2021-11-24 | lteniente |  | 3098.75 | 3098.75 | 3098.75 | 100 | Send in Link to pay by checking. | 0 |  | 2021-11-18 | Self Generated | 0 |  |  | contact | Mario Gonzalez |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-11-18 |  | left a voicemail (11/24/2021 02:18 PM - lteniente) No longer pending payment (11/19/2021 12:17 PM - mmolano) pending payment (11/18/2021 03:21 PM - lteniente) |  |  | (02) Create Material List (Gary) | Open | 2021-11-18 |  |  | lteniente |  |  | 2021-11-24 | lteniente | lteniente | Mario Gonzalez | (956) 235-3322 | mariolandmarkbuilders@live.com
7992 | R2663 | PALMA, MARISSA Residence | PALMA, MARISSA Residence | 819 W COSTA RICA AVE | PHARR | TX | 78577 | kelizondo | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-11-10 | kelizondo | 2021-11-04 | 2021-11-17 | srivas | 1799.67 | 1799.67 | 1799.67 | 899.67 | 100 | 819 W COSTA RICA AVE Address 2: City: PHARR State: TX Zip Code: 78577 Job Details: 1 STORY, LEAKS, USING TARPS, 5-6 YEAR OLD ROOF, QUOTE FOR REPAIR AND REPLACEMENT, SPEAKS MOSTLY SPANISH IS INTERESTED IN 30 YEAR SHINGLE May I ask how you heard about us?: GOOGLE Are there any leaks? if so, where?: YES What type of roofing system do you have?: Shingles | 0 |  | 2021-11-10 | Google | 1799.67 |  |  | contact | Marissa Palma |  | Victor Perez |  |  | Residential | n | [6 empty] | 2021-11-10 |  | verified info in person (11/10/2021 09:54 AM - lteniente) |  |  | (05) Order and Schedule Material | Open | 2021-11-10 |  |  | lteniente |  |  | 2021-11-17 | lteniente | srivas | Marissa Palma | (956) 685-4763 | DIDNT HAVE ONE
7986 | C2956 | Acura of the Rio Grande Valley | Acura of the Rio Grande Valley | 1201 E. EXP 83 | San Juan | TX | 78589 | kelizondo | Low Slope Roof Systems | B. Roof Replacement; A. TPO; D. Retail Contract | (09) IN PRODUCTION | 2021-11-17 | kelizondo | 2021-11-04 | 2021-11-24 | bbuffamonte | 71680.21; 179200.52 | 77593.82 | 77593.82 | 38796.9 | 100 | 1201 E EXP 83 Address 2: City: SAN JUAN State: TX Zip Code: 78589 Job Details: I SENT AN EMAIL WITH THE MEASUREMENTS, CLAIM OPEN, LEAKS, FLAT ROOF May I ask how you heard about us?: CASTLEBRIDGE CONSTRUCTION RECOMMENDED US Are there any leaks? if so, where?: YES What type of roofing system do you have?: May I have the name of the commercial building please?: ACURA OF RIO GRANDE VALLEY Notes: WANTS WHATEVER RECOMMENDED DONE FOR JOB | 0 |  | 2021-11-16 | Referral | 0 |  |  | company | Acura of the Rio Grande Valley | San Juan, TX Office | Will Mitchell |  |  | Commercial | n | [6 empty] | 2021-11-16 |  | permit has been submitted. (11/23/2021 01:27 PM - klopez) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-11-16 |  |  | lteniente |  |  | 2021-11-24 | lteniente | bbuffamonte
7980 | R2666 | HALL, BILLIE Residence | HALL, BILLIE Residence | 2205 Daffodil Ave | MCALLEN | TX | 78501 | kelizondo | Exterior | Gutters | (09) IN PRODUCTION | 2021-11-15 | kelizondo | 2021-11-03 | 2021-11-24 | lteniente |  | 700 | 700 | 350 | 100 | Send Link to pay with checking. 2205 DAFFODIL Address 2: City: MCALLEN State: TX Zip Code: 78501 Job Details: GUTTER QUOTE, 1 STORY May I ask how you heard about us?: GOOGLE May I have the name of the commercial building please?: | 0 |  | 2021-11-11 | Google | 0 |  |  | contact | BILLIE HALL |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-11-11 |  | pending payment (11/11/2021 04:08 PM - lteniente) CALLED TO SET UP PAYMENT (11/10/2021 11:42 AM - kelizondo) |  |  | (02) Create Material List (Gary) | Open | 2021-11-11 |  |  | lteniente |  |  | 2021-11-24 | lteniente | lteniente | BILLIE HALL | (832) 298-1531 | MJE713@YAHOO.COM
7978 | R2657 | Luna, Mario Residence | Luna, Mario Residence | 11910 Manuel Acosta Drive | El Paso | TX | 79936 | jgarza | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract; E2. Solar Panel | (09) IN PRODUCTION | 2021-11-04 | jgarza | 2021-11-03 | 2021-11-21 | srivas |  | 8625 | 8625 | 8625 | 100 |  | 0 |  | 2021-11-04 | Self Generated | 0 |  |  | contact | Mario Luna |  | Johnny Garza |  |  | Residential | n | [6 empty] | 2021-11-04 |  | Material will be del. by southern shing.just still looking for a sub (11/15/2021 11:05 PM - srivas) as pre alfredo passing the prj through (11/08/2021 09:59 AM - klopez) as per alfredo moving prj forward. (11/08/2021 09:18 AM - klopez) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-11-04 |  |  | lteniente |  |  | 2021-11-21 | lteniente | srivas | Mario Luna | (915) 471-2562 | mariotboy32@live.com
7972 | C2941 | DOLLAR GENERAL | DOLLAR GENERAL | 1300 W Ruben M Torres Blvd | BROWNSVILLE | TX | 78520 | kelizondo | Low Slope Roof Systems | C. Addtional Exterior Work; A. Metal; D. Retail Contract | (09) IN PRODUCTION | 2021-11-16 | kelizondo | 2021-11-01 | 2021-11-19 | gsolis |  | 3117.6 | 3117.6 | 1558.8 | 100 | Send Link to pay online by checking. 1300 W Ruben M Torres Blvd Address 2: City: Brownsville State: Texas Zip Code: 78520 Job Details: I need an estimate for a roof leak repair. 1 STORY, METAL ROOF May I ask how you heard about us?: google Are there any leaks? if so, where?: not sure, the store manager has all the information. Her name is Veronica What type of roofing system do you have?: Metal May I have the name of the commercial building please?: Dollar General | 0 |  | 2021-11-08 | Google | 0 | Send Link to pay online by checking. |  | company | DOLLAR GENERAL | BROWNSVILLE, TX Office | Juan Estrada |  |  | Commercial | n | [6 empty] | 2021-11-08 |  | need field verification on metals (11/19/2021 02:28 PM - gsolis) payment no longer pending (11/18/2021 11:30 AM - lteniente) pending payment (11/08/2021 10:07 AM - lteniente) |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-11-08 |  |  | lteniente |  |  | 2021-11-19 | lteniente | gsolis | JACOB JORDAN | (979) 492-6270 | jacob@roserock.co
7956 | R2662 | BOCANEGRA, LINDA Residence | BOCANEGRA, LINDA Residence | 729 KIKA DE LA GARZA BLVD | LA JOYA | TX | 78560 | kelizondo | Low Slope Roof Systems | C. Addtional Interior Work; C. Addtional Exterior Work; B.Roof Repair; D. Retail Contract; A. Tile | (09) IN PRODUCTION | 2021-11-10 | kelizondo | 2021-11-01 | 2021-11-12 | klopez |  | 10540 | 10540 | 5540 | 100 | 729 N KIKA DE LA GARZA BLVD Address 2: City: LA JOYA State: TX Zip Code: 78560 Job Details: 2 STORY WHITE STUCCO HOUSE, TILE, LEAKS IN FRONT OF HOUSE, DINING ROOM, RESTROOM, BACK BEDROOM, INTERSTED IN POWER WASHING AND "PERMAVONN BY SHERWIN WILLIAMS" FOR WHEN IT'S FINISHED, CRACKS ABOVE WINDOWS, WANTS QUOTE FOR REPAIR May I ask how you heard about us?: GOOGLE Are there any leaks? if so, where?: YES, LEAKS IN FRONT OF HOUSE, DINING ROOM, RESTROOM, BACK BEDROOM What type of roofing system do you have?: Tile May I have the name of the commercial building please?: | 0 |  | 2021-11-10 | Google | 0 |  |  | contact | LINDA BOCANEGRA |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-11-10 |  | Tile is terra-cotta color clay mix tile. We are going to need five the following material. 1. 15% breakage factor on Terra-cotta color Claymex tile. 2. Hip and ridge tile to match since this usually breaks during the detach. 3. Make sure we use elevated battens 4. Make sure we do not forget bird stops. 5. Make sure we do not forget metal edge. 6. We need to seal scuppers with either acrylic or strip and some TPO. 7. Don’t forget about tile on chimney 8. There is also a small section in the back of the house on the first floor close to patio that has tile as well do not forget to do that section. (11/23/2021 09:28 AM - rcantu ) left a voicemail and text (11/10/2021 03:06 PM - lteniente) |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-11-10 |  |  | lteniente |  |  | 2021-11-12 | lteniente | klopez | LINDA BOCANEGRA | (956) 432-5235 | LINDABOKI@AOL.COM
7938 | R2655 | VASQUEZ, JOHN Residence | VASQUEZ, JOHN Residence | 2701 N MCCOLL ROAD, LOT E14 | MCALLEN | TX | 78501 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) IN PRODUCTION | 2021-11-02 | kelizondo | 2021-10-27 | 2021-11-11 | srivas |  | 3925.32 | 3925.32 | 3925.32 | 100 | 2701 N MCCOLL ROAD Address 2: LOT E14 City: MCALLEN State: TX Zip Code: 78501 Job Details: MOBILE HOME, METAL ROOF REPLACEMENT, 14*76 May I ask how you heard about us?: TELEVISION AD Are there any leaks? if so, where?: NO What type of roofing system do you have?: Metal May I have the name of the commercial building please?: Can't find on Nearmap | 0 |  | 2021-11-02 | TV Ad | 0 |  |  | contact | JOHN VASQUEZ |  | Flavio Padron |  |  | Residential | n | [6 empty] | 2021-11-02 |  | Client doesn't want to start until the end of NOV. (11/11/2021 04:38 PM - srivas) McAllen does not require permit for shingle repair/re-roof (11/05/2021 09:04 AM - klopez) called, didnt answer, left a voicemail (11/04/2021 03:14 PM - lteniente) was going to order a gaf but there's a huge tree and it's going to come back as obstructed by shrubbery (11/04/2021 03:12 PM - lteniente) Details of this project are on the signed contract. (11/02/2021 08:54 AM - fpadron) Details of this project are on the signed contract. (11/02/2021 08:54 AM - fpadron) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-11-02 |  |  | lteniente |  |  | 2021-11-09 | lteniente | srivas | JOHN VASQUEZ | (956) 258-7923 | VASQUEZ737@yahoo.com
7931 | C2932 | GoodWill Flashing | Goodwill Dixieland | 702 Dixieland rd | Harlingen | TX | 78550 | wmitchell | Low Slope Roof Systems | A. TPO; D. Retail Contract | (09) IN PRODUCTION | 2021-10-28 | wmitchell | 2021-10-26 | 2021-10-29 | gsolis | 1829.17 | 1829.17 | 1829.17 | 1829.17 | 100 |  | 0 |  | 2021-10-28 | Repeat | 0 |  |  | company | Goodwill Store | Harlingen, TX Office | Will Mitchell |  |  | Commercial | n | [6 empty] | 2021-10-28 |  |  |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-10-28 |  |  | lteniente |  |  | 2021-10-29 | lteniente | gsolis | Nick Forsell | (972) 400-2164 | nick@restorewithatlas.com
7918 | R2661 | GARZA, OLGA Residence | GARZA, OLGA Residence | 118 PARK LANE WEST | HARLINGEN | TX | 78552 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) IN PRODUCTION | 2021-11-09 | kelizondo | 2021-10-25 | 2021-11-22 | gsolis | 7581.67 | 7581.67 | 8506.67 | 5853.09 | 100 | 118 PARK LANE WEST Address 2: City: HARLINGEN State: TX Zip Code: 78552 Job Details: REQUESTED INFORMATION TO FINANCE, 1 STORY, SHINGLE, 25 YEAR OLD ROOF, LEAKS ON PATIO ONLY May I ask how you heard about us?: GOOGLE Are there any leaks? if so, where?: YES, PATIO ONLY What type of roofing system do you have?: Shingles May I have the name of the commercial building please?: | 0 |  | 2021-11-09 | Google | 7581.67 |  |  | contact | OLGA GARZA |  | Victor Perez |  |  | Residential | n | [6 empty] | 2021-11-09 |  | the materials list, drawings and consolidated report are in the folder labeled invoices and payments. (11/22/2021 11:06 AM - gsolis) there is no material list need to get with PM & Gary (11/21/2021 10:22 PM - srivas) called yesterday, didnt pick up, left a voicemail (11/10/2021 08:25 AM - lteniente) The customer requested additional 3 years leak free warranty please add $350 & Windstorm Certificate please add $ 575 (11/08/2021 07:43 PM - vperez) |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-11-09 |  |  | lteniente |  |  | 2021-11-10 | lteniente | klopez | OLGA GARZA | (956) 454-4914 | OLGAGARZA1960@GMAIL.COM
7911 | R2664 | Martin, Matthew Residence | Martin, Matthew Residence | 14003 Red Maple Wood | SAN ANTONIO | TX | 78249 | kelizondo | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-11-10 | kelizondo | 2021-10-22 | 2021-11-11 | gsolis |  | 3289.45 | 3289.45 | 986.83 | 100 | 14003 Red Maple Wood Address 2: City: San Antonio State: Texas Zip Code: 78249 Job Details: There is a small leak near the chimney. It falls down the side actually. It is near the corner of the chimney. Please call. I do not notice mold. I see detachment also. There is a small leak near the chimney. It falls down the side actually. It is near the corner of the chimney. Please call. Let me know if you can come out here for the estimate today at anytime. May I ask how you heard about us?: Google online Are there any leaks? if so, where?: yes What type of roofing system do you have?: Shingles May I have the name of the commercial building please?: residence it is for a home | 0 |  | 2021-11-10 | Google | 0 |  |  | contact | Matthew Martin |  | Orlando Marquez |  |  | Residential | n | [6 empty] | 2021-11-10 |  | validated info (11/10/2021 02:55 PM - lteniente) |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-11-10 |  |  | lteniente |  |  | 2021-11-11 | lteniente | gsolis | Matthew Martin | (904) 451-3935 | papamartin13@gmail.com
7893 | C2926 | MERX Trade Inc. | MERX Trade Inc. | 6547 Star Court | Laredo | TX | 78041 | dvazquez | Low Slope Roof Systems | A. TPO; B.Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-11-01 | dvazquez | 2021-10-20 | 2021-11-22 | egomez | 1155 | 1250 | 1250 | 1250 | 100 | 9:02 PM 10/20/2021 Emailed Request for Initial Payment Link to be sent to client. Contract in Docs. -Diane | 0 |  | 2021-10-25 | Repeat | 0 |  |  | company | Grupo San Rafael LTD | Laredo, TX Office | Ed Vazquez |  |  | Commercial | n | [6 empty] | 2021-10-25 |  | need aerial view for area of scope (11/04/2021 03:59 PM - gsolis) no longer pending payment (11/01/2021 02:56 PM - lteniente) pending payment (10/25/2021 10:57 AM - lteniente) Contract Proposal Price Breakdown: Material: $193 Labor: 2 man crew 1 day $400 Permit: $100 Total $693 /0.60 = $1155 (10/20/2021 08:50 PM - dvazquez) |  |  | (10) Completed need to inspect ( PM, OC) | Open | 2021-10-25 |  |  | lteniente |  |  | 2021-11-22 | lteniente | egomez | Fernando Zuniga | (956) 723-6311
7892 | R2644 | Mario Rueda | Rueda, Mario Residence | 1107 Helen Avenue | Mission | TX | 78572 | vperez | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract; E. Special Order | (09) IN PRODUCTION | 2021-10-22 | vperez | 2021-10-20 | 2021-11-05 | egomez | 1015 | 1015 | 1015 | 1014.99 | 100 |  | 0 |  | 2021-10-21 | Self Generated | 0 |  |  | contact | Mario Rueda |  | Victor Perez |  |  | Residential | n | [6 empty] | 2021-10-21 |  | Ismael will fabricate coping cap over the weekend (11/05/2021 02:26 PM - egomez) need design for coping cap (10/25/2021 08:20 AM - gsolis) verified info when payment was taken yesterday (10/22/2021 08:54 AM - lteniente) pending payment (10/21/2021 12:22 PM - lteniente) |  |  | (06) Schedule Labor | Open | 2021-10-21 |  |  | lteniente |  |  | 2021-11-05 | lteniente | egomez | Mario Rueda | (956) 225-7570 | mrueda@gruporuba.net
7880 | R2665 | Flores, Molleigh Residence | Flores, Molleigh Residence | 84 Sunrise Rd | RIO GRANDE CITY | TX | 78582 | kelizondo | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-11-11 | kelizondo | 2021-10-20 | 2021-11-17 | srivas | 1799.67 | 1799.67 | 1799.67 | 1799.67 | 100 | 84 Sunrise Rd Address 2: City: RIO GRANDE CITY State: TX Zip Code: 78582 Job Details: 1 STORY, SHINGLE, MOLD INSIDE THE ATTIC AT THE TOP OF THE GARAGE, THEY FOUND THE LEAK BC SOMEONE WAS WORKING ON THE GARAGE. THERE WAS A LEAK THERE BEFORE BUT THEY PATCHED IT UP, FOR ABOUT 2 MONTHS IT HAS BEEN LEAKING, 8 YEAR OLD ROOF May I ask how you heard about us?: GOOGLE Are there any leaks? if so, where?: YES, ON TOP OF GARAGE What type of roofing system do you have?: Shingles Can't Measure on NEarmaps | 0 |  | 2021-11-10 | Google | 0 |  |  | contact | Molleigh Flores |  | Victor Perez |  |  | Residential | n | [6 empty] | 2021-11-10 |  | validated info (11/11/2021 03:40 PM - lteniente) no longer pending payment (11/11/2021 02:32 PM - lteniente) Pending payment (11/10/2021 03:40 PM - lteniente) Please send her the link to make the 50% Down Payment (11/09/2021 08:53 PM - vperez) She requested the roof inspection again (11/08/2021 11:08 PM - vperez) He cancelled the appointment because he found someone else to repair his little roof leaks (10/22/2021 08:57 AM - vperez) |  |  | (05) Order and Schedule Material | Open | 2021-11-10 |  |  | lteniente |  |  | 2021-11-17 | lteniente | srivas | Molleigh Flores | (956) 617-2002 | molleighflores@outlook.com
7870 | C2933 | Gonzalez Auto Parts #1 4220 San Bernardo | Gonzalez Auto Parts | 4220 San Bernardo Ave | LAREDO | TX | 78041 | kelizondo | Low Slope Roof Systems | A. Metal; B.Roof Repair | (09) IN PRODUCTION | 2021-11-01 | kelizondo | 2021-10-19 | 2021-11-01 | gsolis |  | 3445.25 | 3445.25 | 3345.25 | 100 |  | 0 |  | 2021-11-01 | Self Generated | 0 |  |  | company | J&R RGV RE Co., LLC | Gonzalez Auto Parts LTD | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-11-01 |  |  |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-11-01 |  |  | lteniente |  |  | 2021-11-01 | lteniente | gsolis | JAMES GONZALEZ | (303) 518-3405 | JAMES@GRSTX.COM
7862 | R2651 | ARAFAT, NANCY Residence | ARAFAT, NANCY Residence | 3908 SUNDOWN DRIVE | MCALLEN | TX | 78503 | kelizondo | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-10-27 | kelizondo | 2021-10-18 | 2021-11-16 | srivas |  | 11200 | 11200 | 11200 | 100 | 3908 SUNDOWN DRIVE Address 2: ORANGEWOOD SOUTH GATE CODE: #8693 City: MCALLEN State: TX Zip Code: 78503 Job Details: 2 STORY, 2 LEAKS, CLAY TILE, QUOTE FOR REPAIR May I ask how you heard about us?: GOOGLE Are there any leaks? if so, where?: YES What type of roofing system do you have?: Tile May I have the name of the commercial building please?: | 0 |  | 2021-10-27 | Google | 0 |  |  | contact | NANCY ARAFAT |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-10-27 |  | We will be re-doing complete balcony with new tile. I have also added aerial views of areas that will be worked on. (10/27/2021 12:32 PM - rcantu) Verified Info (10/27/2021 10:49 AM - lteniente) Customer will be paying 35%, 35%, 30% on payment terms. (10/26/2021 10:34 AM - rcantu ) |  |  | (05) Order and Schedule Material | Open | 2021-10-27 |  |  | lteniente |  |  | 2021-11-16 | lteniente | srivas | NANCY ARAFAT | (956) 279-9223 | ARAFATMD@AOL.COM
7835 | R2638 | Lupita Munoz | Munoz, Lupita Residence | 2401 High Ridge Ln. | Edinburg | TX | 78539 | rcantu | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) IN PRODUCTION | 2021-10-15 | rcantu | 2021-10-14 | 2021-11-23 | srivas |  | 6565 | 6565 | 3565 | 100 |  | 0 |  | 2021-10-15 | Self Generated | 0 |  |  | contact | Lupita Munoz |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-10-15 |  | called back, verified info (10/18/2021 04:42 PM - lteniente) called, didnt respond or allow for a voicemail, left a text message (10/18/2021 04:39 PM - lteniente) |  |  | (10) Completed need to inspect ( PM, OC) | Open | 2021-10-15 |  |  | lteniente |  |  | 2021-11-23 | lteniente | srivas | Lupita Munoz | (956) 336-6280 | shoe_dal32@yahoo.com
7826 | R2637 | Garza, Diane Residence | Garza, Diane Residence | 815 Avenida Escandon | Rancho Viejo | TX | 78575 | lrodriguez | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair | (09) IN PRODUCTION | 2021-10-15 | rcantu | 2021-10-13 | 2021-11-15 | srivas |  | 17128 | 17128 | 11133.2 | 100 | We will be doing a detach and reset of clay tile on 2 facets Please see roof drawings | 0 |  | 2021-10-15 | Google | 0 |  |  | contact | Diane Garza |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-10-15 |  | Waiting on sub (Fernando) to be available to start project. (11/15/2021 04:26 PM - srivas) verified info yesterday (10/15/2021 09:46 AM - lteniente) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-10-15 |  |  | lteniente |  |  | 2021-11-15 | lteniente | srivas | Diane Garza | (956) 572-0304 | dianemgarza@hotmail.com
7804 | R2646 | ROHR, AL Residence | ROHR, AL Residence | 1510 E BUS HWY 83, LEMON TREE ESTATES UNIT C5 | MISSION | TX | 78572 | kelizondo | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-10-22 | kelizondo | 2021-10-11 | 2021-11-05 | egomez |  | 2100 | 2100 | 1050 | 100 | 1510 E BUS HWY 83 Address 2: LEMON TREE ESTATES UNIT C5 City: MISSION State: TX Zip Code: 78572 Job Details: MOBILE HOME, METAL ROOF, WATER DAMAGE IN THE BATHROOM CEILING, VENT MIGHT NEED REPLACING, LEAKS WHEN IT RAINS, WOULD ALSO LIKE WASH AFTER MAINTENANCE SHELLY IS AN EMPLOYEE, THESE ARE HER PARENTS May I ask how you heard about us?: EMPLOYEE Are there any leaks? if so, where?: YES What type of roofing system do you have?: Metal | 0 |  | 2021-10-25 | Referral | 0 |  |  | contact | AL ROHR |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-10-25 |  | need field verifications on designs for ridge and awning flashings (10/27/2021 09:08 AM - gsolis) Didnt pick up, no option left for a voicemail (10/25/2021 02:12 PM - lteniente) 956 878 2153 956 205 2957 (10/11/2021 03:17 PM - jestrada ) |  |  | (05) Order and Schedule Material | Open | 2021-10-25 |  |  | lteniente |  |  | 2021-11-05 | lteniente | egomez | AL ROHR | (956) 205-2927 | ROHRAJAY771@GMAIL.CO
7790 | C2927 | SILVER SANDS RENTALS (2727 11th St. U.24) | SILVER SANDS VACATION RENTALS | 732 SAND CASTLE DRIVE, UNIT 3 | PORT ARANSAS | TX | 78373 | kelizondo | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract; E. Special Order | (09) IN PRODUCTION | 2021-10-25 | pwesterman | 2021-10-08 | 2021-11-12 | srivas |  | 1577.48 | 1577.48 | 1025.36 | 100 | 2 STORY, SHINGLE ROOF, REPAIR, CONTACT BEN: MANAGER 3617492600 EMAIL: maintenance@silversandsvacationrentals.com | 0 |  | 2021-10-25 | Repeat | 0 | Send all billing information to Kay the owner of the property. Also, communicate directly with her. Kay Lawley: 512-656-5135 kaylawley@me.com |  | company | SILVER SANDS VACATION RENTALS | PORT ARANSAS, TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-10-25 |  | cant find plastic blk vents. Contacted PM to see what he wanted to do. (11/08/2021 03:17 PM - srivas) does not require permit for shingles (10/27/2021 04:05 PM - klopez) philip says the color is silver birch or as close as possible (10/27/2021 02:51 PM - gsolis) verified info (10/27/2021 10:53 AM - lteniente) |  |  | (05) Order and Schedule Material | Open | 2021-10-25 |  |  | lteniente |  |  | 2021-11-12 | lteniente | srivas
7784 | C2917 | T-Mobile Mobile Skylights | T-Mobile | 3711 San Gabriel | Mission | TX | 78572 | wmitchell | Low Slope Roof Systems | A. BUR; B.Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-10-08 | wmitchell | 2021-10-07 | 2021-10-12 | officestaff |  | 9394.47 | 9394.47 | 9394.47 | 100 |  | 0 |  | 2021-10-08 |  | 0 |  |  | company | T-Mobile | Mission , TX Office | Will Mitchell |  |  | Commercial | n | [6 empty] | 2021-10-08 |  | Will M. says to check with alfredo about how to proceed (10/11/2021 09:34 AM - gsolis) |  |  | (05) Order and Schedule Material | Open | 2021-10-08 |  |  | lteniente |  |  | 2021-10-12 | lteniente | officestaff
7779 | R2641 | Polley, Eric Residence 1631 | Polley, Eric Residence | 1631 Throckmorton | Harlingen | TX | 78550 | wmitchell | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) IN PRODUCTION | 2021-11-18 | wmitchell | 2021-10-07 | 2021-11-18 | ctostado | 8869.00; 9456.25 | 9456.25 | 13436.25 | 0 | 100 | This is a repeat customer of ours doing two residential roofs at one time. Also, on the 1631 address we are doing TPO on the flat roof area. | 0 | ctostado | 2021-11-22 |  | 0 |  |  | contact | Eric Polley |  | Will Mitchell |  |  | Residential | n | [6 empty] | 2021-10-15 |  | Per Will work not done. Still need skylight, flat roof compression. (11/18/2021 09:20 AM - ctostado) CONFIRMED WITH WILL TO INVOICE (11/17/2021 04:29 PM - kelizondo) material will be del. tomorrow 11/03 @ 10:30am (11/02/2021 08:43 AM - srivas) Please select white color drip edge for this roof 1631 (10/19/2021 12:25 PM - wmitchell ) |  |  | (06) Schedule Labor | Completed | 2021-11-18 | 2021-11-22 |  | ctostado | ctostado |  | 2021-11-18 | ctostado | ctostado | Eric Polley | (956) 536-1093 | eric@redelco.com
7759 | C2920 | SILVER SANDS RENTALS (732 Sand Castle Dr) | SILVER SANDS VACATION RENTALS | 732 SAND CASTLE DRIVE, UNIT 3 | PORT ARANSAS | TX | 78373 | kelizondo | Steep Slope Roof Systems | B. Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-10-11 | kelizondo | 2021-10-04 | 2021-11-12 | srivas |  | 1631.6 | 1631.6 | 124.35 | 100 | 2 STORY, SHINGLE ROOF, REPAIR, ROOF AGE SINCE 2017, LEAKS IN BATHROOM CONTACT BEN: MANAGER 3617492600 EMAIL: MAINTENANCE@SILVERSANDSVACATIONRENTALS.COM Can be accessed from the stairwell with 1 story ladder then a ladder pull to go over to the other side of the roof | 0 |  | 2021-10-11 | Repeat | 0 | Customer to pay full amount up front |  | company | SILVER SANDS VACATION RENTALS | PORT ARANSAS, TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-10-11 |  | called, left a voicemail (10/13/2021 09:54 AM - lteniente) |  |  | (05) Order and Schedule Material | Open | 2021-10-11 |  |  | lteniente |  |  | 2021-11-12 | lteniente | srivas
7732 | C2914 | MCALLEN BIS ASSOCIATES | FD McAllen | 5901 S International Pkwy | McAllen | TX | 78503 | gsolis | Low Slope Roof Systems | B. Roof Replacement; A. Metal; D. Retail Contract | (09) IN PRODUCTION | 2021-10-07 | kelizondo | 2021-09-29 | 2021-11-16 | egomez |  | 1450 | 1450 | 1450 | 100 | JIM PEDERSON SENT AN ATTACHMENT FOR A METAL ROOF REPLACEMENT QUOTE, AT THE MOMENT SCHEDULED FOR 9/30 @1PM | 0 |  | 2021-10-05 | Google | 0 |  |  | company | FD McAllen | McAllen , TX Office | Gary Solis |  |  | Commercial | n | [6 empty] | 2021-10-05 |  | Pending panels (11/16/2021 08:52 AM - egomez) scheduled ismael for re-roof 11/4 called client letting them know about the update. (11/03/2021 12:34 PM - klopez) called vendor to get status on materials he let me know that the materials should be ready by Thursday 10/28 or Friday 10/29. (10/26/2021 01:50 PM - klopez) materials have been orders po#QC-62841 (10/19/2021 10:48 AM - egomez) called client and gave him updates regarding project. (10/15/2021 09:08 AM - officestaff) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-10-05 |  |  | lteniente |  |  | 2021-11-16 | lteniente | egomez | Jim Pederson | (956) 960-9768 | pedersonjp2@gmail.com
7659 | R2659 | FRED GOMEZ: LA FERIA | FRED GOMEZ: LA FERIA | 103 S MAIN ST | LA FERIA | TX | 78559 | kelizondo | Low Slope Roof Systems | B. Roof Replacement; A. TPO; D. Retail Contract | (09) IN PRODUCTION | 2021-11-09 | kelizondo | 2021-09-21 | 2021-11-17 | bbuffamonte |  | 28000 | 28000 | 14000 | 100 | 103 S MAIN STREET Address 2: City: LA FERIA State: TX Zip Code: 78559 Job Details: BUILDING NEXT TO LOS AMIGOS RESTAURANT May I ask how you heard about us?: SELF GENERATED Are there any leaks? if so, where?: N/A What type of roofing system do you have?: May I have the name of the commercial building please?: | 0 |  | 2021-11-09 | Self Generated | 0 |  |  | company | FRED GOMEZ: LA FERIA | LA FERIA, TX Office | Roel Cantu |  |  | Commercial | n | [6 empty] | 2021-11-09 |  | Talked with Roel. Waiting on the Mason company to coordinate work. (11/17/2021 02:19 PM - bbuffamonte) left a voicemail (11/09/2021 04:21 PM - lteniente) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-11-09 |  |  | lteniente |  |  | 2021-11-17 | lteniente | bbuffamonte | Fred Gomez | (956) 792-5130 | mbg3517@aol.com
7644 | R2619 | Eric Piater | Piater, Eric Residence | 1310 Tierra Encantada, Weslaco, TX 78596 | Weslaco | TX | 78596 | vperez | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-09-28 | vperez | 2021-09-19 | 2021-10-12 | rlerma |  | 1350 | 1350 | 1350 | 100 |  | 0 |  | 2021-09-27 | Self Generated | 1350 |  |  | contact | Eric Piater |  | Victor Perez |  |  | Residential | n | [6 empty] | 2021-09-27 |  | repeat customer, left a voicemail of the next steps (09/30/2021 01:57 PM - lteniente) pending payment (09/27/2021 11:54 AM - lteniente) |  |  | (06) Schedule Labor | Open | 2021-09-27 |  |  | lteniente |  |  | 2021-10-12 | lteniente | rlerma | Eric Piater | (956) 650-0144 | wpiater@hotmail.com
7640 | C2907 | Lazy A Ranch Beeville: SKIDMORE | Lazy A Ranch Beeville: SKIDMORE | 2785 GUAJOLOTE ROAD | SKIDMORE | TX | 78389 | kelizondo | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair | (09) IN PRODUCTION | 2021-10-27 | kelizondo | 2021-09-17 | 2021-11-16 | srivas |  | 6307.86 | 6307.86 | 6307.86 | 100 | 2785 GUAJOLOTE ROAD Address 2: City: SKIDMORE State: TX Zip Code: 78389 Job Details: 7K SQ FT, 1 STORY, LEAKING, REPAIR, CLAY TILE May I ask how you heard about us?: TELEMARKETING Are there any leaks? if so, where?: YES What type of roofing system do you have?: Tile May I have the name of the commercial building please?: Lazy A Ranch Beeville: SKIDMORE | 0 |  | 2021-09-28 | Telemarketing | 0 | Please send invoice ASAP |  | company | Lazy A Ranch Beeville: SKIDMORE | SKIDMORE, TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-09-28 |  | as per rollie need to send teo out to this job. Will get with erika to see when we can set it up. (11/16/2021 10:05 AM - srivas) payment no longer pending (10/27/2021 03:48 PM - lteniente) pending payment (09/28/2021 04:46 PM - lteniente) |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-09-28 |  |  | lteniente |  |  | 2021-10-28 | lteniente | gsolis | BRENT HOFFMAN | (361) 701-9942 | BRENT@ROCKINHSERVICES.COM
7631 | R2624 | Ayala, Hilda Residence | Ayala, Hilda Residence | 133 Sunflower Ave. | McAllen | TX | 78504 | rcantu | Exterior |  | (09) IN PRODUCTION | 2021-09-30 | rcantu | 2021-09-16 | 2021-10-15 | rlerma |  | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | [5 empty] | Roel Cantu |  |  | Residential | n | [8 empty] | as per OM there is no contact info other than a mexican number. PM Roel is point of contact thru whatsapp. (10/15/2021 08:37 AM - rlerma) waiting on aerial upload to move forward (10/06/2021 08:17 AM - gsolis) Pablo Ayala email pabloayalaguerrero@gmail.com (09/30/2021 12:52 PM - rcantu ) We will be doing the coating and the interior sheet rock repair. (09/30/2021 12:47 PM - rcantu ) |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | [7 empty] | 2021-10-07 |  | gsolis | Hilda Ayala |  | pabloayalaguerrero@gmail.com
7599 | R2648 | Evenson, Patricia Residence | Evenson, Patricia Residence | 7820 N 4th St. | McAllen | TX | 78504 | jestrada | Low Slope Roof Systems | B. Roof Replacement; B. Roof Over Construction; A. TPO; D. Retail Contract | (09) IN PRODUCTION | 2021-10-25 | jestrada | 2021-09-14 | 2021-11-23 | kelizondo |  | 11368 | 12618 | 6934 | 100 |  | 0 |  | 2021-10-25 | Self Generated | 0 | INSPECTION 250 |  | contact | Patricia Everson |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-10-25 |  | JUAN SAID PUNCHOUT (11/23/2021 11:15 AM - kelizondo) Waiting on Fabrication of Turtle Vent will be installed 11/16. (11/15/2021 09:57 AM - bbuffamonte) Lorenzo started 11/10 bottom two tiers needed major deck renovation (11/10/2021 09:49 AM - bbuffamonte) permit uploaded (11/09/2021 11:25 AM - klopez) called the client no answer left a voice mail and text giving her a status update. Materials have been ordered Beacon - QR- 25008 ABC - QR-25009 BRS- QR-25010 (11/02/2021 12:06 PM - klopez) permit submitted (10/28/2021 02:48 PM - klopez) validated info (10/25/2021 02:48 PM - lteniente) |  |  | (11) Punchout - Corrections | Open | 2021-10-25 |  |  | lteniente |  |  | 2021-11-23 | lteniente | kelizondo | Patricia Everson | (908) 200-8410 | p1885.210@gmail.com
7589 | C2923 | LA PALABRA VIVIENTES MINISTRY | LA PALABRA VIVIENTES MINISTRY | 171 DEANNA DR | SAN JUAN | TX | 78589 | kelizondo | Low Slope Roof Systems | C. Addtional Exterior Work; A. Metal; A. Coating Acylic Based; B.Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-10-22 | kelizondo | 2021-09-13 | 2021-11-09 | klopez |  | 0 | 0 | 0 | 0 | 171 DEANNA DR Address 2: City: SAN JUAN State: TX Zip Code: 78589 Job Details: 1 STORY, GUTTER ESTIMATE May I ask how you heard about us?: GOOGLE May I have the name of the commercial building please?: LA PALABRA VIVIENTES MINISTRY | 0 |  |  | Google | 0 | [5 empty] | Juan Estrada |  |  | Commercial | n | [8 empty] | permit uploaded (11/09/2021 11:26 AM - klopez) called the client to let her know the status on her project. (11/02/2021 11:19 AM - klopez) disregard previous message in correct information for this job (11/02/2021 11:14 AM - klopez) permit has been ready since last week Thursday. Couldn't pay for it due to card not having enough funds. Will be going by today to pay for permit. (11/01/2021 11:00 AM - bbuffamonte) submitted permit (10/29/2021 12:43 PM - klopez) |  |  | (06) Schedule Labor | [7 empty] | 2021-11-02 |  | klopez | DESIREE RODRIGUEZ | (956) 702-3211 | DVMMP956@GMAIL.COM
7580 | R2643 | GARZA, MELISSA Residence | GARZA, MELISSA Residence | 733 N. 48TH | MCALLEN | TX | 78501 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-10-19 | kelizondo | 2021-09-10 | 2021-11-15 | mmolano |  | 9663.66 | 9857.66 | 8323.66 | 100 | 1 STORY, SHINGLE, LEAKS, 20 YEAR OLD ROOF, REPLACEMENT, NO CLAIM OPEN CURRENTLY | 0 | ctostado | 2021-11-23 | General Contractor | 0 |  |  | contact | MELISSA GARZA |  | Flavio Padron |  |  | Residential | n | [6 empty] | 2021-10-19 |  | Confirmed with Flavio insurance is what is left (11/11/2021 04:54 PM - kelizondo ) This project was transferred from Jesse to me due to the fact that Jesse had to leave out of town for an indefinite amount of time. Alfredo is aware of this. (10/21/2021 05:11 PM - fpadron) verified info in person (10/19/2021 02:40 PM - lteniente) |  |  | (12B) Ready to Invoice Insurance (Crystal) | Open | 2021-10-19 |  |  | lteniente |  |  | 2021-11-15 | lteniente | mmolano | MELISSA GARZA | (956) 648-9469 | MELMARIBEL@AOL.COM
7537 | C2912 | Alfredo Casso & Co Inc | Alfredo Casso & Co Inc | 14101 Transportation Ave | Laredo | TX | 78041 | dvazquez | Low Slope Roof Systems | A. Coating Acylic Based; A. Coating Silicone Based; B.Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-10-06 | dvazquez | 2021-09-07 | 2021-10-26 | klopez | 10100 | 9730.59 | 9730.59 | 9730.59 | 100 |  | 0 |  | 2021-10-04 | Self Generated | 6051.63 | Diane's Pricing/Material Notes for Production Review: Material QTY Price Total Rag Sets 4 $10 $40 Brush/Roller/Pan Set 2 $82.50 $165 Thermotek Metal Primer 2 $102 $204 Thermotek Wash 1 $71 $71 Thermotek Base Coat 4 $65 $260 Thermotek Acrylic Mastic 3 $80 $240 Thermotek Silicone X99 4 $230 $920 Mesh 2 $27 $54 Delivery Fee $250 Downspouts Provided by Sub $646 Total Allotted for Material $2850 + Tax $235.13 = $3085.13 Labor 5 Days @ $400/day = $2000 Total Allotted for Labor $2000 Equipment/Other Permit $500 Temp Toilet for 1 wk $200 + Tax $16.50 = $216.50 Motel Stay for Project Managers for 2 nights with Taxes $250 Total Allotted for Equipment/Other $966.50 Grand Total of All Expenses Allotted for $6051.63 Contract Pricing $10100 (6051.63/.60) |  | company | Hector Hall DBA | Laredo, TX Office | Ed Vazquez |  |  | Commercial | n | [6 empty] | 2021-10-04 |  | permit uploaded (10/26/2021 04:59 PM - klopez) permit submitted. (10/18/2021 12:17 PM - officestaff) no longer pending payment (10/06/2021 04:01 PM - lteniente) pending payment (10/04/2021 03:57 PM - lteniente) |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-10-04 |  |  | lteniente |  |  | 2021-10-18 | lteniente | officestaff | Ceasar Perales | (956) 999-2851
7534 | R2636 | Jeremias Tezcucano 2018 E. 21st St. | Tezcucano, Jerimias Residence | 2018 E. 21ST ST | MISSION | TX | 78574 | kelizondo | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-10-14 | kelizondo | 2021-09-07 | 2021-11-09 | r_lopez |  | 3454.19 | 3454.19 | 2245.22 | 100 | not much info available, made appt and collected email | 0 |  | 2021-10-14 | Self Generated | 0 |  |  | contact | Jerimias Tezcucano |  | Philip Westerman |  |  | Residential | n | [6 empty] | 2021-10-14 |  | Rollie passed job to Erika said she was going to schedule Thursday. (11/09/2021 09:05 AM - srivas) verified info (10/14/2021 02:48 PM - lteniente) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-10-14 |  |  | lteniente |  |  | 2021-11-09 | lteniente | r_lopez | Jerimias Tezcucano | (903) 235-2451 | miastez@gmail.com
7520 | R2613 | PRUITT, SHELIA Residence | PRUITT, SHELIA Residence | 800 N 46TH | MCALLEN | TX | 78501 | kelizondo | Exterior | Gutters | (09) IN PRODUCTION | 2021-09-30 | kelizondo | 2021-09-02 | 2021-10-06 | officestaff |  | 875 | 875 | 568.75 | 100 | 800 N 46TH Address 2: City: MCALLEN State: TEXAS Zip Code: 78501 Job Details: GUTTERS ESTIMATE, 2 STORY May I ask how you heard about us?: PHILIP | 0 |  | 2021-09-23 | Self Generated | 0 |  |  | contact | SHELIA PRUITT |  | Philip Westerman |  |  | Residential | n | [6 empty] | 2021-09-23 |  | called client, didn't pickup. sent text message with updates on project. (10/06/2021 11:14 AM - officestaff) no longer pending payment, validated info (09/30/2021 04:07 PM - lteniente) pending payment (09/23/2021 11:44 AM - lteniente) |  |  | (05) Order and Schedule Material | Open | 2021-09-23 |  |  | lteniente |  |  | 2021-10-06 | lteniente | officestaff | SHELIA PRUITT | (956) 821-1631 | SPRUITT50@GMAIL.COM
7516 | C2900 | Specs | Specs | 822 Dixieland Rd | Harlingen | TX | 78552 | wmitchell | Exterior | Gutters | (09) IN PRODUCTION | 2021-09-24 | wmitchell | 2021-09-02 | 2021-11-10 | egomez | 2463.84; 9268.49; 6489.75 | 2463.84 | 2463.84 | 2463.84 | 100 |  | 0 |  | 2021-09-24 |  | 0 |  |  | contact | Bailey McDonald |  | Will Mitchell |  |  | Commercial | n | [6 empty] | 2021-09-24 |  | called client and gave him updates on project. told me marco montoyo: 214-218-8330 is preferred contact for scheduling. (10/15/2021 09:03 AM - officestaff) |  |  | (05) Order and Schedule Material | Open | 2021-09-24 |  |  | lteniente |  |  | 2021-11-10 | lteniente | egomez
7501 | R2597 | PENA, LAURA Residence | PENA, LAURA Residence | 125 OLD ALICE ROAD | BROWNSVILLE | TX | 78552 | kelizondo | Low Slope Roof Systems | B. Roof Replacement; C. Addtional Exterior Work; A. TPO; D. Retail Contract | (09) IN PRODUCTION | 2021-09-03 | kelizondo | 2021-08-31 | 2021-11-09 | kelizondo |  | 10650 | 10650 | 6922.5 | 100 | 125 OLD ALICE ROAD Address 2: City: BROWNSVILLE State: TEXAS Zip Code: 78552 Job Details: SHINGLE, 1 STORY, NO LEAKS, REPLACEMENT QUOTE, NEEDS WHATEVER IS PURCHASED TO BE WINDSTORM CERTIFIED May I ask how you heard about us?: GOOGLE Are there any leaks? if so, where?: NO What type of roofing system do you have?: Shingles | 0 | ctostado | 2021-10-29 | Google | 0 |  |  | contact | LAURA PENA |  | Philip Westerman |  |  | Residential | n | [6 empty] | 2021-09-03 |  | spoke to customer today, said all issues in my last note still exist: carport has nails sticking out, plastic is still on trimming, old trimming wasn't completely removed in one corner and new trimming is misaligned at the corner of the front of the house. those are mrs. pena's words (11/09/2021 09:14 AM - kelizondo) Sub was out there making corrections of Saturday 10/29/21 (11/03/2021 11:21 AM - egomez) WAS SCHEDULING FINAL INSPECTION BUT SHE SAID SHE SENT PICTURES OF NAILS HANGING OUT OF CARPORT ROOF AND PLASTIC THAT IS STILL ON TRIMMING. I TOLD HER WE WOULD WORK ON GETTING OUT THERE TO FIX THIS AND THEN WOULD CALL BACK TO SCHEDULE A REAL FINAL INSPECTION (11/02/2021 11:24 AM - kelizondo) PENDING 2 PIECE (10/18/2021 02:57 PM - kelizondo) tentative date for jaime on 10/7-10/8. (09/28/2021 11:32 AM - officestaff) uploaded permit (09/24/2021 08:23 AM - klopez) permit is ready for pickup. (09/22/2021 11:45 AM - officestaff) permit submitted (09/15/2021 09:38 AM - klopez) validated info, no longer pending payment (09/07/2021 03:06 PM - lteniente) Pending payment (09/03/2021 11:29 AM - lteniente) Tear off down to the deck: Replace rooted decking. Be creative with the metal to TPO transition. Use TPO in our stock pile (09/02/2021 04:21 PM - pwesterman) CUSTOMER WAS TOLD TO ASK FOR A QUOTE ON WINDOWS, I REFERRED TO JUAN AUCES. WANTS 3 FRENCH 4FT WINDOWS PLUS ANOTHER AREA (09/01/2021 12:47 PM - kelizondo) |  |  | (11) Punchout - Corrections | Completed | 2021-09-03 | 2021-10-29 |  | lteniente | ctostado |  | 2021-11-09 | ctostado | kelizondo | LAURA PENA | (202) 297-7807 | PENA.LAURA@GMAIL.COM
7498 | R2676 | MUNOZ, CIRIA Residence | MUNOZ, CIRIA Residence | 803 S. STANDARD AVE | SAN JUAN | TX | 78589 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; A. Metal ; B. Roof Repair; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-11-23 | kelizondo | 2021-08-31 | 2021-11-24 | lteniente |  | 3916.15 | 3916.15 | 1661.52 | 100 | May I have the address where the appointment is needed?: 803 S. STANDARD AVE Address 2: City: SAN JUAN State: TEXAS Zip Code: 78589 Job Details: LEAKING IN LIVING ROOM, DINING ROOM, 1200 SQ FT, WOODFRAME HOUSE, ROOF 20 YEARS + May I ask how you heard about us?: GOOGLE Are there any leaks? if so, where?: YES, DINING ROOM AND LIVING ROOM What type of roofing system do you have?: Shingles | 0 | lteniente | 2021-11-23 | Google | 0 |  |  | contact | CIRIA MUNOZ |  | Flavio Padron |  |  | Residential | n | [6 empty] | 2021-11-23 |  | verified info, awaiting gaf (11/24/2021 02:23 PM - lteniente) |  |  | (01) Validate Info - (Leila) | Open | 2021-11-23 |  |  | lteniente |  |  | 2021-11-23 | lteniente | lteniente | CIRIA MUNOZ | (956) 393-9011 | CIRIAMNZ0527@GMAIL.COM
7495 | C2908 | VINEYARD CHRISTIAN FELLOWSHIP | VINEYARD CHRISTIAN FELLOWSHIP | 1200 Mackintosh Dr | BROWNSVILLE | TX | 78521 | kelizondo | Low Slope Roof Systems | B. Roof Replacement; A. Metal; A. Coating Acylic Based; D. Retail Contract | (09) IN PRODUCTION | 2021-10-04 | kelizondo | 2021-08-30 | 2021-11-22 | egomez |  | 28260 | 28260 | 10267.5 | 100 | 1200 Mackintosh Dr Address 2: City: Brownsville State: Texas Zip Code: 78521 Job Details: Routine Maintenance handling? no What is the square footage? 6,200 How many stories is your roof? 1 What is the age of your roof? 20 When was last time inspected or restored? na Will we be inspecting more than 1 facility? no Any current issues? yes leak Any emergency repairs needed? no Have you contacted your insurance? no If no external access– who can we meet for internal access? See Jim roof is metal looking to replace, but if cost to much then repairs….Jim is on vacation and will be returning September 13 So much go at this Time Sept 14 May I ask how you heard about us?: Telemarketing Are there any leaks? if so, where?: not sure What type of roofing system do you have?: May I have the name of the commercial building please?: Vineyard Church Brownsville Can't find on Maps | 0 |  | 2021-10-04 | Telemarketing | 0 |  |  | company | VINEYARD CHRISTIAN FELLOWSHIP | BROWNSVILLE, TX Office | Roel Cantu |  |  | Commercial | n | [6 empty] | 2021-10-04 |  | Giving customer an estimate to paint the rest of the building. I want to take care of these punch outs for him so that we can possibly get the paint project as well. (11/11/2021 12:15 PM - rcantu ) Punch out Inspected project. Customer had just a few concerns. 1. When I sold the project we sold new gutters on the building. He had a gutter downspout at the entrance on the right hand side. They only put one on the left-hand side. 2. Gutter in back has a section where it runs into the electrical boxes. I had spoke with the customer mentioning that we would try to find a solution to divert water into the gutters. The man that were out there told him that we can put a flashing to divert the water into the gutters but it was not done. (11/11/2021 12:15 PM - rcantu ) aurelio is installing the gutters (11/08/2021 11:12 AM - klopez) Panel Replacement and Coating Complete. Only pending gutter and downspout replacement (11/03/2021 11:59 AM - egomez) called the client to inform them about tentative date for 11/1 scheduled for beto weather permitting. WE will be continuing the coating part of the main dwelling. (10/26/2021 03:51 PM - klopez) Metal panels have been replaced pending Coating Tentatively Next Week 11/01/21 (10/25/2021 04:37 PM - egomez) permit uploaded (10/19/2021 10:15 AM - klopez) called client and gave him updates on project. (10/12/2021 11:34 AM - officestaff) permit submitted (10/08/2021 10:38 AM - klopez) validated info (10/05/2021 11:07 AM - lteniente) |  |  | (10) Completed need to inspect ( PM, OC) | Open | 2021-10-04 |  |  | lteniente |  |  | 2021-11-22 | lteniente | egomez | Jim Odabaschan | (956) 459-7836 | Isa6112@yahoo.com
7461 | C2955 | TITLEMAX LAREDO (by Gonzalez Auto Parts) | TITLEMAX LAREDO | 4316 SAN BERNARDO AVE | LAREDO | TX | 78041 | kelizondo | Low Slope Roof Systems | B. Roof Over Construction; A. Modified; D. Insurance Proceeds; E. Special Order | (09) IN PRODUCTION | 2021-11-17 | kelizondo | 2021-08-24 | 2021-11-23 | klopez |  | 51183.87 | 51183.87 | 18192.47 | 100 | REQUESTED BY PHILIP, I DID SPEAK WITH CESAR THE MANAGER AT THIS LOCATION AND HE DID SAY THEY HAD A PROBLEM WITH THE ROOF | 0 |  | 2021-11-17 | Self Generated | 0 | Also, Replacing metal coping caps |  | company | TITLEMAX LAREDO | LAREDO, TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-11-17 |  | permit has been submitted (11/23/2021 01:24 PM - klopez) |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-11-17 |  |  | lteniente |  |  | 2021-11-23 | lteniente | klopez | Julie Saathoff | (210) 392-0258 | julies@jlrsanjuantx.com
7437 | C2764 | RandR Ventures LLc Casa Padre | Casa Padre | 7480 Padre Island Hwy | Brownsville | TX | 78521 | lteniente | Low Slope Roof Systems | B. Roof Replacement; A. Coating Acylic Based; D. Retail Contract | (09) IN PRODUCTION | 2021-08-20 | lteniente | 2021-08-20 | 2021-11-16 | egomez |  | 56895.12 | 56895.12 | 28447.56 | 100 |  | 0 | lteniente | 2021-08-20 |  | 0 |  |  | company | Randr Ventures LLC | Brownsville, TX Office | Alfredo Villalobos |  |  | Commercial | n | [6 empty] | 2021-08-20 |  | Pending change order (11/16/2021 09:15 AM - egomez) permit uploaded (09/07/2021 11:09 AM - klopez) called client, didn't pickup. sent text message with status of project. (09/07/2021 11:04 AM - officestaff) permit paid for/ waiting on city to send over the permit. (09/07/2021 10:42 AM - klopez) permit submitted (09/01/2021 12:01 PM - klopez) called client, did not pickup. left voicemail with status of project. (08/25/2021 10:40 AM - officestaff) |  |  | (06) Schedule Labor | Open | 2021-08-20 |  |  | lteniente |  |  | 2021-11-16 | lteniente | egomez | Ryad Bakalem | (956) 561-1442 | Ryad@me.com
7425 | C2936 | Gonzalez Auto Parts- #9 Laredo | Gonzalez Auto Parts | 3518 Culebra Rd | San Antonio | TX | 78228 | anovack | Low Slope Roof Systems | B. Roof Replacement; B. Roof Over Construction; A. Metal; A. Modified; A. Coating Silicone Based; D. Retail Contract | (09) IN PRODUCTION | 2021-11-01 | pwesterman | 2021-08-19 | 2021-11-09 | klopez |  | 42695.33 | 42695.33 | 42595.33 | 100 | Several roof systems to work on | 0 |  | 2021-10-29 | Self Generated | 59000 |  |  | company | TITLEMAX LAREDO | LAREDO, TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-10-29 |  | permit uploaded (11/09/2021 11:20 AM - klopez) permit submitted (11/04/2021 12:20 PM - klopez) |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-10-29 |  |  | lteniente |  |  | 2021-11-04 | lteniente | klopez
7414 | R2599 | Castillo, Candida Residence | Castillo, Candida Residence | 27432 White Ranch Rd | La Feria | TX | 78559 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Metal ; D. Retail Contract | (09) IN PRODUCTION | 2021-09-03 | kelizondo | 2021-08-18 | 2021-10-26 | klopez |  | 9350 | 10225 | 5550 | 100 | Job Details: metal roof replacement, 1 story, yes leaks May I ask how you heard about us?: google Are there any leaks? if so, where?: yes and where not provided What type of roofing system do you have?: Metal Can't estimate | 0 |  | 2021-09-03 | Google | 0 |  |  | contact | Candida Castillo |  | José Rogelio Pina Miranda |  |  | Residential | n | [6 empty] | 2021-09-03 |  | pending change order (10/26/2021 02:01 PM - klopez) materials have already been ordered. (09/15/2021 04:33 PM - officestaff) permit submitted (09/13/2021 01:21 PM - klopez) verified info (09/09/2021 01:46 PM - lteniente) |  |  | (11) Punchout - Corrections | Open | 2021-09-03 |  |  | lteniente |  |  | 2021-10-07 | lteniente | kelizondo | Candida Castillo | (956) 331-9192 | jaime_davalos@yahoo.com
7397 | R2658 | Garza, Jorge Residence | Garza, Jorge Residence | 1037 Washington St. | Mission | TX | 78572 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-11-08 | kelizondo | 2021-08-17 | 2021-11-23 | kelizondo | 5053.52 | 5605.41 | 5605.41 | 3828.63 | 100 | Job Details: Estimate for roof replacement shingles not sure how old 1 story (hurricane damage) May I ask how you heard about us?: Saw a truck Are there any leaks? if so, where?: yes What type of roofing system do you have?: Shingles | 0 |  | 2021-11-08 | Moving Advertisement | 0 |  |  | contact | Jorge Garza |  | Victor Perez |  |  | Residential | n | [6 empty] | 2021-11-08 |  | VICTOR SAID JUST NOTICE IS INSURANCE PROCESS (11/23/2021 11:31 AM - kelizondo) VICTOR SAID JUST NOTICE IS INSURANCE PROCESS (11/23/2021 11:31 AM - kelizondo) By customer request please check in all house existing metal flashing. We will install if it does not have it or replace if it is in bad condition. (11/15/2021 06:23 PM - vperez) dropping off permit tomorrow (11/11/2021 11:57 AM - klopez) called back, verified info (11/09/2021 04:50 PM - lteniente) called, left a voicemail (11/09/2021 04:17 PM - lteniente) |  |  | (12) Ready to Invoice (Crystal) | Open | 2021-11-08 |  |  | lteniente |  |  | 2021-11-23 | lteniente | kelizondo | Jorge Garza | (956) 279-4614 | jpgarza1031@att.net
7396 | R2598 | ROGERS, CHARLES Residence | ROGERS, CHARLES Residence | 212 E Cowan Terrace, | Brownsville | TX | 78521 | kelizondo | Steep Slope Roof Systems | C. Additional Exterior Work; A. Tile (Concrete); B. Roof Repair; D. Retail Contract; C. Additional Carpentry | (09) IN PRODUCTION | 2021-09-08 | kelizondo | 2021-08-17 | 2021-11-02 | srivas |  | 10650 | 10650 | 5325 | 100 | Send in Link to pay by checking. Job Details: I NEED CONCRETE TILES FOR MY ROOF, AS WELL AS A GUTTER INSPECTION. May I ask how you heard about us?: GOOGLE Are there any leaks? if so, where?: ONE WAS PATCHED RECENTLY. A SMALL SECTION WAS LEAKING ON MY PATIO. What type of roofing system do you have?: Tile May I have the name of the commercial building please?: NONE | 0 |  | 2021-09-03 | Google | 0 |  |  | contact | Charles Rogers |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-09-03 |  | Jose V has started on this repair today (11/02/2021 10:55 AM - srivas) called client and gave him updates on project, requested permit to be emailed and sent him an email with the document attached. (09/27/2021 11:51 AM - officestaff) permit uploaded (09/17/2021 03:30 PM - klopez) permit submitted (09/15/2021 09:41 AM - klopez) verified info (09/09/2021 01:51 PM - lteniente) no longer pending payment (09/08/2021 08:45 AM - lteniente) no longer pending payment (09/08/2021 08:45 AM - lteniente) pending payment (09/03/2021 11:54 AM - lteniente) |  |  | (09) * Work In Progress | Open | 2021-09-03 |  |  | lteniente |  |  | 2021-10-12 | lteniente | rlerma | Charles Rogers | (503) 704-0201 | char_rogers_8@msn.com
7377 | C2881 | Aquiles Inc. (Clear Coat 3 exterior walls) | Aquiles Inc. | 3201 International Blvd, | Hidalgo | TX | 78557 | kelizondo | Exterior |  | (09) IN PRODUCTION | 2021-09-07 | pwesterman | 2021-08-15 | 2021-11-17 | egomez |  | 20420.58 | 20420.58 | 20420.58 | 100 | Going to clear coat, vapor barrier 3 walls | 0 |  | 2021-09-07 | Telemarketing | 0 |  |  | company | Aquiles Inc. | Hidalgo , TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-09-07 |  | spoke to Noe - materials should be arriving early next week. Also spoke to Jorge De La Pena and gave him an update - explained to him that due to the holiday we won't be able to start next week but that we are aiming to get him on the schedule for the following week (11/17/2021 12:15 PM - egomez) waiting for call back about labor to be scheduled please (11/16/2021 11:17 AM - kelizondo) as per Olanna from budget they are still waiting on ETA for these materials. Everything has been ordered. (10/26/2021 01:55 PM - klopez) P.o QC- 62834 Materials have been ordered from budget. ETA on materials is 2- 3 weeks (10/18/2021 04:36 PM - klopez) called client and gave updates on project. (09/16/2021 11:41 AM - officestaff) verified info (09/07/2021 04:51 PM - lteniente) no longer pending payment (09/07/2021 04:04 PM - lteniente) no longer pending payment (09/07/2021 04:04 PM - lteniente) pending payment (09/07/2021 10:55 AM - lteniente) Must be this product. Exactly as stated to work. It is special order. We do NOT need 15 gallon drums but rather 2 50 gallon drums or 15 5 gallon buckets (09/01/2021 05:17 PM - pwesterman) About 75 total SQs, 1 gallon per SQ because we will applying 2 coats, For 5 gallon drum cost roughly $200. Will need 15 drums. Can get this clear coat water vapor barrier from Sherwin Williams or other places. Must NOT go cheap as the cinder blocks are very porous and must be sealed (08/15/2021 01:04 PM - pwesterman) |  |  | (06) Schedule Labor | Open | 2021-09-07 |  |  | lteniente |  |  | 2021-10-18 | lteniente | klopez | Jorge "De la Pena " | (956) 843-8586 | jorge@aquilesinc.com
7371 | C2846 | Atlas Restoration / Goodwill Store | Goodwill Store | 702 Dixieland Road | Harlingen | TX | 78552 | wmitchell | Low Slope Roof Systems | A. TPO; B.Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-08-13 | kelizondo | 2021-08-13 | 2021-10-26 | klopez |  | 3400 | 5100 | 5100 | 100 |  | 0 |  | 2021-08-13 | Repeat | 0 |  |  | contact | Nick Forsell |  | Will Mitchell |  |  | Commercial | n | [6 empty] | 2021-08-13 |  | pending 2 - H-vac curbs need update from pm (10/26/2021 04:08 PM - klopez) Tentative start date 9/18 for Beto (09/15/2021 08:57 AM - egomez) tentative start date for 9/11 for beto. (09/10/2021 10:24 AM - officestaff) called client, did not pick up. will try again later. (08/18/2021 11:25 AM - officestaff) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-08-13 |  |  | lteniente |  |  | 2021-09-10 | lteniente | officestaff
7357 | C2860 | Burkett Dentistry | Burkett Dentistry | 1421 N 10th St, | McAllen, | TX | 78501 | kelizondo | Low Slope Roof Systems | C. Addtional Interior Work; A. Modified; A. Coating Acylic Based; D. Retail Contract | (09) IN PRODUCTION | 2021-08-26 | kelizondo | 2021-08-11 | 2021-11-10 | kelizondo |  | 15074.13 | 15074.13 | 15074.13 | 100 | Job Details: Estimate for repairs or replacement May I ask how you heard about us?: referral and google Are there any leaks? if so, where?: not sure Can't find on Nearmaps | 0 |  | 2021-08-23 | Referral | 0 |  |  | company | Burkett Dentistry | McAllen,, TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-08-23 |  | in the ceiling in the lobby (11/10/2021 02:37 PM - kelizondo) Joanne called and said we missed 2 mold spots (11/10/2021 02:34 PM - kelizondo) Joanne called and said we missed 2 mold spots (11/10/2021 02:34 PM - kelizondo) office manager Joanne said they're going to conduct a mold test first and then she'll be ready for a final inspection (11/04/2021 12:16 PM - kelizondo) working on interior today ( Gomez Crew) (11/01/2021 11:02 AM - bbuffamonte) called client didnt pick up. send her a text letting her know our crew is heading out today to work on interior. (11/01/2021 08:51 AM - klopez) Brian B spoke with client yesterday and both came to an agreement to start interior on 11/1 (10/26/2021 02:58 PM - klopez) scheduled tio for interior work on 11/1 (10/26/2021 02:56 PM - klopez) Called Joanna to schedule interior - no answer left voicemail. (10/25/2021 12:26 PM - egomez) called the client to let her know if we can send a crew to work on the interior work. Client Joanna declined wants 1-2 days of advance. (10/19/2021 08:33 AM - klopez) CUSTOMER CALLED, 2 CUSTOMERS ARE AHEAD FOR INTERIOR, THEY ASKED TO BE NOTIFIED AHEAD OF TIME (FROM AN ANONYMOUS #) WHEN INTERIOR WORK WILL BEGIN SO THEY CAN VACATE THE PROPERTY (10/12/2021 01:18 PM - kelizondo) Coating complete - pending interior (10/12/2021 09:00 AM - egomez) called client and gave him updates on project. (09/16/2021 11:34 AM - officestaff) permit is ready (09/13/2021 02:26 PM - klopez) permit submitted (09/01/2021 04:47 PM - klopez) they called back, verified info (08/30/2021 03:53 PM - lteniente) called to verify info, didnt pick up left a voicemail and text (08/30/2021 03:17 PM - lteniente) per philip, customer office manager Joanna Lopez 956 391 7364 will speak with erica (08/24/2021 01:58 PM - kelizondo) pending payment (08/23/2021 12:03 PM - lteniente) |  |  | (11) Punchout - Corrections | Open | 2021-08-23 |  |  | lteniente |  |  | 2021-11-10 | lteniente | kelizondo | Matthew Davis | (956) 429-8772 | matthewhoustondavis@gmail.com
7327 | C2833 | 7-Eleven # 41871 | 7-Eleven # 41871 | 1327 E. Interstate 2 | Mission | TX | 78572 | gsolis | Low Slope Roof Systems | B. Roof Replacement; A. PVC; D. Retail Contract | (09) IN PRODUCTION | 2021-08-05 | gsolis | 2021-08-05 | 2021-11-05 | egomez |  | 37616.88 | 37616.88 | 37616.88 | 100 |  | 0 |  | 2021-08-05 | Repeat | 0 |  |  | company | Helker & Crawford | Lewisville, TX Office | Gary Solis |  |  | Commercial | n | [6 empty] | 2021-08-05 |  | new construction site will not be ready until october per GC (08/08/2021 10:58 AM - gsolis) |  |  | (06) Schedule Labor | Open | 2021-08-05 |  |  | lteniente |  |  | 2021-11-05 | lteniente | egomez
7283 | R2552 | Lin, Rick Residence | Lin, Rick Residence | 1905 Hidden Pond Dr. | Palmhurst | TX | 78504 | kelizondo | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-10-20 | kelizondo | 2021-07-30 | 2021-10-20 | mmolano |  | 0 | 0 | 0 | 0 |  | 0 |  |  | Self Generated | 0 | [5 empty] | Joshua Rodriguez |  |  | Residential | n | [8 empty] | Client called, claims there is still a leak. (10/20/2021 02:32 PM - mmolano) |  |  | (11) Punchout - Corrections | [7 empty] | 2021-10-20 |  | mmolano | Rick Lin | (469) 658-9004 | ricklynn2@yahoo.com
7271 | R2573 | Daniels, John Residence | Daniels, John Residence | 104 NW Augusta Square, | McAllen | TX | 78503 | kelizondo | Exterior | Gutters | (09) IN PRODUCTION | 2021-08-11 | kelizondo | 2021-07-29 | 2021-08-26 | klopez |  | 1000 | 1000 | 500 | 100 | Job Details: Estimate for gutters & check on sidding wood (Customer wants the gutters on the west side of the house) he said to call him, he might not be there but call when on way, you can do inspection on your own . English speaker only | 0 |  | 2021-08-11 | Google | 0 |  |  | contact | John Daniels |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-08-11 |  | CALLED AND SPOKE WITH RAMIRO (08/24/2021 10:28 AM - kelizondo) verified info (08/11/2021 04:26 PM - lteniente) |  |  | (05) Order and Schedule Material | None | [6 empty] | 2021-08-26 | lteniente | klopez | John Daniels | (210) 232-2649 | restorevette@yahoo.com
7171 | R2633 | Guadalupe Prieto | Guadalupe Prieto | 408 E Emory Ave, | McAllen | TX | 78504 | kelizondo | Exterior | Windows | (09) IN PRODUCTION | 2021-10-22 | kelizondo | 2021-07-21 | 2021-11-19 | kelizondo |  | 6450 | 6450 | 3225 | 100 | Job Details: Code for the gate #5653. I would like an estimate for roof repair. It is causing leaks, mainly through the window. We manage the property. The owner is Guadalupe Prieto. Her phone number 956-605-7943. The roof is flat. I think it is a commercial roofing. May I ask how you heard about us?: my boss gave me your number, she has worked with you before. Are there any leaks? if so, where?: Yes, it is coming through the windows, as well as other places What type of roofing system do you have?: Shingles May I have the name of the commercial building please?: none | 0 |  | 2021-10-14 | Referral | 0 |  |  | contact | Ilse Barrera |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-10-14 |  | not completed: window installer needs to get back out there to finish, the windows are still leaking--text from roel about me not scheduling final inspection yet (11/19/2021 03:51 PM - kelizondo) called, didnt pick up, left a voicemail (10/22/2021 10:10 AM - lteniente) Budget Juan to build two windows= $2520 Seal windows = $1100 (10/08/2021 12:30 PM - rcantu ) Estimate to seal de roof and windows (07/22/2021 04:17 PM - kelizondo) |  |  | (11) Punchout - Corrections | Open | 2021-10-14 |  |  | lteniente |  |  | 2021-11-19 | lteniente | kelizondo | Ilse Barrera | (956) 340-5518 | management@rentnowrgv.com
7161 | C2874 | 7-11 Store # 42001 | 7-11 Store # 42001 | redwood & hwy 83 | rio grande | TX | 78582 | gsolis | Low Slope Roof Systems | B. New Roof Construction; A. Dura-Last; D. Retail Contract | (09) IN PRODUCTION | 2021-08-27 | gsolis | 2021-07-21 | 2021-10-26 | klopez |  | 28699.38 | 28699.38 | 28699.38 | 100 |  | 0 |  | 2021-08-27 | Referral | 0 |  |  | company | LaGrone Services | Houston, TX Office | Gary Solis |  |  | Commercial | n | [6 empty] | 2021-08-27 |  | delivery date for materials is : 11/05. (10/26/2021 12:13 PM - klopez) |  |  | (09) * Work In Progress | Open | 2021-08-27 |  |  | lteniente |  |  | 2021-10-12 | lteniente | egomez
7158 | R2592 | John Harper | HARPER, JOHN Residence | 19910 Encino Ridge St, | San Antonio | TX | 78259 | kelizondo | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-08-30 | kelizondo | 2021-07-20 | 2021-10-20 | kelizondo |  | 2116.8 | 2116.8 | 2116.8 | 100 |  | 0 |  | 2021-08-27 | Google | 0 |  |  | contact | JOHN HARPER |  | Orlando Marquez |  |  | Residential | n | [6 empty] | 2021-08-27 |  | LET MR AND MRS HARPER KNOW JUAN BRAVO WILL BE AT THE PROPERTY AROUND 3PM (10/20/2021 10:15 AM - kelizondo) Rollie sent text to Orlando on Oct.19 2021 To see whats status on this job. (10/19/2021 02:45 PM - rlerma) called client, didn't pickup. sent text message with status update. (09/03/2021 09:02 AM - officestaff) verified info when i took payment over the phone (08/30/2021 03:59 PM - lteniente) pending payment (08/27/2021 02:44 PM - lteniente) |  |  | (06) Schedule Labor | Open | 2021-08-27 |  |  | lteniente |  |  | 2021-10-12 | lteniente | rlerma | JOHN HARPER | (913) 558-4705 | JOHNOHARPER@GMAIL.COM
7107 | R2677 | Ornelas, Miguel Residence | Ornelas, Miguel Residence | 2432 Quince Ave, | McAllen | TX | 78501 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) IN PRODUCTION | 2021-11-23 | kelizondo | 2021-07-15 | 2021-11-24 | lteniente |  | 5250 | 5250 | 1030.13 | 100 |  | 0 |  | 2021-11-23 | Mail Outs | 0 |  |  | contact | Miguel Ornelas |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-11-23 |  | verified info, awaiting gaf (11/24/2021 02:28 PM - lteniente) |  |  | (01) Validate Info - (Leila) | Open | 2021-11-23 |  |  | lteniente |  |  | 2021-11-23 | lteniente | lteniente | Miguel Ornelas | (956) 618-5802 | no use of email
7086 | C2891 | Utility Trailer Sales South East Texas | Utility Trailer Sales South East Texas | 4320 Trade Center | Laredo | TX | 78041 | mmolano | Low Slope Roof Systems | A. Metal; A. TPO; B.Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-10-19 | mmolano | 2021-07-14 | 2021-11-10 | egomez |  | 10294.71 | 10294.71 | 5147.35 | 100 |  | 0 |  | 2021-09-15 | Repeat | 0 |  |  | company | Utility Trailer Sales South East Texas | Laredo , TX Office | Victor Perez |  |  | Commercial | n | [6 empty] | 2021-09-15 |  | called client to provide a status update. MAterials have been ordered BRS- QC- 62962 and QM- QC-62961 (11/02/2021 02:17 PM - klopez) permit uploaded (10/29/2021 04:54 PM - klopez) been in contact with city still under review (10/28/2021 03:01 PM - klopez) permit submitted. (10/20/2021 12:24 PM - officestaff) no longer pending (10/19/2021 03:53 PM - lteniente) pending payment (09/15/2021 11:11 AM - lteniente) |  |  | (06) Schedule Labor | Open | 2021-09-15 |  |  | lteniente |  |  | 2021-11-10 | lteniente | egomez | Richard Gamez | (956) 401-3284 | rgamez@utilitytrailers.com
7045 | R2558 | Kiscadon, Sharon Residence | Kiscadon, Sharon Residence | 27179 White Ranch Rd, | La Feria | TX | 78559 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Exterior Work; D. Retail Contract | (09) IN PRODUCTION | 2021-08-04 | kelizondo | 2021-07-12 | 2021-09-10 | rlerma |  | 10215 | 10215 | 5107.5 | 100 | Job Details: Estimate for roof replacement tile since 1978 wants to replace it with metal roof also needs wood repairs: soffit and facia She wants also inspection on a little house she owns next door. May I ask how you heard about us?: Google Are there any leaks? if so, where?: yes | 0 |  | 2021-08-04 | Google | 0 |  |  | contact | Sharon Kiscadon |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-08-04 |  | GUTTERS STILL NEED TO BE DONE (09/10/2021 09:18 AM - rlerma) MATERIALS HAVE BEEN ORDERED WITH QR-24470 (09/01/2021 12:34 PM - rlerma) PM SPOKE WITH CLIENT 08/30, HE WILL GO OUT 08/31 FTO MEET WOTH CLIENT FOR COLOR SELECTION (08/30/2021 06:49 PM - rlerma) waiting on pm for shingle color from om, pewter gray is not available, pm will speak to client to see if they will change shingle color. (08/20/2021 11:06 AM - rlerma) called client to update them on status of project. (08/10/2021 04:52 PM - officestaff) dont need permit (08/10/2021 09:04 AM - klopez) (08/04/2021 08:49 AM - jestrada ) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-08-04 |  |  | lteniente |  |  | 2021-09-10 | lteniente | rlerma | Sharon Kiscadon | (956) 640-3014 | srsagain@yahoo.com
7021 | R2541 | Abrego, Efren Residence | Abrego, Efren Residence | 5917 N 35th St | McAllen | TX | 78504 | rcantu | Low Slope Roof Systems | C. Addtional Exterior Work; A. Modified; B.Roof Repair | (09) IN PRODUCTION | 2021-09-14 | kelizondo | 2021-07-09 | 2021-11-02 | kelizondo |  | 2450 | 2450 | 1225 | 100 | Job Details: Customer wants an detailled inspection report with pictures $400 dlls charge he will pay by phone. May I ask how you heard about us?: google Are there any leaks? if so, where?: not sure What type of roofing system do you have?: Shingles | 0 |  | 2021-07-27 | Google | 0 | FASCIA BOARD NOT READY --9/10 |  | contact | Efren Abrego |  |  |  |  | Residential | n | [6 empty] | 2021-07-27 |  | ROEL SENT 6 PICTURES. CUSTOMER UNHAPPY WITH CARPENTRY. CEDAR FACIA HAS PAINT ON IT, WILL ROT SAID ROEL (11/02/2021 10:58 AM - kelizondo) called client to let them know that we are sending a crew out. did not pick up send a text couldnt leave voicemail (10/25/2021 08:47 AM - klopez) (09/14/2021 10:06 AM - Rcantu ) SCHEDULED HECTOR AND CREW FOR THIS THURSDAY WEATHER PERMITTING. (08/31/2021 03:00 PM - klopez) called the client letting him know about the tentative start date for 9/7. client was upset bc he wants his prj to be done sooner. let him know that we will double check our schedule and see if we can fine an earlier date to start. (08/30/2021 04:30 PM - klopez) CUSTOMER CALLED ASKING WHEN WORK WILL BEGIN, GAVE HIM ROEL CANTU'S PHONE NUMBER (08/30/2021 10:20 AM - kelizondo) called client and let them about tentative start date of project. (08/20/2021 12:22 PM - officestaff) tentative date 8/30-9/1 for hector (08/19/2021 03:52 PM - klopez) called client to let him know about status of project. (08/18/2021 10:40 AM - officestaff) CLIENT Called asking for an update, i advised her that its being processed through and will be checking on permit to see if it requires one. once i have confirmation client would like a call to be up to date. (07/30/2021 12:37 PM - klopez) |  |  | (11) Punchout - Corrections | Open | 2021-07-27 |  |  | lteniente |  |  | 2021-11-02 | lteniente | kelizondo | Efren Abrego | (956) 313-9752 | eabrego3@gmail.com
6935 | R2567 | Jester, William Residence | Jester, William Residence | 4910 Haven Oak, | San Antonio | TX | 78249 | kelizondo | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-08-17 | kelizondo | 2021-07-06 | 2021-08-17 | lteniente |  | 2972.59 | 2972.59 | 2972.59 | 100 | Job Details: we had a tree limb thAT FELL ON THE ROOF, AND WE NEED TO GET AN ESTIMATE TO GET PATCHED. May I ask how you heard about us?: ONLINE Are there any leaks? if so, where?: NO | 0 |  | 2021-08-09 | Google | 0 |  |  | contact | William Jester |  | Orlando Marquez |  |  | Residential | n | [6 empty] | 2021-08-09 |  | payment no longer pending (08/17/2021 03:56 PM - lteniente) pending payment (08/09/2021 10:04 AM - lteniente) |  |  | (06) Schedule Labor | Open | 2021-08-09 |  |  | lteniente |  |  | 2021-08-17 | lteniente | lteniente | William Jester | (210) 416-7028 | lsjester@gmail.com
6913 | R2507 | Estrada, Ruth & Uswaldo Residence | Estrada, Uswaldo Residence | 1400 Citrine Dr, | Weslaco | TX | 78596 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-07-06 | kelizondo | 2021-07-01 | 2021-09-07 | kelizondo |  | 8752.59 | 8752.59 | 1980 | 100 | Job Details: I am just looking to get an estimate on a roof replacement. May I ask how you heard about us?: internet Are there any leaks? if so, where?: no there is not. | 0 |  | 2021-07-06 | Google | 0 | Crystal, PLease send an invoice for the deductible to be paid upfront online |  | contact | Uswaldo Ruth Estrada |  | Philip Westerman |  |  | Residential | n | [6 empty] | 2021-07-06 |  | MATERIALS HAVE BEEN ORDERED WITH PO QR-24317 (08/18/2021 07:14 AM - rlerma) permit uploaded (08/05/2021 02:30 PM - klopez) called client. gave them status update on project. (08/04/2021 03:12 PM - officestaff) permit still under review (08/02/2021 03:42 PM - klopez) permit submitted (07/21/2021 09:24 AM - klopez) called, verified info, had no questions (07/08/2021 09:12 AM - lteniente) |  |  | (12) Ready to Invoice (Crystal) | Open | 2021-07-06 |  |  | lteniente |  |  | 2021-09-07 | lteniente | kelizondo | Uswaldo Ruth Estrada | (913) 309-1532 | usvaldovazquez@gmail.com
6912 | R2544 | Padilla, Juanita Residence | Padilla, Juanita Residence | 2717 madrid ave | Brownsville | TX | 78520 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-07-23 | kelizondo | 2021-07-01 | 2021-10-28 | mmolano |  | 8048.93 | 8048.93 | 1069.33 | 100 | Job Details: I need a roof repair,there's a roof leak & wind damage May I ask how you heard about us?: online | 0 |  | 2021-07-23 | Google | 0 |  |  | contact | Juanita Padilla |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-07-23 |  | MATERIALS HAVE BEEN ORDERED WITH QR-24301. FROM SOUTHERN SHINGLES (08/16/2021 03:22 PM - rlerma) SPOKE TO PM ABOUT HICKORY SHINGLE NOT BEING AVAILABLE, PM SAID HE WOULD SPEAK TO CLIENT (08/10/2021 02:01 PM - rlerma) permit uploaded (08/05/2021 04:18 PM - klopez) called client. gave them status update on project. (08/04/2021 03:19 PM - officestaff) permit was submitted on 08/02 still under review (08/04/2021 09:03 AM - klopez) verified info (07/27/2021 03:11 PM - lteniente) |  |  | (12B) Ready to Invoice Insurance (Crystal) | Open | 2021-07-23 |  |  | ctostado |  |  | 2021-10-28 | ctostado | mmolano | Juanita Padilla | (956) 346-7670 | janiepadilla1965@gmail.com
6873 | R2534 | Celia Cadena Residential | Celia Cadena Residential | 2606 Vicente St | Laredo | TX | 78046-6531 | dvazquez | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-08-03 | dvazquez | 2021-06-28 | 2021-10-28 | ctostado |  | 4066.26 | 4366.26 | 2642.89 | 100 |  | 0 |  | 2021-07-21 | Referral | 0 |  |  | contact | Rebeca Villarreal |  | Diane Vazquez |  |  | Residential | n | [6 empty] | 2021-07-21 |  | permit submitted (08/09/2021 03:09 PM - klopez) verified info (08/09/2021 10:20 AM - lteniente) no longer pending payment (08/03/2021 02:09 PM - lteniente) pending payment (07/21/2021 03:46 PM - lteniente) (07/20/2021 04:23 PM - dvazquez ) |  |  | (12B) Ready to Invoice Insurance (Crystal) | Open | 2021-07-21 |  |  | lteniente |  |  | 2021-10-28 | lteniente | ctostado | Rebeca "Villarreal " | (956) 251-6949 | r_villarreal_813@hotmail.com
6871 | C2853 | Del Rio Board of Realtors | Del Rio Board of Realtors | 127 Foster Dr. | Del Rio | TX | 78840 | kelizondo | Low Slope Roof Systems | B. Roof Replacement; A. TPO; D. Retail Contract | (09) IN PRODUCTION | 2021-08-23 | kelizondo | 2021-06-25 | 2021-09-23 | egomez | 34000.00; 13500.00 | 36805 | 36805 | 24905 | 100 | 08/18/2021 Emailed contract to Crystal and requested she make contact so that we can obtain the appropriate documentation for a non-taxable entity and copy of the first initial payment check. Contract is also uploaded in DF Docs and pricing notes in Budget Notes.-Diane 07/23/202160 Mil TPO Up to 54 Sqs (with waste): Material $8471.18 + Equipment $4362 + Taxes = $13891.92 + Labor $6481.20 = $20373.12/0.60= $33955.20. Dianes Material/Pricing Notes in Docs/Estimates.-Diane 06/29/2021 Material $159.77/SQ + Labor $150/SQ + Equip/Permit $54.55 =$364.32/.6 = $607.20/SQ X 22 SQ = $13358.40. Proposal of $13,500 if accepted by 7/31/2021.--Diane Customer wants estimate for repairs and is considering in the future to do a full roof renovation. | 0 |  | 2021-08-23 | Self Generated | 0 | 07/23/2021 60 Mil TPO Up to 54 Sqs (with waste): Material $8471.18 + Equipment $4362 + Taxes = $13891.92 + Labor $6481.20 = $20373.12/0.60= $33955.20. Diane's Material/Pricing Notes in Docs/Estimates.-Diane |  | company | Del Rio Board of Realtors | Del Rio , TX Office | Ed Vazquez |  |  | Commercial | n | [6 empty] | 2021-08-23 |  | permit is still in progress (09/13/2021 02:30 PM - klopez) permit submitted (09/01/2021 04:48 PM - klopez) submitted permit (09/01/2021 03:11 PM - klopez) called and left a voicemail (08/25/2021 05:02 PM - lteniente) |  |  | (09) * Work In Progress | Open | 2021-08-23 |  |  | lteniente |  |  | 2021-09-23 | lteniente | egomez | Karla Ponce | (830) 774-3320 | drboardofrealtors@stx.rr.com
6870 | R2516 | Martinez, Tammy Residence | Martinez, Tammy Residence | 6205 N 32nd St, | McAllen | TX | 78504 | kelizondo | Exterior | Windows | (09) IN PRODUCTION | 2021-07-08 | kelizondo | 2021-06-25 | 2021-07-20 | klopez |  | 5998 | 5998 | 2999 | 100 | Job Details: I am calling to get an estimate on gettng some new windows. | 0 |  | 2021-07-08 | Google | 0 |  |  | contact | Tammy Martinez |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-07-08 |  | windows have been ordered from specs P.O QR-24106 (07/20/2021 08:54 AM - klopez) Customer called to cancel 2 36x60 windows. The new price came out to $5379.00. That comes out to a credit of $619.00 (07/19/2021 05:01 PM - rcantu) Called, verified information, had no questions (07/08/2021 04:30 PM - lteniente) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-07-08 |  |  | lteniente |  |  | 2021-07-20 | lteniente | klopez | Tammy Martinez | (361) 480-4487 | tammymartinez7373@gmail.com
6789 | C2876 | Little Folks | Little Folks | 1233 Paseo Danubio | Laredo | TX | 78046 | kelizondo | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-09-01 | kelizondo | 2021-06-17 | 2021-11-01 | egomez |  | 4769.13 | 5364.13 | 5364.13 | 100 |  | 0 |  | 2021-09-01 | Repeat | 0 |  |  | contact | Diana Castillo |  | Victor Perez |  |  | Commercial | n | [6 empty] | 2021-09-01 |  | new tentative date on 10/4-10/8 for hector. (09/28/2021 11:25 AM - officestaff) called client, didn't pickup. left voicemail with tentative start date of project. (09/15/2021 12:52 PM - officestaff) disregard previous note, first tentative date on 9/24 for hector is correct. (09/15/2021 12:27 PM - officestaff) disregard previous note, tentative date is on 9/18 for beto. (09/15/2021 12:09 PM - officestaff) tentative date for hector on 9/24. (09/15/2021 09:57 AM - officestaff) outside of city limits, no permit needed. (09/10/2021 02:52 PM - officestaff) called client and gave them update on project. (09/01/2021 04:00 PM - officestaff) |  |  | (09) * Work In Progress | Open | 2021-09-01 |  |  | lteniente |  |  | 2021-11-01 | lteniente | egomez | Diana Castillo | (956) 462-9881 | dcastillo@webcountytx.gov
6740 | R2484 | Reynaldo Cantu | Cantu, Reynaldo Residence | 410 E 8th St | Weslaco | TX | 78596 | nsorrell | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-07-13 | nsorrell | 2021-06-13 | 2021-11-16 | mmolano |  | 8447.83 | 8447.83 | 1392.17 | 100 |  | 0 |  | 2021-07-13 |  | 0 |  |  | contact | Reynaldo Cantu |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-07-13 |  | MATERIALS HAVE BEEN ORDERED WITH PO QR-24313. (08/18/2021 02:39 PM - rlerma) MATERIALS HAVE BEEN ORDERED WITH PO QR-24313. (08/18/2021 02:39 PM - rlerma) called client to update them on status of project. (08/11/2021 09:55 AM - officestaff) permit uploaded (08/05/2021 02:29 PM - klopez) called client and let them know of status update on project. (08/04/2021 03:40 PM - officestaff) permit submitted (07/23/2021 10:48 AM - klopez) called verified info, had no questions (07/16/2021 11:53 AM - lteniente) no longer pending payment and insurance proceeds (07/13/2021 04:13 PM - lteniente) pending insurance proceeds, pending payment (06/20/2021 09:45 AM - lteniente) |  |  | (12B) Ready to Invoice Insurance (Crystal) | Open | 2021-07-13 |  |  | lteniente |  |  | 2021-11-16 | lteniente | mmolano | Reynaldo Cantu | (956) 854-5188 | Reynaldocnt@aol.com
6660 | R2532 | Anderson, Patrick Residence | Anderson, Patrick Residence | 107 E. Resaca Dr. | Los Fresnos | TX | 78566 | kelizondo | Exterior | Windows | (09) IN PRODUCTION | 2021-07-19 | kelizondo | 2021-06-08 | 2021-07-27 | klopez |  | 24456 | 24456 | 7336.8 | 100 | Estimate for 15 windows Pella shield Storm windows Insulated frame. Get info Bronze colored frame. Likes fiberglass or vinyl frame | 0 |  | 2021-07-19 | Google | 0 |  |  | contact | Patrick Anderson |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-07-19 |  | submitted window order to west end P.O QR- 24137 (07/27/2021 10:04 AM - klopez) (06/08/2021 02:54 PM - Rcantu ) (06/08/2021 02:30 PM - Rcantu ) (06/08/2021 02:25 PM - Rcantu ) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-07-19 |  |  | lteniente |  |  | 2021-07-27 | lteniente | klopez | Patrick Anderson | (956) 266-0719 | patricktanderson@yahoo.com
6653 | R2480 | Cascos, Rebecca Residence | Cascos, Rebecca Residence | 3 Ivy Lane | Brownsville | TX | 78521 | kelizondo | Exterior | Windows | (09) IN PRODUCTION | 2021-06-16 | kelizondo | 2021-06-07 | 2021-11-01 | kelizondo |  | 3499 | 3499 | 0 | 100 | Job Details: I would like to schedule and appointment to have all the windows replaced. My husbands name is Hugo cascos May I ask how you heard about us?: Internet Becky.cascos@gmail.com | 0 |  | 2021-06-16 | Google | 6998 |  |  | contact | Rebecca Cascos |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-06-16 |  | CUSTOMER PASSED AWAY (11/01/2021 09:07 AM - kelizondo) Submitted P.O to specs QR-23945 (06/23/2021 11:47 AM - klopez) called, verified info (06/21/2021 04:53 PM - lteniente) Customer has signed agreement and the agreement has been uploaded. Customer is going to be sending in ACH form through Docusign. (06/15/2021 03:03 PM - rcantu) (06/08/2021 04:06 PM - Rcantu ) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-06-16 |  |  | lteniente |  |  | 2021-06-25 | lteniente | klopez | Rebecca Cascos | (956) 371-6664 | becky.cascos@gmail.com
6633 | R2467 | Forshage, Alta Residence | Forshage, Alta Residence | 4025 Burns Ct, | McAllen | TX | 78503 | kelizondo | Low Slope Roof Systems | B. Roof Replacement; A. TPO | (09) IN PRODUCTION | 2021-06-10 | kelizondo | 2021-06-04 | 2021-09-15 | officestaff |  | 31500 | 31500 | 20475 | 100 | Job Details: Estimate for repairs flat roof wet spots May I ask how you heard about us?: google | 0 |  | 2021-06-09 | Google | 0 |  |  | contact | Alta Forshage |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-06-09 |  | called client, let them know we are still pending facia covers. told her i would speak to PM about project since she claimed it was finished. (09/15/2021 12:55 PM - officestaff) pending 11 pc facia cover (08/31/2021 10:13 AM - klopez) Edforshage@yahoo.com (08/24/2021 01:36 PM - Rcantu ) roof complete only pending fascia cover (08/06/2021 03:53 PM - egomez) #8693 (08/05/2021 11:54 AM - Rcantu ) jaime is being schedule for monday (07/28/2021 10:09 AM - klopez) Gate code #8693 (07/27/2021 09:56 AM - Rcantu ) called the client let him know about the tentative dates for 26-28th (07/19/2021 10:33 AM - klopez) didnt answer call, left a voicemail and text (06/14/2021 04:15 PM - lteniente) ACH waived (06/10/2021 03:55 PM - lteniente) pending Ach (06/09/2021 08:37 AM - lteniente) |  |  | (11) Punchout - Corrections | Open | 2021-06-09 |  |  | lteniente |  |  | 2021-08-31 | lteniente | klopez | Alta Forshage | (956) 369-1922 | no email
6599 | C2817 | Mission Consolidated Independent School District | Mission Consolidated Independent School District | 1201 bryce | mission | TX | 78572 | gsolis | Low Slope Roof Systems | A. Modified; B.Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-07-26 | gsolis | 2021-06-03 | 2021-10-26 | klopez |  | 57145.18 | 57145.18 | 57145.18 | 100 |  | 0 |  | 2021-07-26 | Repeat | 0 |  |  | company | NM Contracting | McAllen, TX Office | Gary Solis |  |  | Commercial | n | [6 empty] | 2021-07-26 |  | pending on general contractor to approve the mob bid and insulation. (10/26/2021 01:57 PM - klopez) need onsite visit to generate a material list (07/30/2021 10:25 AM - gsolis) |  |  | (05) Order and Schedule Material | Open | 2021-07-26 |  |  | lteniente |  |  | 2021-08-26 | lteniente | officestaff | Charles Anderson | (956) 499-8719
6583 | R2579 | Valdez, Henry Residence | Valdez, Henry Residence | 520 Medford Ave | Brownsville | TX | 78521 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds; C. Additional Carpentry | (09) IN PRODUCTION | 2021-08-16 | kelizondo | 2021-06-02 | 2021-10-06 | rlerma |  | 9079.33 | 9079.33 | 6799.73 | 100 | Job Details: Estimate for repairs or replacement Shingles 16yrs old 1 story loose & missing shingles leaks up front soffit through fascia too. May I ask how you heard about us?: Anita & Ruben Evangelista (Juan EStradas customer) Are there any leaks? if so, where?: yes leaks up front soffit through fascia too. | 0 |  | 2021-08-16 | Referral | 0 |  |  | contact | Henry Valdez |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-08-16 |  | WORK WOOD BEGINS TODAY (10/06/2021 08:51 AM - rlerma) THE ROFF HAS BEEN DONE, STILL PENDING WOOD WORK (09/10/2021 09:31 AM - rlerma) MATERIALS HAVE BEEN ORDERED WITH QR-24419 (08/27/2021 11:59 AM - rlerma) permit uploaded (08/24/2021 08:58 AM - klopez) called client, did not pickup. sent text message with status of update. (08/23/2021 11:30 AM - officestaff) permit uploaded (08/18/2021 11:43 AM - klopez) verified info (08/17/2021 10:41 AM - lteniente) |  |  | (09) * Work In Progress | Open | 2021-08-16 |  |  | lteniente |  |  | 2021-10-06 | lteniente | rlerma | Henry Valdez | (956) 640-9399 | valdezhenry19@yahoo.com
6574 | C2781 | Fort Ringgold | Fort Ringgold | 1 s Ringgold st | Rio Grande | TX | 78582 | gsolis | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) IN PRODUCTION | 2021-06-23 | gsolis | 2021-06-02 | 2021-11-17 | srivas |  | 92147.81 | 92147.81 | 92147.81 | 100 |  | 0 |  | 2021-06-22 | Referral | 0 |  |  | company | NM Contracting | McAllen, TX Office | Gary Solis |  |  | Commercial | n | [6 empty] | 2021-06-22 |  | republic services is scheduled for pick up 11/19. (11/17/2021 03:20 PM - srivas) put on hold due to shingle color and style not available. (07/14/2021 04:24 PM - officestaff) permit uploaded (07/13/2021 10:33 AM - klopez) permit approved. called the city the dept was closed advised me to call monday to pay (07/09/2021 04:18 PM - klopez) submitted permit (07/06/2021 10:12 AM - klopez) |  |  | (09) * Work In Progress | Open | 2021-06-22 |  |  | lteniente |  |  | 2021-09-01 | lteniente | officestaff
6568 | R2488 | Gomez, Oscar Residence | Gomez, Oscar Residence | 102 Odis St | San Antonio | TX | 78211 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) IN PRODUCTION | 2021-09-09 | kelizondo | 2021-06-01 | 2021-11-01 | srivas |  | 5372.85 | 5372.85 | 2686.42 | 100 | Job Details: Message: Hello, Last year your company installed a new roof on my house here in San Antonio, TX. I would like an inspection on my Father Home, his roof has a small leak and hail damage. I would like to get it replaced as well. * Wants replacement on the roof for the small shed & laundry room too. His address is: 102 Odis Street San Antonio, Tx 78204 His father is Spanish speaker but asked to call him when you arrive so he can explain you what he wants. Can't find on Maps | 0 | ctostado | 2021-09-02 | Google | 0 |  |  | contact | Oscar Gomez |  | Orlando Marquez |  |  | Residential | n | [6 empty] | 2021-06-21 |  | wood work and painted pending. Rollie will contact labor. (11/01/2021 03:18 PM - srivas) contact orlys san antonio sub to do 50ft of facsia and paint (11/01/2021 03:16 PM - r_lopez) As per client- There were items in the contract that weren’t replaced and some items that need to be repaired. (09/09/2021 08:23 AM - mmolano) MATERIALS HAVE BEEN ORDERED WITH QR-24158, CLIENT IS AWARE SINHLE WAS GARD TO FIND, PENDING HIP/RIDGE FROM VENDOR FOR DELIVERY (07/29/2021 07:50 AM - rlerma) SPOKE TO CLIENT ADVISED THAT THERE NO COLOR FOR DRIP EDGE AND SHINGLE COLOR (07/01/2021 02:03 PM - rlerma) |  |  | (11) Punchout - Corrections | Completed | 2021-06-21 | 2021-09-02 |  | lteniente | ctostado |  | 2021-09-09 | ctostado | mmolano | Oscar Gomez | (210) 897-3950 | ogomezenriquez@gmail.com
6564 | R2504 | Trevino, Jose Residence | Trevino, Jose Residence | 1538 S Virginia Ave, | Mercedes | TX | 78570 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-07-06 | kelizondo | 2021-06-01 | 2021-11-16 | mmolano |  | 5294.88 | 5294.88 | 5294.88 | 100 | Job Details: I need an estimate for replacing the roof and to discuss the different options of roofing matieral May I ask how you heard about us?: online Are there any leaks? if so, where?: kitchen/living room area and daughter's room What type of roofing system do you have?: Shingles | 0 |  | 2021-07-06 | Google | 0 |  |  | contact | Jose Trevino |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-07-06 |  | MATERIALS HAVE BEEN ORDERED WITH QR-24206, CLIENT AND PM ARE AWARE. DELIVERY WILL BE 08/06 (08/05/2021 09:16 AM - rlerma) permit has been approved and paid... need to pick up the permit (07/23/2021 10:10 AM - klopez) have been reaching out to the city to check on status. has not yet been approved. (07/20/2021 10:10 AM - klopez) permit has been submitted (07/12/2021 05:26 PM - klopez) called, verified info (07/08/2021 04:48 PM - lteniente) (06/30/2021 09:02 AM - jestrada ) |  |  | (12B) Ready to Invoice Insurance (Crystal) | Open | 2021-07-06 |  |  | lteniente |  |  | 2021-11-16 | lteniente | mmolano | Jose Trevino | (956) 998-8225 | joetlaw@yahoo.com
6540 | R2464 | Chavana, Romeo Residence | Chavana, Romeo Residence | 20005 Fallow Ln | Edinburg | TX | 78542 | ctostado | Steep Slope Roof Systems | B. Roof Replacement; A. Metal ; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-06-09 | ctostado | 2021-05-27 | 2021-11-15 | mmolano |  | 6750.94 | 6750.94 | 2864.94 | 100 |  | 0 |  | 2021-06-09 |  | 0 |  |  | contact | Romeo Chavana |  | Philip Westerman |  |  | Residential | n | [6 empty] | 2021-06-09 |  | confirmed with philip to move to invoice 10/28 (10/28/2021 09:47 AM - kelizondo) Pending base board. Item is discontinued. (10/18/2021 03:54 PM - egomez) erika is waiting on custom base board (10/18/2021 03:53 PM - rlerma) Pending Interior (09/15/2021 08:55 AM - egomez) gate code : #3939 (08/13/2021 10:12 AM - klopez) spoke with sergio to check on ETA has yet to get an update will reach back to me today with an ETA (07/20/2021 10:00 AM - klopez) spoke with vendor still has not received coils and is working on getting the ETA (07/07/2021 03:27 PM - klopez) called client letting him know that we still dont have an eta on materials as soon as we do we will update him. (06/25/2021 10:24 AM - klopez) Materials have been ordered. Need to have a pre-construction meeting with Metal Fabricator (Julio) on site (06/23/2021 12:35 PM - egomez) CALLED THE CLIENT LET HIM KNOW THAT THE MATERIALS HAVE BEEN ORDERED DUE TO THE COLOR IT WILL BE TAKING ABOUT 2-3 WEEKS AS ITS SPECIAL ORDER. CLIENT WAS UNDERSTANDING. (06/21/2021 02:26 PM - klopez) CALLED THE CLIENT LET HIM KNOW THAT THE MATERIALS HAVE BEEN ORDERED DUE TO THE COLOR IT WILL BE TAKING ABOUT 2-3 WEEKS AS ITS SPECIAL ORDER. CLIENT WAS UNDERSTANDING. (06/21/2021 02:26 PM - klopez) submitted p.o for materials to Quality Metals P.O QR-23931 (06/21/2021 12:38 PM - klopez) no permit needed (06/21/2021 09:45 AM - klopez) called the client to give him an update. letting him know that the permit has been submitted and we are pending approval. As well Erika is ordering panels as well. (06/16/2021 08:43 AM - klopez) permit submitted. (06/15/2021 09:18 AM - klopez) need sub to go out for cut list (06/10/2021 01:55 PM - gsolis) customer answered the phone (06/10/2021 08:20 AM - lteniente) not pending payment, pending insurance (06/08/2021 10:17 AM - lteniente) pending payment (06/08/2021 10:14 AM - lteniente) |  |  | (12B) Ready to Invoice Insurance (Crystal) | Open | 2021-06-09 |  |  | lteniente |  |  | 2021-11-15 | lteniente | mmolano | Romeo Chavana | (956) 279-9844 | rchavana3@gmail.com
6454 | R2574 | Salinas, Dana Residence | Salinas, Dana Residence | 13502 23rd Lane | Ediburg | TX | 78541 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) IN PRODUCTION | 2021-08-11 | kelizondo | 2021-05-21 | 2021-11-21 | srivas |  | 16875.67 | 16875.67 | 4892.81 | 100 | Job Details: Estimate for roof replacement May I ask how you heard about us?: referal Rober Callaway | 0 |  | 2021-08-11 | Referral | 0 |  |  | contact | Dana Salinas |  | Victor Perez |  |  | Residential | n | [6 empty] | 2021-08-11 |  | Jose avila friend will be doing the work. Client wants them to start on 11/29 (11/21/2021 08:54 PM - srivas) waiting for javier to get back to us to start (11/15/2021 11:06 PM - srivas) Rollie has been calling javier no answer (11/02/2021 04:03 PM - srivas) only pending interior work Kitchen cabinets (10/11/2021 02:20 PM - klopez) La pintura es en los gabinetes de madera de la cocina y puerta de Salida al jardin (09/21/2021 09:31 PM - vperez) Material List of Kitchen Wood Paint : 1) 5 Galones de Primer 2) 5 Galones de Pintura de Aceite 3) 1 Caja de coking 4) 1 Caja o rollo de Plastico para cubrir gabinetes. 5) 2 Rollos de Tape. 6) 1 Galon de Paint Thinner 7) 1 Paquete de Lija del Numero 120 Costo de Mano de Obra de Javi Covarrubias $ 1,500 Tiempo de ejecucion : 10 Dias Habiles. (09/21/2021 09:30 PM - vperez) outside city limits (08/18/2021 10:40 AM - klopez) verified info (08/17/2021 10:42 AM - lteniente) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-08-11 |  |  | lteniente |  |  | 2021-11-01 | lteniente | srivas | Dana Salinas | (956) 655-7152 | danasal7@outlook.com
6441 | C2845 | KEYSTONE APARTMENTS | KEYSTONE APARTMENTS | 1409 W. Business 83 | Westlaco | TX | 78596 | mmolano | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) IN PRODUCTION | 2021-08-23 | mmolano | 2021-05-20 | 2021-10-11 | klopez |  | 216243 | 216243 | 108121.49 | 100 | Very Important that we do units these first!!!!! 9 , 6 , 5 and then 3. In that order please. That are in dire need and customer was told we can accommodate. | 0 |  | 2021-08-13 | Repeat | 0 | Billing***** Communicate with the district Manager with this information: Not with the one on the contract: Stacy: stacy@wls-inc.com 713-907-7060 |  | contact | Gaby Guerra |  | Philip Westerman |  |  | Residential | n | [6 empty] | 2021-08-13 |  | melo crew is working on this prj (10/11/2021 02:23 PM - klopez) permit uploaded (09/22/2021 04:40 PM - klopez) permit has been approved need to go the city hall and pay (09/21/2021 12:17 PM - klopez) permit submitted. (09/13/2021 03:54 PM - officestaff) materials have been ordered with QC-6248 AND QC-62377 (09/13/2021 09:53 AM - rlerma) called, no response. no option for voicemail in answering machine. (09/07/2021 12:04 PM - officestaff) called, didnt answer, there wasnt an option for a voicemail and rang for a long time might be a landline (08/25/2021 05:00 PM - lteniente) no longer pending payment (08/23/2021 09:23 AM - lteniente) pending payment (08/13/2021 08:28 AM - lteniente) Communicate with the district Manager with this information: Not with the one on the contract: Stacy: stacy@wls-inc.com 713-907-7060 (08/12/2021 05:06 PM - pwesterman) Very Important that we do units these first!!!!! 9 , 6 , 5 and then 3. In that order please. That are in dire need and customer was told we can accommodate. (08/12/2021 04:55 PM - pwesterman) Owen's Corning: Weathered Wood (08/12/2021 04:52 PM - pwesterman) |  |  | (09) * Work In Progress | Open | 2021-08-13 |  |  | lteniente |  |  | 2021-10-11 | lteniente | klopez | Gaby Guerra | (956) 447-3100 | ksasst@ wlsapts.com
6409 | R2465 | Gonzalez, Sergio Residence | Gonzalez, Sergio Residence | 3217 Sunbow Ln | McAllen | TX | 78504 | kelizondo | Exterior | Windows | (09) IN PRODUCTION | 2021-06-08 | kelizondo | 2021-05-19 | 2021-08-16 | gsolis |  | 2430 | 2430 | 1579.5 | 100 | Job Details: I am calling for an estimate for repair or replacement for windows. 5 win or more | 0 |  | 2021-06-08 | Google | 0 |  |  | contact | Sergio Gonzalez |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-06-08 |  | they called back today, verified information (06/14/2021 10:17 AM - lteniente) didn't pick up the phone, left a voicemail and a text message (06/10/2021 08:21 AM - lteniente) submitted P.O to specs QR-23853 (06/09/2021 04:21 PM - klopez) |  |  | (05) Order and Schedule Material | Open | 2021-06-08 |  |  | lteniente |  |  | 2021-08-16 | lteniente | gsolis | Sergio Gonzalez | (956) 777-5154 | sergiogzz213@gmail.com
6386 | R2503 | Edwards, Enedelia Residence | Edwards, Enedelia Residence | 508 N 13th St | Donna | TX | 78537 | kelizondo | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-06-30 | kelizondo | 2021-05-18 | 2021-10-19 | kelizondo |  | 1598.21 | 1598.21 | 1598.21 | 100 | Job Details: Estimate for roof repairs shingles 10 yrs old 1 story started claim but not sure if will go with insurance leaks yes Needs estimate ASAP Shingles lifted, wind damage | 0 |  | 2021-06-30 | Google | 0 |  |  | contact | Enedelia Edwards |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-06-30 |  | got with juan let mek now that the change order has been made and send to ramiro a while back, will remove from hold to move forward. (10/11/2021 01:50 PM - klopez) need change order from pm (07/22/2021 09:35 AM - gsolis) need areal view of areas where work is to be done, notified noah on 7/2 (07/06/2021 08:13 AM - gsolis) called, verified info, had no questions (07/02/2021 11:42 AM - lteniente) |  |  | (12) Ready to Invoice (Crystal) | Open | 2021-06-30 |  |  | lteniente |  |  | 2021-10-19 | lteniente | kelizondo | Enedelia Edwards | (956) 239-0928 | eedwards2@yahoo.com
6340 | R2660 | Conner, David Residence | Conner, David Residence | 1318 Tierra Santa St | Weslaco | TX | 78596 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Tile (Concrete); D. Insurance Proceeds | (09) IN PRODUCTION | 2021-11-09 | kelizondo | 2021-05-13 | 2021-11-21 | srivas | 56243.97 | 59393 | 59393 | 17155.36 | 100 | Job Details: Estimate for roof repairs Tile, 24 yrs old 1 story not sure of leaks storm and water damage May I ask how you heard about us?: repeat customer form 6 yrs ago. | 0 |  | 2021-11-09 | Google | 56243.97 |  |  | contact | David Conner |  | Victor Perez |  |  | Residential | n | [6 empty] | 2021-11-09 |  | Material will be delivered Monday 11/22 by noon. client said that westend can del material on one side of the driveway. i did mention to him that material will be there for a while due to our schedule being full at the moment. he said it was fine. (11/21/2021 10:29 PM - srivas) verified info (11/09/2021 04:14 PM - lteniente) need to order take off from vendor send the gaf for materials order (11/09/2021 04:11 PM - gsolis) |  |  | (05) Order and Schedule Material | Open | 2021-11-09 |  |  | lteniente |  |  | 2021-11-15 | lteniente | srivas | David Conner | (956) 245-7756 | david@mrzink.com
6306 | C2747 | Motel 6 Del Rio | Motel 6 Del Rio | 2115 Veterans Blvd | Del Rio | TX | 78840 | dvazquez | Low Slope Roof Systems | B. Roof Replacement; A. Coating Acylic Based; A. Dura-Last; D. Retail Contract | (09) IN PRODUCTION | 2021-06-02 | dvazquez | 2021-05-12 | 2021-10-08 | egomez | 217400 | 235335.5 | 228241.6 | 145874.17 | 100 | 05/25/2021 Emailed customer PDF binder info with proposal. Customer texted confirmation of receipt. States it normally takes about 5 business days for approval. -Diane 05/24/2021 Customer would like paperwork for both PVC & Mansard wall projects for a total of $217,400.-Diane 05/24/2021 Alfredo approved retails prices/sq.-Diane 05/21/2021 Insurance Proposal Presented as per Gatekeeper. Decision Maker stated it needed to be retail. Our proposal was 40% above everyone else so about ($211K). Made arrangements for late Monday appt.-Diane | 0 |  | 2021-06-01 | Moving Advertisement | 0 | 05/24/2021 Alfredo Approved $700/Sq for PVC Up to 242sq (includes warranty fees, boom, scizzerlift, dump, coping cap,etc) and Mansard Shingles Up to 96 at $500/sq.--Diane |  | company | Del Rio Hotel Group LLC | Rancho Cucamonga, CA Office | Ed Vazquez |  |  | Commercial | n | [6 empty] | 2021-06-01 |  | as per duro- last delivery changed from 9/16 - 9/22 (08/26/2021 12:49 PM - klopez) pending duro-last (07/28/2021 10:04 AM - klopez) Diane uploaded permit. (06/18/2021 09:52 AM - klopez) Permit has been submitted (06/17/2021 04:25 PM - klopez) eagle view uploaded (06/15/2021 08:11 AM - klopez) ordered eagle view (06/14/2021 04:32 PM - klopez) the city of Del rio emailed me letting me know that i would have to mail the permit and contractors registration. As of today we a re just waiting for the insurance info that crystal is getting for me. once having that I will mail the permit. (06/14/2021 09:56 AM - klopez) finally got through to the permit department submitted permit. (06/11/2021 11:29 AM - klopez) been calling the city of del rio to get an email address to submit the permit. they are always busy and when leaving a call back number i never hear from them. (06/10/2021 02:10 PM - klopez) payment no longer pending (06/02/2021 08:33 AM - lteniente) pending payment shingles included (06/01/2021 03:58 PM - lteniente) |  |  | (09) * Work In Progress | Open | 2021-06-01 |  |  | lteniente |  |  | 2021-10-08 | lteniente | egomez | Melissa Gonzalez | (830) 320-1919 | Jimini1948@Gmail.com
6244 | R2448 | Alleen Koch | Alleen Koch Residence | 1910 22nd St | Hondo | TX | 78861 | nsorrell | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-06-02 | nsorrell | 2021-05-05 | 2021-11-05 | srivas |  | 0 | 0 | 0 | 0 |  | 0 |  |  | Self Generated | 0 | [5 empty] | Juan Estrada |  |  | Residential | n | [8 empty] | Pending gutters & chim. cap as per juan said he needs to go out there. (11/05/2021 02:28 PM - srivas) tried to call client, number out of service/not working. (08/11/2021 09:44 AM - officestaff) disreguard note (08/11/2021 08:22 AM - r_lopez) need pictures and counts of pipe stacks, 750s, ridge vensts etcs..... (08/11/2021 08:20 AM - r_lopez) no insurance proceeds (05/28/2021 08:54 AM - lteniente) Claim rep- Don Bernshausen 800-222-4736 ex 1072 Calim # 9639649. (05/11/2021 01:38 PM - nsorrell) |  |  | (09) * Work In Progress | [7 empty] | 2021-11-05 |  | srivas | Alleen Koch | (830) 426-2345
6224 | C2694 | Sea Vista Condominiums I | Sea Vista Condominiums | 110 Padre Blvd, | South Padre Island | TX | 78597 | kelizondo | Low Slope Roof Systems | B. Roof Over Construction; A. Coating Silicone Based; D. Retail Contract; E. Special Order | (09) IN PRODUCTION | 2021-05-10 | pwesterman | 2021-05-04 | 2021-11-10 | egomez |  | 70699.25 | 70699.25 | 45954.51 | 100 | Job Details: Routine Maintenance handling? No What is your square footage? 83,520 How many stories is your roof? 2 buildings 6 stories, 2 building office What is the age of your roof? na When was the last time inspected or restored? na Will we be inspecting more than 1 facility? yes 4 Any current issues? has leaks office building Any emergency repairs needed? yes Have you contacted your insurance? no If no external access- who can we meet for internal access? See Martha the office building has leaking brick roof, The 6 story building wants to have looked at, not sure if it has leaks in coating. | 0 |  | 2021-05-04 | Telemarketing | 70000 |  |  | company | Sea Vista Condominiums | South Padre Island , TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-05-04 |  | called client to let her know about the status update. Materials have been ordered BRS - QC-62970 and HD - QC-62972 (11/02/2021 03:26 PM - klopez) called client to find out availability, said that philip has been in discussion with one of the higher ups of the company for a time frame. (08/30/2021 11:50 AM - officestaff) called the client to let her know about the updates that are happening, left a message with an associate. (06/28/2021 05:11 PM - klopez) prj on hold as per p.m (06/07/2021 03:49 PM - klopez) does not require permit for coating (05/26/2021 04:14 PM - klopez) 05/14 submitted permit (05/18/2021 09:27 AM - klopez) scheduled beto 05/27-06/11 (05/17/2021 04:31 PM - klopez) low slope no gaf measurements (05/10/2021 04:47 PM - lteniente) |  |  | (05) Order and Schedule Material | Open | 2021-05-04 |  |  | lteniente |  |  | 2021-11-10 | lteniente | egomez | Martha "Neri " | (956) 761-5526 | seavistacondos@aol.com
6204 | R2471 | Velez, Lesly & Frank | Velez, Lesly Residence | 3501 Oak Ridge Ln. gate code: #5735 | Mission | TX | 78573 | pwesterman | Exterior | Gutters | (09) IN PRODUCTION | 2021-06-14 | kelizondo | 2021-05-03 | 2021-07-22 | gsolis |  | 100 | 100 | 0 | 100 |  | 0 |  | 2021-06-14 | Google | 0 |  |  | contact | Lesly & Frank Velez |  | Philip Westerman |  |  | Residential | n | [6 empty] | 2021-06-14 |  | project will be treated as work order (07/22/2021 09:47 AM - gsolis) spoke to pm. need to install 3 new scuppers and identify if there is any rotted wood underneath (07/02/2021 10:19 AM - egomez) Remove the collection box and downspout. and see where it is leaking into the wood from (06/08/2021 05:42 PM - pwesterman) |  |  | (14) Project on Hold | Open | 2021-06-14 |  |  | lteniente |  |  | 2021-07-22 | lteniente | gsolis | Lesly & Frank Velez | (813) 787-3252
6088 | C2691 | Los Compadres | Los Compadres | 1012 S Closner Blvd | Edinburg | TX | 78542 | kelizondo | Low Slope Roof Systems | B. Roof Over Construction; A. Dura-Last; D. Retail Contract | (09) IN PRODUCTION | 2021-05-04 | kelizondo | 2021-04-21 | 2021-09-15 | egomez | 1924.18; 1291.87; 12068.36 | 15958.83 | 15958.83 | 7988.63 | 100 | Techs will be on site this afternoon | 0 |  | 2021-05-04 | Referral | 0 |  |  | company | Los Compadres | Edinburg , TX Office | Will Mitchell |  |  | Commercial | n | [6 empty] | 2021-05-04 |  | rescheduled hector for 8/31 (08/27/2021 10:08 AM - klopez) pending drains for hector (08/26/2021 12:31 PM - klopez) pending 2 drains (08/16/2021 09:20 AM - klopez) rescheduled ramon for 07/12-07/16 called the client to let her know about changes (07/06/2021 03:11 PM - klopez) eta ON MATERIALS 06/22 (06/18/2021 01:27 PM - klopez) materials have been ordered (06/07/2021 03:13 PM - egomez) scheduled ramon for 05/27-06/02 (05/17/2021 04:24 PM - klopez) uploaded permits (05/15/2021 02:19 PM - klopez) submitted permit (05/06/2021 12:36 PM - klopez) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-05-04 |  |  | lteniente |  |  | 2021-08-26 | lteniente | klopez | Nidia Villarreal | (956) 279-4331 | medaid@gmail.com
6059 | R2561 | Weber Trusty, Chelsea Residence | Weber Trusty, Chelsea Residence | 1700 Casanova Ave, | Pflugerville, | TX | 78660 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Interior Work; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-08-06 | kelizondo | 2021-04-19 | 2021-11-21 | srivas |  | 19964.02 | 19964.02 | 4801.92 | 100 |  | 0 |  | 2021-08-06 | Self Generated | 0 | I'm bringing in the insurance Check on Wednesday |  | contact | Chelsea Weber Trusty |  | Philip Westerman |  |  | Residential | n | [6 empty] | 2021-08-06 |  | Approved by Alfredo; Sending Juan B & Jerry on Monday to do interior work (11/12/2021 09:47 AM - srivas) got with Jannette to see if she can head out to this location and give us a price on the interior work pending. (10/28/2021 07:46 AM - srivas) roof has been finalized, but the interior is still pending. client is aware that we are actively looking for an interior guy. (10/06/2021 07:11 AM - rlerma) MATERIALS HAVE BEEN ORDERED WITH PO QR-24331 (08/18/2021 02:36 PM - rlerma) called client, gave them update on status of project. (08/16/2021 12:44 PM - officestaff) she called back,verified info (08/09/2021 11:06 AM - lteniente) typed verified info by accident, she didnt pick up when called, i left a voicemail and text message (08/09/2021 10:53 AM - lteniente) verified info (08/09/2021 10:32 AM - lteniente) no longer pending payment or insurance (08/06/2021 03:20 PM - lteniente) We ARE doing the interior work! (08/04/2021 04:40 PM - pwesterman) pending insurance, pending payment (08/04/2021 02:48 PM - lteniente) Let's schedule the tiny interior work right away (08/03/2021 02:32 PM - pwesterman) |  |  | (12) Ready to Invoice (Crystal) | Open | 2021-08-06 |  |  | lteniente |  |  | 2021-11-21 | lteniente | srivas | Chelsea Weber Trusty | (618) 530-2857 | chelseatrusty18@gmail.com
6058 | R2528 | McNierney, Patrick Residence | McNierney, Patrick Residence | 16701 Dumas St. | patrick.mcnierney@gmail.com | TX | 78660 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-07-22 | kelizondo | 2021-04-19 | 2021-10-28 | mmolano |  | 27099.86 | 27099.86 | 3858 | 100 |  | 0 |  | 2021-07-16 | Self Generated | 0 |  |  | contact | Patrick McNierney |  | Philip Westerman |  |  | Residential | n | [6 empty] | 2021-07-16 |  | I haven't heard back from them about it, but did so have some qualms with regards to additional damage to metal roof above office and some of elements that stop water overflowing from the previous roofline are all bent up. There's some scratches on the gutters from ladders too. Also, did we install those solar vents we talked about? Patrick McNierney: Pflugerville (10/20/2021 01:06 PM - pwesterman) delivery today (08/02/2021 09:46 AM - klopez) called, verified info (07/22/2021 04:10 PM - lteniente) no longer pending ACH, still pending payment (07/16/2021 12:16 PM - lteniente) pending payment, pending ACH (07/16/2021 12:08 PM - lteniente) |  |  | (12B) Ready to Invoice Insurance (Crystal) | Open | 2021-07-16 |  |  | lteniente |  |  | 2021-10-28 | lteniente | mmolano | Patrick McNierney | (303) 579-7641 | patrick.mcnierney@gmail.com
6010 | R2427 | Sharpless, Joshua Residence | Sharpless, Joshua Residence | 1505 Goldcrest Ave | McAllen | TX | 78504 | kelizondo | Exterior | Windows | (09) IN PRODUCTION | 2021-05-12 | kelizondo | 2021-04-14 | 2021-11-18 | klopez |  | 1632.78 | 1632.78 | 816.39 | 100 | Replace 3 Windows Job Details: I have three windows I would like an estimate for. We are remodeling the kitchen now and would like to have the window done as soon as possible. | 0 |  | 2021-05-12 | Google | 0 |  |  | contact | Joshua Sharpless |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-05-12 |  | called the client let him know that we have been in contact with oscar from mccoys for the ETA on windows nothing has changed (11/18/2021 11:21 AM - klopez) TALKED TO OSCAR AT MCCOYS, SAID HE'LL CALL BACK, HIS NOTES SAY NOV. 11 IS ETA. WILL KEEP POSTED OF COURSE. SHARPLESS CALLED TODAY, SAID WE WOULD CALL HIM BACK WITH UPDATE (11/09/2021 11:55 AM - kelizondo) contacted atrium, they said a 14 week extension was placed on all products to texas, said customer would have product by dec. 9 (09/24/2021 11:56 AM - kelizondo) called oscar from mccoys asking for the status. They state that they never received the p.o i gave oscar the date, time, email it was send too, and p.o number. will call back with me once they find it. (08/26/2021 04:05 PM - klopez) mccoys p.o for windows QR-23769 was send to the vendor on 6/9. (08/26/2021 02:28 PM - klopez) Send P.O to Carlos at West End QR-23769 (05/26/2021 09:04 AM - klopez) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-05-12 |  |  | lteniente |  |  | 2021-06-26 | lteniente | klopez | Joshua Sharpless | (956) 777-8661 | joshuasharpless@gmail.com
5936 | R2403 | Wilke, Scott Residence | Wilke, Scott Residence | 2412 Sterling Avenue | Edinburgh | TX | 78539 | rcantu | Exterior | Windows | (09) IN PRODUCTION | 2021-04-22 | rcantu | 2021-04-07 | 2021-07-01 | kelizondo |  | 5085 | 5085 | 2542.5 | 100 | We need 8 windows reapirs. Gate code- #037 Atrium 8100 almond color Turtle low E no grids Turtle Low-E glass No grids | 0 |  | 2021-04-22 | Google | 5085 |  |  | contact | Scott Wilke |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-04-22 |  | Project manager said the glass doesnot have the low E all the way to the edge so its going to be replace on two windows . (07/01/2021 05:04 PM - kelizondo) called the client did not pick up, left voice mail letting him know about the 6-8 weeks lead. P.O has been created QR-23555 and send to specs (04/22/2021 10:06 AM - klopez) |  |  | (11) Punchout - Corrections | Open | 2021-04-22 |  |  | lteniente |  |  | 2021-07-01 | lteniente | kelizondo | Scott Wilke | (956) 566-2939 | kwilke1990@gmail.com
5907 | C2756 | Move it Self Storage - Julian Perez | Move It Storage fredericksburg | 383 FM2093, | Fredericksburg | TX | 78624 | nsorrell | Low Slope Roof Systems | A. Metal; A. Coating Silicone Based; B.Roof Repair | (09) IN PRODUCTION | 2021-06-04 | nsorrell | 2021-04-04 | 2021-06-23 | egomez |  | 2814.5 | 2814.5 | 2814.5 | 100 |  | 0 |  | 2021-06-04 | Telemarketing | 0 |  |  | company | Move it Self Storage Pearland TX | Alvin, TX Office |  |  |  | Commercial | n | [6 empty] | 2021-06-04 |  | no proper contract (05/27/2021 02:15 PM - lteniente) Full payment will be collected after the job is completed. Approved by Crystal. (05/14/2021 11:42 AM - nsorrell) The AC Systems on the roof are leaking. It's the only current building with leaks. Will get specified building number before crew is sent out. (05/14/2021 11:38 AM - nsorrell) |  |  | (14) Project on Hold | Open | 2021-06-04 |  |  | lteniente |  |  | 2021-06-23 | lteniente | egomez | Julian Perez | (361) 737-8880
5871 | C2919 | Move it Storage Austin | Move it Storage Austin | 9311 N FM 620, | Austin | TX | 78726 | kelizondo | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-10-11 | kelizondo | 2021-03-30 | 2021-10-13 | gsolis |  | 3231.42 | 3231.42 | 3231.42 | 100 | Job Details: Job Details: Routine Maintenance handling? no What is your square footage? 130000 How many stories is your roof? 2 and 1 What is the age of your roof? na When was the last time inspected or restored? na Will we be inspecting more than 1 facility? yes Any current issues? yes has leaking Any emergency repairs needed? no Have you contacted your insurance? not yet If no external access- who can we meet for internal access? See manager on duty, roof is 1 and 2 stories metal. | 0 |  | 2021-10-11 | Telemarketing | 0 | NET 30. NO INVOICE UNTIL COMPLETE |  | company | Move it Storage Austin | Austin, TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-10-11 |  |  |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-10-11 |  |  | lteniente |  |  | 2021-10-13 | lteniente | gsolis | Tiffney Nicols | (512) 336-7233 | tnicols@moveitstorage.com
5861 | R2563 | Miltex Properties | Miltex properties | 47 DODGE RD | Boerne | TX | 78006 | kelizondo | Steep Slope Roof Systems | B. Roof Repair | (09) IN PRODUCTION | 2021-08-11 | kelizondo | 2021-03-29 | 2021-09-29 | kelizondo |  | 819113.09 | 819113.09 | 412370.33 | 100 | Job Details: Job Details: Routine Maintenance handling? no What is your square footage? 3800 How many stories is your roof? 1 What is the age of your roof? 20plus When was the last time inspected or restored? na Will we be inspecting more than 1 facility? 1 Any current issues? yes needs new roof Any emergency repairs needed? yes in market to replace Have you contacted your insurance? not yet If no external access- who can we meet for internal access? See Greg Roof, is comp shingle, vintage style is needed. Needs replacement | 0 | ctostado | 2021-08-11 | Telemarketing | 0 |  |  | contact | Greg Hilgemeier |  | Orlando Marquez |  |  | Residential | n | [6 empty] | 2021-08-11 |  | MATERIALS DELIVERED 3 CEDAR (09/29/2021 08:25 AM - kelizondo) |  |  | (09) * Work In Progress | Open | 2021-08-11 |  |  | ctostado |  |  | 2021-08-16 | ctostado | gsolis | Greg Hilgemeier | (830) 755-8575 | not provided
5791 | R2375 | LUDWIG, DEREK Residence | LUDWIG, DEREK Residence | 8506 COLCHESTER | San Antonio | TX | 78254 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) IN PRODUCTION | 2021-04-01 | kelizondo | 2021-03-22 | 2021-05-25 | egomez |  | 8480 | 8480 | 4480 | 100 | Job Details: AFTER THE BIG STORM WE HAVE LIKE 2 DIFFERENT LEAKS ON EITHER SIDE OF THE HOUSE. | 0 |  | 2021-03-30 | Google | 0 |  |  | contact | DEREK LUDWIG |  | Tim Parrish |  |  | Residential | n | [6 empty] | 2021-03-30 |  | PRJ is on hold as per Alfredo. (04/23/2021 10:25 AM - rlerma) does not require permit (04/22/2021 12:27 PM - klopez) got with ashley who will be submitting the permits. i keep getting error messages and will not let me move forward. will call san Antonio service to see what can be done. (04/22/2021 12:12 PM - klopez) JUST GO THE USERNAME AND PASSWORD TO START THE PERMIT APPLICATION, ASKING FOR A CONTRACTORS LICENSE #, WHICH IVE GOTTEN IN CONTACT WITH ASHLEY WHO WILL SEND ME THE INFORMATION SO I CAN PROCEED FORWARD. (04/20/2021 03:40 PM - klopez) call client to schedule delivery of materials and start of project, will wait for call back. (04/20/2021 09:38 AM - rlerma) EAGLE VIEW HAS BEEN SUBMITTED (04/09/2021 09:01 AM - rlerma) called the client didnt pick up left a text stating the 2 week lead (04/08/2021 03:38 PM - klopez) no longer pending ID (04/01/2021 09:50 AM - lteniente) TX DRIVERS LICENSE NUMBER: 3770272713 (04/01/2021 09:46 AM - tparish) Pending ID (03/30/2021 11:42 AM - lteniente) |  |  | (15) Archive | Open | 2021-03-30 |  |  | lteniente |  |  | 2021-05-25 | lteniente | egomez | DEREK LUDWIG | (724) 972-9456 | DLUDWIG1589@GMAIL.COM
5787 | R2444 | KRAFT, JACKIE Residence | KRAFT, JACKIE Residence | 2314 Arthur Ave | Edinburg | TX | 78542 | kelizondo | Exterior | Gutters | (09) IN PRODUCTION | 2021-07-01 | kelizondo | 2021-03-19 | 2021-11-08 | srivas |  | 7795.26 | 8450.26 | 4450.26 | 100 |  | 0 | ctostado | 2021-06-30 | Referral | 0 |  |  | contact | JACKIE KRAFT |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-05-26 |  | gutters were completed by Juan b a while back pics are uploaded. (11/08/2021 08:48 AM - srivas) pending gutters (07/28/2021 09:28 AM - klopez) Project manager said still pending with gutters. (07/27/2021 10:31 AM - kelizondo) Juan Estrada Jun 30, 2021, 7:12 PM Job is not complete. Missing gutters (07/01/2021 10:47 AM - ctostado) materials have been ordered with QR-23831, delivery will be 06/14. client and pm have been advised. (06/09/2021 04:54 PM - rlerma) Materials have been ordered with PO QR-23831. (06/08/2021 07:37 AM - rlerma) permit uploaded (06/03/2021 10:08 AM - klopez) permit submitted (05/28/2021 12:55 PM - klopez) |  |  | (11) Punchout - Corrections | Completed | 2021-05-26 | 2021-06-30 |  | lteniente | ctostado |  | 2021-09-23 | ctostado | kelizondo | JACKIE KRAFT | (956) 537-8569 | jcqlnkraft@gmail.com
5687 | R2374 | Garcia, Alejandro Residence | Garcia, Alejandro Residence | 915 Navajo Drive | Rio Grande City | TX | 78582 | kelizondo | Exterior | Windows | (09) IN PRODUCTION | 2021-03-30 | kelizondo | 2021-03-09 | 2021-10-26 | egomez |  | 9815 | 9815 | 4815 | 100 |  | 0 | lteniente | 2021-03-30 | Referral | 0 | Price for Windows 5700 series without the butt to windows is =$5,455.00/ Our cost is $3,817.34 |  | contact | Alejandro Garcia |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2021-03-30 |  | Juan Auces will be going out on 10/29 to fix windows (10/26/2021 10:55 AM - egomez) Project manager said that we are missing one window to be installed. (08/13/2021 10:41 AM - kelizondo) Send Out P.O to specs QR-23436 (04/06/2021 03:26 PM - klopez) eagle view has been uploaded (03/31/2021 11:46 AM - rlerma) called the client id not answer texted them giving 2-3 lead (03/30/2021 03:07 PM - klopez) no longer pending ACH (03/30/2021 01:41 PM - lteniente) Pending ACH Form (03/30/2021 08:44 AM - lteniente) |  |  | (08) * Scheduled & Ready to Start | Open | 2021-03-30 |  |  | lteniente |  |  | 2021-10-26 | lteniente | egomez | Alejandro Garcia | (956) 352-0191 | Agp20@yahoo.com
5644 | C2695 | Sea Vista Condominiums II | Sea Vista Condominiums | 110 Padre Blvd, | South Padre Island | TX | 78597 | kelizondo | Low Slope Roof Systems | B. Roof Over Construction; A. Coating Silicone Based; D. Retail Contract; E. Special Order | (09) IN PRODUCTION | 2021-10-26 | kelizondo | 2021-03-02 | 2021-11-10 | egomez |  | 82855.36 | 82855.36 | 53855.98 | 100 | Job Details: Routine Maintenance handling? No What is your square footage? 83,520 How many stories is your roof? 2 buildings 6 stories, 2 building office What is the age of your roof? na When was the last time inspected or restored? na Will we be inspecting more than 1 facility? yes 4 Any current issues? has leaks office building Any emergency repairs needed? yes Have you contacted your insurance? no If no external access- who can we meet for internal access? See Martha the office building has leaking brick roof, The 6 story building wants to have looked at, not sure if it has leaks in coating. | 0 | lteniente | 2021-05-04 | Telemarketing | 80000 |  |  | company | Sea Vista Condominiums | South Padre Island , TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-05-04 |  | called client to give her a status update, materials have been ordered BRS - QC-62963 HD - QC- 62969 (11/02/2021 03:27 PM - klopez) as per Jorge Martinez inspector supervisor for building permits in SPI no permit is required for the coating. as per he second contract in this prj the building has been done; Philip. (10/29/2021 02:02 PM - klopez) DON'T MISS THEM: THERE ARE 2 CONTRACTS IN HERE. (05/03/2021 08:15 PM - pwesterman) follow up call: left a message (03/25/2021 05:04 PM - bmcsteen) Follow up text: no reply (03/22/2021 05:06 PM - bmcsteen) |  |  | (05) Order and Schedule Material | Open | 2021-05-04 |  |  | lteniente |  |  | 2021-11-10 | lteniente | egomez | Martha "Neri " | (956) 761-5526 | seavistacondos@aol.com
5573 | R2429 | Garza, David Residence | Garza, David Residence | 3307 Pelican Lake Ave. | Edinburg | TX | 78539 | kelizondo | Steep Slope Roof Systems | A. Tile (Concrete); B. Roof Repair; D. Retail Contract; E. Special Order | (09) IN PRODUCTION | 2021-09-21 | kelizondo | 2021-02-18 | 2021-09-21 | mmolano |  | 3500 | 3500 | 1750 | 100 | Job Details: Estimate for repairs Needs fix the facia underneath the tile. Please call when arrive. Need to give the access code. Tile is 12 yrs old 1 story leaks yes! | 0 | ctostado | 2021-06-12 | Google | 0 |  |  | contact | David Garza |  | Philip Westerman |  |  | Residential | n | [6 empty] | 2021-05-17 |  | Roof still leaking as per client email. (09/21/2021 01:47 PM - mmolano) spoke to client and PM, both are ok with starting today 05/26. sub will go after 3pm to start project (05/26/2021 11:04 AM - rlerma) repair no gaf (05/20/2021 03:26 PM - lteniente) no longer pending payment still pending ach (05/19/2021 02:56 PM - lteniente) pending ach, pending payment (05/17/2021 10:32 AM - lteniente) Follow up text: no reply (03/22/2021 05:14 PM - bmcsteen) |  |  | (11) Punchout - Corrections | Completed | 2021-05-17 | 2021-06-12 |  | lteniente | ctostado |  | 2021-09-21 | ctostado | mmolano | David Garza | (830) 968-0197 | garza.david@gmail.com
5481 | C2757 | First Presbyterian Church McAllen Big One | First Presbyterian Church | 104 S 12th St, | McAllen | TX | 78501 | kelizondo | Low Slope Roof Systems | C. Addtional Exterior Work; A. TPO; B.Roof Repair; D. Insurance Proceeds; A. Tile | (09) IN PRODUCTION | 2021-06-09 | kelizondo | 2021-01-29 | 2021-10-13 | ctostado |  | 40096.33 | 40096.33 | 21768.24 | 100 | Job Details: Routine Maintenance handling? no What is your square footage? 19,250 How many stories is your roof? 2 What is the age of your roof? na When was the last time inspected or restored? na Will we be inspecting more than 1 facility? no Any current issues? yes tile lifted on west side of alley Any emergency repairs needed? yes Have you contacted your insurance? yes already got the money If no external access- who can we meet for internal access? See Michael, roof is 2 story tiles north side damage to tiles on alley side. | 0 | ctostado | 2021-06-08 | Telemarketing | 36000 |  |  | company | First Presbyterian Church | McAllen , TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-06-04 |  | Tile Repairs complete only pending TPO (09/02/2021 12:48 PM - egomez) tentative date for 8/2 need to confirm with fernando to see if he can make it by then (07/28/2021 10:21 AM - klopez) permit uploaded (07/13/2021 03:57 PM - klopez) permit approved, waiting for check to be made to go pay and pick up the permit (07/12/2021 04:58 PM - klopez) " I show under review, normal is from 5 to 15 bus days." email from the city of McAllen for update on permit (07/08/2021 12:17 PM - klopez) permit submitted (07/06/2021 10:48 AM - klopez) no longer pending payment (06/09/2021 06:40 PM - lteniente) pending payment (06/04/2021 11:18 AM - lteniente) Closing the deal (05/26/2021 08:55 AM - pwesterman) Follow up text: no reply (03/23/2021 03:19 PM - bmcsteen) |  |  | (12) Ready to Invoice (Crystal) | Open | 2021-06-04 |  |  | lteniente |  |  | 2021-10-12 | lteniente | kelizondo | Michael Pullin | (956) 682-2836 | FPchurch@sbcglobal.net
5215 | C2693 | Rodd Field Congregation of Jehovah's Witness | Rodd Field Congregation of Jehovah's Witness | 2753 Rodd Field Road | Corpus Christi | TX | 78414 | gsolis | Steep Slope Roof Systems | B. Roof Replacement; A. Metal ; C. Additional Exterior Work; D. Retail Contract | (09) IN PRODUCTION | 2021-05-04 | gsolis | 2020-12-09 | 2021-11-08 | klopez |  | 52500 | 52500 | 52500 | 100 |  | 0 | ctostado | 2021-11-16 | Repeat | 0 |  |  | contact | David Lung |  | Gary Solis |  |  | Commercial | n | [6 empty] | 2021-05-04 |  | called client last Monday to let him know that we will be sending a crew for the gutters. Unfortunately, our sub couldn't make it today rescheduled for next week 11/15 (11/08/2021 12:49 PM - klopez) Pending gutters (10/08/2021 10:32 AM - egomez) TENTATIVE START DATE CHANGED TO SEPT. 16. (08/26/2021 02:19 PM - klopez) Start date for September 13th, per PM Jose, sub will be Julian (08/18/2021 10:16 AM - officestaff) spoke with sergio to check on ETA has yet to get an update will reach back to me today with an ETA (07/20/2021 09:38 AM - klopez) due to materials taking longer than expected. we will be placing the prj on hold (06/24/2021 03:24 PM - klopez) permit upload (05/26/2021 05:11 PM - klopez) called the city no one picked up send an email again asking for an update (05/19/2021 10:33 AM - klopez) Quality Metals P.O QC-61799 for coils (05/07/2021 03:15 PM - klopez) submitted permit (05/06/2021 10:54 AM - klopez) pending color choices on metal and gutter (05/03/2021 04:06 PM - gsolis) |  |  | (08) * Scheduled & Ready to Start | Completed | 2021-05-04 | 2021-11-16 |  | lteniente | ctostado |  | 2021-11-08 | ctostado | klopez
5168 | R2280 | Cardenas, Betty Residence | Cardenas, Betty Residence | 15475 E Farm To Market 2812 | Edinburg | TX | 78542 | kelizondo | Exterior | Windows | (09) IN PRODUCTION | 2020-12-28 | kelizondo | 2020-12-02 | 2021-03-17 | kelizondo |  | 7975 | 7975 | 3987.5 | 100 | Job Details: Estimate for 6 windows and 1 galss Door. 3-17-21 Project manager said that Betty has cracked glass on two windows from delivery. Atrium is aware and is sending a tech to switch out the two glass. She won't pay until glass has ben fixed. (K.Elizondo) | 0 |  | 2020-12-17 | Google | 0 |  |  | contact | Betty Cardenas |  | Roel Cantu |  |  | Residential | n | [6 empty] | 2020-12-17 |  | should arrive this week 2/13 (02/08/2021 01:51 PM - gsolis) gary will get eta on window (02/08/2021 12:19 PM - klopez) waiting on one more window unit (01/29/2021 03:11 PM - gsolis) gary is taking care of this prj. (01/26/2021 04:43 PM - klopez) gary will get with roel (01/21/2021 02:54 PM - klopez) check with roel (01/12/2021 11:23 AM - klopez) Roel has ordered window and has sub lined up (01/07/2021 01:09 PM - gsolis) Informed the client about the 4 week lead. since this project is windows only the wait may differ. will call her once we get updates for her project (12/28/2020 12:32 PM - klopez) ID no longer pending (12/28/2020 08:16 AM - lteniente) License has been uploaded (12/23/2020 01:05 PM - rcantu) ID Pending (12/17/2020 08:23 AM - lteniente) |  |  | (11) Punchout - Corrections | Open | 2020-12-17 |  |  | lteniente |  |  | 2021-03-17 | lteniente | kelizondo | Betty Cardenas | (956) 451-6635 | beatrizcardenas42@yahoo.com
5148 | R2345 | Long, Robert Residence | Long, Robert Residence | 2700 Brazos Ct | McAllen | TX | 78504 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Tile (Clay); D. Retail Contract | (09) IN PRODUCTION | 2021-03-08 | kelizondo | 2020-11-30 | 2021-11-01 | srivas |  | 39500 | 39500 | 39500 | 100 | Inspectionon on your own send text to customer when arrive Job Details: 2 estimate for repairs and replacement Type of roof clay tile 12 yrs old 1 story private payment leaks yes Cusotmer authorized to do the inspection on your own. | 0 |  | 2021-03-08 | Google | 0 |  |  | contact | Robert Long |  | Orlando Marquez |  |  | Residential | n | [6 empty] | 2021-03-08 |  | waiting on client to see what the mediation outcome is (11/01/2021 02:13 PM - srivas) short 2 bundles of title materials were ordered Monday 05/24. (05/26/2021 11:24 AM - klopez) materials will arrive on 26th (04/12/2021 03:09 PM - klopez) pending materials (03/30/2021 02:26 PM - klopez) 2 week lead time (03/29/2021 03:44 PM - egomez) Materials have been ordered (03/29/2021 03:44 PM - egomez) uploaded gaf (03/10/2021 04:31 PM - klopez) SPOKE TO CUST ABOUT THE 2-3 WEEK WAIT TIME FOR MATERIALS TO GET HERE. CUST AGREED. (03/08/2021 03:16 PM - rlerma) Payment no longer pending (03/08/2021 09:45 AM - lteniente) Pending Payment (03/08/2021 09:32 AM - lteniente) |  |  | (14) Project on Hold | Open | 2021-03-08 |  |  | lteniente |  |  | 2021-06-09 | lteniente | gsolis | Robert Long | (956) 227-7452 | rdlong@1stpatriotins.com
5124 | C2627 | Esperanza Construction - Casita Lantana | Casita Lantana | 3954 Dana Ave | Brownsville | TX | 78526 | gsolis | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. New Roof Construction; D. Retail Contract | (09) IN PRODUCTION | 2021-02-08 | gsolis | 2020-11-24 | 2021-03-22 | ctostado |  | 293643.28 | 293643.28 | 293643.28 | 100 |  | 0 | lteniente | 2021-02-08 | Referral | 0 |  |  | company | Esperanza Construction | McAllen, TX Office | Gary Solis |  |  | Commercial | n | [6 empty] | 2021-02-08 |  | Melo to dry in houses 1 2 5 6 7 10 13 3 4 11. 2/24/21 (02/23/2021 01:33 PM - jcoronado) scheduled melo for 3/1 (02/19/2021 02:30 PM - klopez) materials will depend on the style of apartment that is ready to (02/09/2021 07:12 AM - gsolis) called the client the number was giving me an error let the p.m know about the phone number (02/08/2021 04:53 PM - klopez) |  |  | (09) * Work In Progress | Open | 2021-02-08 |  |  | lteniente |  |  | 2021-03-15 | lteniente | klopez | Esteban Lozano | (956) 683-5048
4958 | R2383 | Revisore, Sharon Interior and Garage |  | 3954 Dana Ave | Brownsville | TX | 78526 | anovack | Steep Slope Roof Systems | C. Additional Interior Work; D. Retail Contract; C. Additional Carpentry | (09) IN PRODUCTION | 2021-10-20 | pwesterman | 2020-11-03 | 2021-11-16 | srivas |  | 22488.22 | 22488.22 | 13477.91 | 100 | CONFIRMED WITH PHILIP 9/20 TO MOVE TO INVOICE | 0 | ctostado | 2021-09-25 | Google | 0 |  |  | contact | Sharon Revisore |  | Philip Westerman |  |  | Residential | n | [6 empty] | 2021-04-01 |  | spoke to Enrique said that he was going to contact customer and will go out there sat. (11/16/2021 09:01 AM - srivas) Client claims that she still has a leak (10/20/2021 03:54 PM - mmolano) waiting on new flooring to arrive (07/23/2021 11:16 AM - gsolis) will have a pre construction meeting with PM at clients home to walk through the scoop of work with sub (05/27/2021 08:25 AM - rlerma) NO GARAGE ROOF. CUSTOMER CANCELLED. ONLY INTERIOR TO BE DONE. (05/05/2021 09:02 AM - ctostado) Customer is unsure about the roof and just wants interior done (05/04/2021 04:59 PM - lteniente) |  |  | (08) * Scheduled & Ready to Start | Completed | 2021-04-01 | 2021-09-25 |  | lteniente | ctostado |  | 2021-11-16 | ctostado | srivas | Sharon Revisore | (512) 965-5030 | sharonrevisore@gmail.com
4861 | R2229 | Perez, Javier Residence | Perez, Javier Residence | 405 S. Woodland dr. | Pharr | TX | 78577 | kelizondo | Steep Slope Roof Systems | B. Roof Replacement; A. Metal ; A. Cedar Shake; D. Insurance Proceeds | (09) IN PRODUCTION | 2020-11-04 | kelizondo | 2020-10-21 | 2021-02-25 | lteniente |  | 52820.4 | 52820.4 | 24525.77 | 100 | Wants 3 estimate options: metal, wood, tyle. Already made on xactimate | 0 |  | 2020-11-04 | Google | 0 |  |  | contact | Javier Perez |  | Joshua Rodriguez |  |  | Residential | n | [6 empty] | 2020-11-04 |  | Insurance check bounced. Waiting on new one. (12/19/2020 10:31 AM - ctostado) send out the permit. They are needing our construction registration form submitted first once they accept it I will then upload the permit. (12/10/2020 09:51 AM - klopez) submitted GAF (12/07/2020 09:39 AM - klopez) missing color and boot counts (12/05/2020 09:56 AM - gsolis) submitted permit waiting for status (11/30/2020 03:12 PM - klopez) permit was submitted but is missing information. will resend it once i get the eagleview and get the measurements (11/25/2020 01:34 PM - klopez) submitted permit on 11/23 still waiting on status. moving project forward. (11/25/2020 01:20 PM - klopez) send vendor for cut list (11/11/2020 02:28 PM - gsolis) called the client did not answer left a text letting him know about the 4 week lead (11/04/2020 03:39 PM - klopez) customer has paid (11/04/2020 08:58 AM - lteniente) |  |  | (14) Project on Hold | Open | 2020-11-04 |  |  | lteniente |  |  | 2020-12-19 | lteniente | ctostado | Javier Perez | (956) 223-7843 | jav1276@aol.com
4823 | C2896 | Beacon Roofing Supply West End Garrison Construction | Beacon Roofing Supply | 1702 S. Expressway 281 | Edinburgh | TX | 78542 | kelizondo | Low Slope Roof Systems | B. Roof Over Construction; A. Coating Silicone Based | (09) IN PRODUCTION | 2021-10-07 | kelizondo | 2020-10-19 | 2021-11-23 | kelizondo |  | 28074.35 | 28074.35 | 15106.98 | 100 | Job Details: Estimate for commercial building repairs. On site contact: Fabian Gonzalez phone: 956 787 5766 Roof repairs metal roof 1 building 1 story | 0 |  | 2021-09-21 | Google | 0 |  |  | company | Garrison Construction Group LLC | Houston , TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-09-21 |  | Ismael working on replacing panels, fasteners and skylights Coating will be Lorenzo on Friday 11/5/21 (11/03/2021 09:06 AM - egomez) called client to let them know that we will be going by tomorrow to start on prj (11/02/2021 02:36 PM - klopez) P.O QC- 62840 materials ordered 10/19 Panels are ready for pick up. (10/26/2021 01:48 PM - klopez) called, didn't pickup. left voicemail about updates on project. (10/15/2021 09:28 AM - officestaff) no longer pending payment (10/07/2021 04:47 PM - lteniente) pending payment (09/23/2021 11:02 AM - lteniente) |  |  | (12) Ready to Invoice (Crystal) | Open | 2021-09-21 |  |  | lteniente |  |  | 2021-11-23 | lteniente | kelizondo | Will Thurmond | (713) 376-4276 | will@garrisonconstructiongroup.com
4676 | C2608 | Doctor's Clinic of Rio Grande City 210 N Britton | 210 N. Britton | 210 N. Britton | Rio Grande City | TX | 78582 | gpena | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Interior Work; D. Insurance Proceeds | (09) IN PRODUCTION | 2020-12-16 | gpena | 2020-10-07 | 2021-11-05 | avillalobos |  | 16313.13 | 16313.13 | 8778.2 | 100 |  | 0 |  | 2020-12-16 | Repeat | 0 |  |  | company | Doctors Clinic of Rio Grande City | Doctors Clinic of Rio Grande City |  |  |  | Commercial | n | [6 empty] | 2020-12-16 |  | interior work pending. we will allow the crew to use our account to get material and will take out from check. if crew doesn't go out by wed. we will assign to another crew. (11/01/2021 02:02 PM - srivas) project on hold due to insurance dispute (05/22/2021 10:23 AM - gsolis) waiting on client to clear area to scheduled labor (04/26/2021 11:37 AM - rlerma) one of melos crew is there, spoke to client. he said that if crew needs power there is a blue socket under the meter on the next building. (03/19/2021 08:30 AM - rlerma) Ramiro confirmed with client to change with crew. waiting on new crew to confirm if they can start prj. (03/15/2021 02:22 PM - klopez) scheduled for 02/23/2021 to go out and start the work on roof. (02/22/2021 04:40 PM - rlerma) waiting on the clinic to give us availability (02/19/2021 02:29 PM - klopez) changed date for 2/15 - 2/17 (02/08/2021 10:25 AM - klopez) rescheduled juan for 2/11 - 2/12 (02/05/2021 04:06 PM - klopez) scheduled bustos for 1/4-1/5 (01/26/2021 02:06 PM - klopez) pending int. still (01/21/2021 04:16 PM - klopez) pending int. (01/12/2021 09:39 AM - klopez) uploaded eagle view (12/22/2020 11:50 AM - klopez) Owens corning Estate Gray White drip edge client wants sergio/felipe crew to work on his prj (12/22/2020 08:50 AM - klopez) been getting in contact with p.m Waiting for client to pick a color for shingles (12/21/2020 04:01 PM - klopez) called the client let him know about the 4 week lead, client would like the same crew he had before (sergio) (12/17/2020 09:34 AM - klopez) |  |  | (12) Ready to Invoice (Crystal) | Open | 2020-12-16 |  |  | lteniente |  |  | 2021-11-05 | lteniente | avillalobos | Delfino Garza | (210) 560-4335 | drandygarza@gmail.com
4547 | R2168 | Aurora Luna | Aurora Luna Residence | 8179 E State HWY 107 | Edinburg | TX |  | lteniente | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Exterior Work; C. Additional Interior Work; D. Insurance Proceeds | (09) IN PRODUCTION | 2021-01-15 | lteniente | 2020-09-28 | 2021-02-10 | klopez |  | 21136.71 | 18858.18 | 3260.7 | 100 |  | 0 | ctostado | 2020-12-19 |  | 0 |  |  | contact | Aurora Luna |  | Noah Sorrell |  |  | Residential | n | [6 empty] | 2020-10-15 |  | project placed on hold due to insurance (02/10/2021 04:54 PM - klopez) still pending insurance (02/08/2021 12:18 PM - klopez) Pending insurance (01/28/2021 02:47 PM - egomez) twins should be heading out (01/27/2021 09:46 AM - klopez) need to get with the project managers when they are planning int. (01/21/2021 04:14 PM - klopez) PENDING INT (01/20/2021 04:55 PM - mmolano) materials were delivered to customer by Southern Shingles (11/18/2020 05:12 PM - ocovarrubias) spoke to customer and advised that we are working on gathering materials (11/12/2020 08:39 AM - ocovarrubias) GAF ordered (10/27/2020 12:25 PM - ocovarrubias) Pictures have been added. (10/27/2020 11:51 AM - nsorrell) client will be placed on hold due to missing pics. pm will email them to me since he does not have access to dataforma, just waiting on update. (10/20/2020 10:28 AM - klopez) photos are missing, emailed pm to upload them to dataforma. (10/16/2020 10:27 AM - klopez) called the client spoke to her son Frank, who takes care of his mothers info, let him know about the 4 week lead. (10/16/2020 10:14 AM - klopez) |  |  | (14) Project on Hold | Completed | 2020-10-15 | 2020-12-19 |  | lteniente | ctostado |  | 2021-02-10 | ctostado | klopez | Aurora Luna | (956) 458-1983
4440 | R2479 | Rueda, Mario Residence | Rueda, Mario Residence | 1107 Helen Avenue | Mission | TX | 78572 | kelizondo | Low Slope Roof Systems | A. TPO; B.Roof Repair; D. Retail Contract; E. Special Order | (09) IN PRODUCTION | 2021-07-14 | anovack | 2020-09-21 | 2021-10-18 | egomez |  | 1475 | 1475 | 955 | 100 | Flat Ceramic tiled terrace off master bedroom is leaking. Water tested for 1.5 hrs and no leak. Wait until next heavy rain... Alfredo quoted verbally $5000-$7000 | 0 |  | 2021-06-21 | Google | 5000 |  |  | contact | Mario Rueda |  | Victor Perez |  |  | Residential | n | [6 empty] | 2021-06-21 |  | punch out per alfredo (10/18/2021 04:57 PM - egomez) Customer to replace section of roof meeting with 9/28 him (09/23/2021 09:10 AM - avillalobos) alfredo and pm will be doing inspection today (09/15/2021 10:13 AM - klopez) waiting for it to rain t check on the leak (08/02/2021 09:30 AM - klopez) client and pm have been updated with tentative date (07/20/2021 03:02 PM - klopez) TENTATIVE scheduled date for punch out 07/22 for alfredo and Gomez (07/20/2021 01:48 PM - klopez) client called asking to speak with erika to see when the crew will be going back. unfortunately, she was absent will let gary call the client since the client wanted to speak with a manager. (07/19/2021 03:06 PM - klopez) called, verified info (06/22/2021 10:32 AM - lteniente) Contract & ID Already uploaded in dataforma. The customer did not sign the ACH form because he will pay in cash (06/18/2021 12:35 PM - vperez) pending contract (06/17/2021 05:45 PM - lteniente) |  |  | (11) Punchout - Corrections | Open | 2021-06-21 |  |  | lteniente |  |  | 2021-10-18 | lteniente | egomez | Mario Rueda | (956) 225-7570 | mrueda@gruporuba.net
4383 | R2349 | Groninger, Monique Residence | Groninger, Monique Residential | 23 Ocelot Trail Rd | Laguna Vista | TX | 78578 | anovack | Steep Slope Roof Systems | A. Tile (Concrete); B. Roof Repair; D. Insurance Proceeds; E. Special Order | (09) IN PRODUCTION | 2021-05-11 | anovack | 2020-09-17 | 2021-11-01 | ctostado |  | 10530.18 | 10530.18 | 2961.78 | 100 | 303-521-4495 | 0 |  | 2021-03-19 | Google | 0 |  |  | contact | Monique Groninger |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-03-19 |  | Ni interior. Roof only on insurance. Juan supplementing. (11/01/2021 02:41 PM - ctostado) NEED TO WORK ON INTERIOR-ADVISED TO ADD RUNNING NOTE (09/01/2021 04:37 PM - kelizondo) materials will get delivered on friday 08/20 as per vender. client/pm is aware (08/18/2021 02:49 PM - rlerma) (08/12/2021 04:39 PM - jestrada ) waiting to hear delivery date from vendor Southern Shingles. (07/02/2021 02:56 PM - rlerma) as per ramiro the materials have been ordered will be getting ETA from vendor. (06/01/2021 03:34 PM - klopez) got the report from jorge from southern shingles on the tile, will do the order today and have eta on delivery (05/24/2021 10:33 AM - rlerma) remove tile from the front slope above the garage. Replace those tile with new tile. (see Itel report) Use any tile from that area that aren't damaged to replace other damaged tile across the rest of the roof. (05/11/2021 12:17 PM - nsorrell) roof repair no gaf measurements (05/11/2021 11:31 AM - lteniente) no longer pending ID (03/19/2021 11:56 AM - lteniente) Pending ID Pending Payment (03/17/2021 10:10 AM - lteniente) invoice customer for deductible amount of $7500.00. Contract will be uploaded soon. (03/16/2021 11:47 AM - nsorrell) Pending Contract (03/16/2021 09:27 AM - lteniente) Insurance has approved repairs. (03/12/2021 12:06 PM - nsorrell) |  |  | (12B) Ready to Invoice Insurance (Crystal) | Open | 2021-03-19 |  |  | lteniente |  |  | 2021-11-01 | lteniente | srivas | Monique Groninger | (956) 299-4024 | mgroninger84@gmail.com
4226 | C2843 | Country Pancake House, Pharr TX | Country Pancake House, Pharr TX | 4325 N Cage Blvd | Pharr | TX | 78577 | pwesterman | Low Slope Roof Systems | B. Roof Replacement; A. Coating Silicone Based; A. Dura-Last; D. Retail Contract; E. Special Order | (09) IN PRODUCTION | 2021-08-17 | kelizondo | 2020-09-10 | 2021-11-04 | bbuffamonte |  | 24875.85 | 24875.85 | 12437.92 | 100 | Roof repairs Metal flat roof 20ft to 25 ft tall 1 building Wind & Hail damage Leaks several places. Needs pictures of inspection to show insurance Contact in the facility is Mary (the manager) They have a latter attached to the building, PM can use that one (mentioned the customer). | 0 |  | 2021-08-12 |  | 0 |  |  | company | Country Pancake House, Pharr TX | Pharr, TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-08-12 |  | Will look at the drains and go to budget to get the drain covers. (11/04/2021 03:24 PM - bbuffamonte) WAS GOING TO SCHEDULE A FINAL INSPECTION BUT PHILIP SAID THE BIRDCAGES WERE NOT INSTALLED, THEY ARE SUPPOSED TO GO OVER THE ROOF DRAIN AND THEY SHOULD BE PLASTIC (11/02/2021 11:29 AM - kelizondo) Finished second coat Friday. (11/01/2021 07:11 AM - bbuffamonte) Spoke to Duro-Last materials are scheduled to be shipped out on 10/1/21 (09/23/2021 01:16 PM - egomez) Materials Ordered PO#QC-62546 (09/15/2021 01:44 PM - egomez) special order of duro-shield (duro-last). (08/26/2021 02:42 PM - officestaff) client did not pickup. sent text with status update of project. (08/26/2021 02:28 PM - officestaff) called the city of pharr. they do not require a permit for coating. (08/24/2021 08:29 AM - klopez) verified information (08/17/2021 10:27 AM - lteniente) |  |  | (11) Punchout - Corrections | Open | 2021-08-12 |  |  | lteniente |  |  | 2021-11-02 | lteniente | kelizondo | Mike Bayrami | (972) 567-1711 | mikeBayrami@yahoo.com
4172 | R2486 | Garcia, Jessica Residence | Garcia, Jessica Residence | 907 Cactus Ln | Edinburgh | TX | 78541 | kcampbell | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Exterior Work; C. Additional Interior Work; D. Insurance Proceeds; C. Additional Carpentry | (09) IN PRODUCTION | 2021-08-30 | kelizondo | 2020-09-08 | 2021-11-16 | mmolano |  | 7508.38 | 7508.38 | 6649.64 | 100 | Job Details: We're needing roofing repair, and possible replacement for a small house. Are there any leaks? if so, where?: My daughter's bedroom | 0 |  | 2021-08-30 | Google | 8000 |  |  | contact | Jessica Garcia |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-08-30 |  | CONFIRMED WITH JUAN (11/11/2021 04:41 PM - kelizondo) JESSICA CALLED BACK AND SET UP HER FINAL APPT (11/09/2021 01:36 PM - kelizondo) Punch outs were completed by Juan B. Photos have been uploaded. (10/27/2021 05:27 PM - srivas) had client scheduled for today, however will not be able too because of the chance of rain in the forecast. Will check tomorrow and see if there is availability. client is aware (09/29/2021 11:28 AM - rlerma) uploaded permit (09/07/2021 11:04 AM - klopez) MATERIALS HAVE BEEN ORERED WITH QR-24484 (09/02/2021 04:44 PM - rlerma) SUBMITTED PERMIT (09/01/2021 03:05 PM - klopez) verified info (08/30/2021 03:46 PM - lteniente) no longer pending anything (08/30/2021 03:46 PM - lteniente) pending contract, pending insurance proceeds (06/21/2021 11:26 AM - lteniente) |  |  | (12B) Ready to Invoice Insurance (Crystal) | Open | 2021-08-30 |  |  | lteniente |  |  | 2021-11-16 | lteniente | mmolano | Jessica Garcia | (409) 999-1079 | garciaj3504@icloud.com
4149 | R2085 | Jessie's Custom Airbrush | Jesus Ramos | 1703 N Grant St | Roma | TX | 78584 | lteniente | Low Slope Roof Systems | B. Roof Replacement; A. Metal; D. Retail Contract | (09) IN PRODUCTION | 2020-09-08 | lteniente | 2020-09-08 | 2021-11-16 | egomez |  | 20274.54 | 20274.54 | 10479.13 | 100 |  | 0 |  | 2020-09-08 |  | 0 |  |  | contact | Jesus Ramos |  | Gonzalo Pena |  |  | Residential | n | [6 empty] | 2020-09-08 |  | Pending Flashing and interior (11/16/2021 09:18 AM - egomez) Finished Roof and wood work. Trim and painting needs to be scheduled. (11/01/2021 07:17 AM - bbuffamonte) called client to update him on status of project. (08/18/2021 10:34 AM - officestaff) Site visit w/Rolando. Have a meeting lined up to meet with Gonzalo on scope of work for next week ( 8-16) (08/13/2021 10:22 AM - bbuffamonte) submitted permit (07/27/2021 03:11 PM - klopez) NEED TO GET WITH GONZALO ON STATUS FOR THIS PROJECT. (06/18/2021 12:58 PM - klopez) Still waiting for insurance to approve. (12/21/2020 04:14 PM - klopez) We are still waiting on approval from insurance reason why prj is on hold. Gonzalo has personally gone and spoke with the client letting him know about the matter. (11/19/2020 12:18 PM - klopez) called client to update status on their project/ material list. (10/14/2020 05:30 PM - klopez) sent customer EZtext touching base and advising of waiting period (09/08/2020 11:30 AM - ocovarrubias) pictures included on the contract (09/08/2020 11:20 AM - ocovarrubias) |  |  | (08) * Scheduled & Ready to Start | Open | 2020-09-08 |  |  | lteniente |  |  | 2021-11-16 | lteniente | egomez | Jesus Ramos | (956) 500-1713 | jessiesairbrush@hotmail.com
3430 | R2650 | Escobedo, Lilvia Residence | Escobedo, Lilvia Residence | 839 Tierra Encantada Street | Alamo | TX | 78516 | anovack | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-11-04 | anovack | 2020-08-11 | 2021-11-18 | srivas |  | 1500 | 1500 | 1500 | 100 |  | 0 |  | 2021-11-01 | Google | 0 |  |  | contact | Lilvia Escobedo |  | Flavio Padron |  |  | Residential | n | [6 empty] | 2021-11-01 |  | called back, verified info (11/09/2021 04:12 PM - lteniente) Called, didnt pick up left a voicemail (11/09/2021 04:10 PM - lteniente) no longer pending payment (11/04/2021 03:21 PM - lteniente) pending payment (11/01/2021 02:37 PM - lteniente) |  |  | (09) * Work In Progress | Open | 2021-11-01 |  |  | lteniente |  |  | 2021-11-18 | lteniente | srivas | Lilvia Escobedo | (956) 313-2329 | lilviarosas@gmail.com
3387 | C2875 | Our Lady of Refuge Church CCD Building | Our Lady of Refuge Church CCD Building | 4 W Eugene De Mazenod Ave | Roma | TX | 78584 | jestrada | Steep Slope Roof Systems | B. Roof Replacement; A. Tile (Clay); C. Additional Exterior Work; D. Retail Contract | (09) IN PRODUCTION | 2021-08-30 | jestrada | 2020-08-10 | 2021-11-23 | srivas |  | 44462.08 | 44462.08 | 22231.04 | 100 | Color of Tiles to be El Camino Blend | 0 | lteniente | 2021-08-30 |  | 0 |  |  | contact | Clint Brown |  | Juan Estrada |  |  | Commercial | n | [6 empty] | 2021-08-30 |  | crew is starting today (11/08/2021 09:43 AM - srivas) Spoke to Fernando he said he would start tom. morning (11/02/2021 10:02 AM - srivas) Material will be del. Monday Nov. 1 as per carlos from West-end (10/29/2021 02:24 PM - srivas) materials have been ordered with southern shingles with QC-62619 (09/22/2021 02:13 PM - rlerma) called client and let him know of status update of project. would like a call before we deliver the materials to see where we would we place them. (09/15/2021 03:34 PM - officestaff) permit uploaded (09/14/2021 09:05 AM - klopez) permit submitted (09/13/2021 03:43 PM - klopez) called client, didn't pickup. left voicemail with status of project. (09/01/2021 04:16 PM - officestaff) not available in eagleview or gaf (08/30/2021 03:37 PM - lteniente) |  |  | (10) Completed need to inspect ( PM, OC) | Open | 2021-08-30 |  |  | lteniente |  |  | 2021-11-23 | lteniente | srivas | Clint Brown | (956) 781-5323 | cbrown@cdob.org
3290 | R2505 | Rivera, Mario Residence | Rivera, Mario Residence | 3701 W Hobbs Dr | Edinburg | TX | 78539 | bmcsteen | Steep Slope Roof Systems | A. Metal ; B. Roof Repair; D. Insurance Proceeds; E. Special Order | (09) IN PRODUCTION | 2021-08-10 | bmcsteen | 2020-08-05 | 2021-10-27 | egomez |  | 70387.65 | 70387.65 | 35193.83 | 100 |  | 0 | lteniente | 2021-08-06 | Website | 0 |  |  | contact | Mario Rivera |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-08-06 |  | Materials have been ordered (10/27/2021 04:43 PM - egomez) CUSTOMER CALLED FOR STATUS UPDATE, TOLD HER WE WOULD CALL HER BACK (10/27/2021 12:10 PM - kelizondo) Send Material list to West End and SS. Waiting on Quote and ETA (08/23/2021 12:06 PM - egomez) permit uploaded (08/19/2021 10:28 AM - klopez) called client, did not pick up. sent text message with status of project. (08/18/2021 11:11 AM - officestaff) permit submitted (08/17/2021 09:37 AM - klopez) verified info (08/11/2021 04:26 PM - lteniente) no longer pending payment or contract, still pending insurance (08/06/2021 03:00 PM - lteniente) pending payment, pending insurance, pending contract (07/01/2021 08:53 AM - lteniente) (06/30/2021 04:50 PM - jestrada ) |  |  | (06) Schedule Labor | Open | 2021-08-06 |  |  | lteniente |  |  | 2021-10-27 | lteniente | egomez | Mario Rivera | (956) 457-2141 | rivy2k@aol.com
3084 | C2849 | Florence 2- Condo in SPI | Florence 2- Condo in SPI | 5570 Gulf Boulevard | South Padre Island | TX | 78597 | anovack | Low Slope Roof Systems | B.Roof Repair; A. Dura-Last; D. Retail Contract | (09) IN PRODUCTION | 2021-09-29 | anovack | 2020-07-30 | 2021-11-17 | kelizondo |  | 4139.48 | 4139.48 | 4139.48 | 100 |  | 0 |  | 2021-08-20 | Telemarketing | 0 |  |  | company | Florence 2- Condo in SPI | South Padre Island, TX Office | Juan Estrada |  |  | Commercial | n | [6 empty] | 2021-08-20 |  | JUAN SAID REPAIRS THAT HE FOUND HAD NOT BEEN COMPLETED, HAS NOT SAID WHAT YET (11/17/2021 04:10 PM - kelizondo) waiting for Wendy to call back to say whether Mr. Chacon can meet on Monday. I'll aim for 130pm (11/11/2021 04:24 PM - kelizondo) called client, left message with receptionist about updates on project. (10/12/2021 11:23 AM - officestaff) verified info (09/30/2021 04:20 PM - lteniente) No longer pending payment (09/29/2021 09:40 AM - lteniente) Pending payment (08/20/2021 02:21 PM - ctostado) |  |  | (11) Punchout - Corrections | Open | 2021-08-20 |  |  | ctostado |  |  | 2021-11-17 | ctostado | kelizondo
2718 | R1936 | Norman, Robert Residence | Norman, Robert Residence | 41344 Schafer Road | Los Fresnos | TX | 78566 | anovack | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract; E. Special Order | (09) IN PRODUCTION | 2021-10-14 | anovack | 2020-06-30 | 2021-11-16 | srivas |  | 16176.69 | 16176.69 | 10514.85 | 100 | Roof portion complete pending mod bit it has yet to be delivered from Budget. Sent P.O 8/18/20. | 0 | ctostado | 2020-12-05 | Google | 0 |  |  | contact | Robert Norman |  | Philip Westerman |  |  | Residential | n | [6 empty] | 2020-07-14 |  | Jorge with southern shingles ordered red granules should be in a week or so. I updated client as well (11/16/2021 09:09 AM - srivas) No luck finding granules. (11/02/2021 03:28 PM - srivas) Called client & no numbers on file were current numbers. I spoke to Philip and the number he had didn't work either. Rollie called all vendors this morning to see who had granules. (11/02/2021 03:27 PM - srivas) Need to call client and let them know we are waiting to get TARAKATA granules (11/01/2021 02:28 PM - srivas) granules have been ordered. (09/01/2021 10:05 AM - officestaff) looking for granules for correction (08/26/2021 12:20 PM - klopez) WPI-8E uploaded (08/02/2021 08:15 AM - klopez) Still not complete: Change status (07/20/2021 08:47 AM - pwesterman) Robert Norman Jul 9, 2021, 4:31 PM (11 days ago) to me, miriam@mcallenvalleyroofing.com, carolnrobbie@aol.com Philip, my wife and I spoke last night regarding the roof, and during an interesting time while raining and 10 leaks in our roof, 8 leaks in sunroom (flat roof) & 2 leaks in our closet upstairs. I asked her what was going on with her not sending the remaining payment and she said there had been several emails between her and you, and you stated someone was coming to finish it but that's been months. The issues we have are leaks and the bitmod was laid down hasty and has several flaws from huge wrinkles and crew walking on it while very hot and rubbing off the top layer. She forwarded all the emails today to you so that you could review what you and her had talked about and where you left off. I asked her to just pay the remainder minus the 10% you instructed and maybe you would come back to finish the roof. She didn't go for that, she said she doesn't trust that arrangement because of the bad experiences so far and would most likely be calling Lowes to repair the installation from McAllen Residential Construction, LLC. Philip, I paid my part which was the first installment from my 401K and she was to pay the remainder. I really hope something can be done before attorney's are employed by either party (and then everyone looses but the attorney). Please reach out to her to make closing actions. Her number is 540.846.7059 (07/20/2021 08:28 AM - pwesterman) ordered flashing p.o QR-23333 (03/22/2021 08:24 AM - klopez) notified client and pm that we will be sending workers on 03/22 (03/19/2021 03:40 PM - klopez) scheduled tio for 03/22 monday (03/15/2021 02:57 PM - klopez) SPOKE TO JORGE FROM SOTUHERN SHINGLES FOR THE PRESIDENTIAL SHINGLES WE ORDERED. ADVISED THAT IT COULD TAKE UP TO 4-6 WEEKS AND THE SHORTEST TIME COULD BE 3 WEEKS. HE WILL KEEP US UPDATED. (03/12/2021 09:31 AM - rlerma) will be needing more flashing (03/01/2021 04:15 PM - klopez) scheduled tio for monday 2/15 jonna to get with lalo for inspection and see how much he charges (02/12/2021 01:58 PM - klopez) erica get with lalo to do inspection (02/10/2021 01:09 PM - klopez) Flashing is ready will schedule tio when his availability opens up. (02/08/2021 09:55 AM - klopez) scheduled tio for this friday (01/26/2021 02:42 PM - klopez) also, production meeting with philip on scupper (01/21/2021 11:19 AM - klopez) waiting on custom flashing that has been ordered (01/21/2021 11:18 AM - klopez) scheduled rosalio for punch out on monday 1/18 (01/14/2021 04:50 PM - klopez) 1. Above the garage, even though we painted it, it still looks atrocious. Could we please install some painted wood over that?2. All the edges where we installed metal flashing. Some of them are still not sealed completely.3. The short lift between the 1st story flat roof and the shingle roof: Could we also install a painted wood piece to cover over the ugly old metal bent flashing. (12/07/2020 08:04 PM - pwesterman) As per Kevin Punch out list has been addressed. 12/2/2020 (12/03/2020 09:42 AM - jcoronado) reached out to customer to let him know techs would be on site this morning (10/13/2020 08:54 AM - ocovarrubias) called customer to let him know weather permitted, we will be starting project Monday (10/09/2020 04:25 PM - ocovarrubias) customer is reaching out for update, waiting on update from vendor so we can let customer know (10/01/2020 08:17 AM - ocovarrubias) sent mass EZtext advising fan of weather and delay (09/18/2020 09:09 AM - ocovarrubias) sent mass EZtext advising fan of weather and delay (09/11/2020 04:55 PM - ocovarrubias) pending material (09/08/2020 11:12 AM - jcoronado) texted customer that we will reach out when we have an update on his material (08/19/2020 04:27 PM - ocovarrubias) as per Philip, no permit just windstorm (08/10/2020 02:38 PM - ocovarrubias) called customer to touch base, told customer that we are aiming to get to his project within the next 2-3 weeks. customer is ok with that just wants updates (08/05/2020 12:22 PM - ocovarrubias) customer called wanting update on schedule (07/31/2020 10:46 AM - ocovarrubias) waiting for eagle view to come in (07/17/2020 03:32 PM - ocovarrubias) called customer to touch base, no answer, sent text advising of 2-3 week notice (07/17/2020 01:46 PM - ocovarrubias) 5 STAR Warranty Color Choice: Cottage Red Flat roof Color: (07/13/2020 03:55 PM - pwesterman) |  |  | (11) Punchout - Corrections | Completed | 2020-07-14 | 2020-12-05 |  | ocovarrubias | ctostado |  | 2021-07-22 | ctostado | gsolis | Robert Norman | (540) 846-6555 | robert5703@aol.com
2703 | C2934 | Gonzalez Auto Parts- San Antonio #11 Culebra | Gonzalez Auto Parts | 3518 Culebra Rd | San Antonio | TX | 78228 | anovack | Low Slope Roof Systems | B. Roof Over Construction; A. EPDM; A. Coating Acylic Based; D. Insurance Proceeds; E. Special Order | (09) IN PRODUCTION | 2021-11-01 | pwesterman | 2020-06-28 | 2021-11-08 | klopez |  | 0 | 0 | 0 | 0 | Working on getting a coating with insurance 3518 Culebra Rd, San Antonio, TX 78228 | 0 |  |  | Self Generated | 0 | [5 empty] | Philip Westerman |  |  | Commercial | n | [11 empty] | (04) Pre-Construction Meeting (PM,IS,OS) Call | [7 empty] | 2021-11-08 |  | klopez
2702 | C2937 | Gonzalez Auto Parts- San Antonio #8- Rigsby | Gonzalez Auto Parts | 3518 Culebra Rd | San Antonio | TX | 78228 | anovack | Low Slope Roof Systems | B. Roof Over Construction; A. Modified; D. Retail Contract | (09) IN PRODUCTION | 2021-10-29 | pwesterman | 2020-06-28 | 2021-11-01 | klopez |  | 45203.43 | 45203.43 | 3445.07 | 100 | Go over the metal with the new roof system | 0 |  | 2021-10-29 | Referral | 0 |  |  | contact | JAMES GONZALEZ |  | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-10-29 |  |  |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-10-29 |  |  | lteniente |  |  | 2021-11-01 | lteniente | klopez
2700 | C2935 | Gonzalez Auto Parts- Pleasanton #17 | Gonzalez Auto Parts | 3518 Culebra Rd | San Antonio | TX | 78228 | anovack | Low Slope Roof Systems | A. Coating Acylic Based; B.Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-11-01 | pwesterman | 2020-06-28 | 2021-11-01 | gsolis |  | 7193.56 | 7193.56 | 7093.56 | 100 |  | 0 |  | 2021-11-01 | Self Generated | 0 |  |  | company | J&R RGV RE Co., LLC | Gonzalez Auto Parts LTD | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-11-01 |  |  |  |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | Open | 2021-11-01 |  |  | lteniente |  |  | 2021-11-01 | lteniente | gsolis
2653 | R2324 | Martin, David Residence | Martin, David Residence | 4140 Las Floresta Avenue | Mercedes | TX | 78570 | anovack | Steep Slope Roof Systems | A. Tile (Clay); C. Additional Exterior Work; B. Roof Repair; D. Retail Contract; C. Additional Carpentry | (09) IN PRODUCTION | 2021-02-10 | anovack | 2020-06-22 | 2021-11-01 | srivas |  | 26563 | 26563 | 13281.5 | 100 | can not find on Nearmap | 0 |  | 2021-02-10 | Google | 0 |  |  | contact | David Martin |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2021-02-10 |  | Spoke to Juan E said that client is using their own insurance and the tile is discontinued so we are put on pause until we hear back from client. (11/01/2021 01:53 PM - srivas) CALLED FOR A QUOTE FOR 6 WINDOWS (08/31/2021 02:21 PM - kelizondo) client called wanting update, told client pm would stop by his home to let him know what the insurance was advising over discontinued tile. (08/31/2021 10:27 AM - rlerma) prj has been placed on hold due to tile has been discontinued will be getting in contact with juan to get status on tile from insurance. Also we are short on hip & ridge. Client called today asking when everything is going to be finished no one has been there for 3 weeks. When wanting to explain he interrupted and wanted to just talk to a higher up. Due to weather that we had, workers were unable to attend. (05/26/2021 10:55 AM - klopez) less than a quarter to finish. (05/04/2021 02:04 PM - klopez) called the client letting him know that the workers will be going back tomorrow. (04/27/2021 10:54 AM - klopez) called client, did not pick up send a message letting him know that the worker is having family issues and we will be sending someone new to finish proj. (04/21/2021 05:04 PM - klopez) scheduled for 03/29 (03/26/2021 09:48 AM - klopez) rescheduled hector for 03/25 (03/24/2021 09:26 AM - klopez) rescheduled hector for 03/24 (03/22/2021 01:31 PM - klopez) notified the client and pm about tentative date 03/22 (03/19/2021 03:45 PM - klopez) erika spoke with client to update him on his roof (03/17/2021 09:57 AM - klopez) scheduled wood work for joe for 03/22 scheduled coating for hector for 03/23 (03/15/2021 02:54 PM - klopez) project will be next in line after tommie wilkins (03/05/2021 12:10 PM - klopez) submitted permit (03/03/2021 11:47 AM - klopez) uploaded eagleview (02/12/2021 08:56 AM - klopez) ordering eagleview (02/11/2021 02:41 PM - klopez) called the client let him know about the 4v week lead (02/10/2021 03:53 PM - klopez) Flat roof (02/10/2021 09:37 AM - lteniente) |  |  | (14) Project on Hold | Open | 2021-02-10 |  |  | lteniente |  |  | 2021-05-26 | lteniente | klopez | David Martin | (361) 777-5658 | 4140lafloresta@gmail.com
2535 | R2330 | Garza, Roberta & Edgar Residence | Garza, Roberta Residence | 2601 Santa Ana | Mission | TX | 78572 | anovack | Steep Slope Roof Systems | A. Tile (Concrete); B. Roof Repair; D. Retail Contract; E. Special Order | (09) IN PRODUCTION | 2021-02-17 | anovack | 2020-06-10 | 2021-11-01 | srivas |  | 18812.48 | 18812.48 | 9406.24 | 100 | (956) 600-5977- First Reach out to Edgar | 0 |  | 2021-02-15 | Google | 0 | Pending Payment |  | contact | Roberta Garza |  | Philip Westerman |  |  | Residential | n | [6 empty] | 2021-02-15 |  | Touched base with philip said he was going to reach out to client so we can figure out a start date. (11/01/2021 01:46 PM - srivas) spoke to client about scheduling start date. client mentioned that attorney is asking to put project on hold due to insurance delay. (07/09/2021 08:15 AM - rlerma) erika will meet with philip (05/04/2021 03:00 PM - klopez) tio will get sample to claymex (04/19/2021 04:25 PM - klopez) need to find out what type of tile (03/15/2021 02:17 PM - klopez) uploaded permit (03/15/2021 08:57 AM - klopez) need to schedule a meeting with pm need to order materials birdstop and rake as well (03/05/2021 12:06 PM - klopez) ramiro is taking permits today (03/03/2021 11:58 AM - klopez) called the client let him know about the 2-3 week to order material if not stocked. let him know about the 4 week lead (02/17/2021 10:18 AM - klopez) (956) 600-5977- First Reach out to Edgar (02/15/2021 11:02 AM - pwesterman) |  |  | (14) Project on Hold | Open | 2021-02-15 |  |  | lteniente |  |  | 2021-07-09 | lteniente | rlerma | Roberta Garza | (956) 600-5975 | Roberta.tijerina@egginco.com
2465 | C2239 | Sunny Produce | Sunny Produce | 6500 S. 23rd. St. Suite 10 | McAllen | TX | 78503 | pwesterman | Low Slope Roof Systems | A. Metal; B.Roof Repair | (09) IN PRODUCTION | 2021-10-25 | anovack | 2020-06-04 | 2021-10-25 | ctostado |  | 2409.75 | 2409.75 | 1204.87 | 100 |  | 0 | ctostado | 2020-07-17 | Google | 0 |  |  | company | Sunny Produce | McAllen, TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2020-06-09 |  | Customer states still leaking (10/25/2021 11:58 AM - ctostado) scheduled Ramon for punch out 12/14 (12/11/2020 11:38 AM - klopez) punch out pending, leak (11/07/2020 09:53 AM - mmolano) Called customer on 9/17/20; spoke with Norma from A/P, she stated that job has not been completed. She said that she has emailed the office several times to let us know about the situation. MC (09/18/2020 09:11 AM - officestaff) reached out to customer, gave two weeks notice (06/09/2020 03:25 PM - ocovarrubias) |  |  | (11) Punchout - Corrections | Completed | 2020-06-09 | 2020-07-17 |  | ctostado | ctostado |  | 2021-10-25 | ctostado | ctostado | Victor Myers | (956) 631-2806 | myersv@sunnyproduce.com
2403 | C2370 | USA Fireworks | USA Fireworks | 6115 State Highway 107 | Mission | TX | 78573 | anovack | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-01-07 | anovack | 2020-06-01 | 2021-11-01 | egomez | 9484 | 10266.43 | 10266.43 | 6947.03 | 100 | 01-27-21 Ms. Castillo said its still leaking. She wants the project manager to go on Feb 1st to check it out. She will be out of town after the 5th until the end of the month. (Kelizondo) Project Manager said they still have leaks 01-21-21. That is why they are still holding $1,200 until we fix it. Cynthia107107@gmail.com | 0 | ctostado | 2020-09-17 | Google | 9484 |  |  | company | USA Fireworks | Mission, TX Office | Roel Cantu |  |  | Commercial | n | [6 empty] | 2020-07-28 |  | called client, said she would be back on the 7th or 8th of September. didn't tell me her availability and said to call her back then to figure that out with her. (08/27/2021 12:22 PM - officestaff) Waiting of client to return in April (03/04/2021 01:19 PM - gsolis) called the client to let her know that we can start her prj. client advised that she is still out of town and wont be back until April (03/01/2021 08:20 AM - klopez) called the client to see if we can send someone to check on leak. client advised that she is out of town no one will be there until monday (02/25/2021 08:22 AM - klopez) hector working on this prj. (02/12/2021 11:29 AM - klopez) still having leaks. need to get roel and a worker to go out there and check on leak. (02/08/2021 12:34 PM - klopez) need to get with roel on his availability. (01/12/2021 10:06 AM - klopez) scheduled hector 1/18 (01/08/2021 11:18 AM - klopez) as per roel customer still has leaks need to send tech with PM to find problem and correct (01/07/2021 02:03 PM - gsolis) CALLED THE CLIENT SO WE CAN DO INSPECTION FOR LEAK. WONT BE OPEN UNTIL MONDAY, WILL SCHEDULE UNTIL THEN. (11/25/2020 12:11 PM - klopez) called customer to let her know we will be there today (08/24/2020 08:42 AM - ocovarrubias) sent customer a follow up email, to touch base (08/10/2020 01:04 PM - ocovarrubias) called customer, no answer, left voicemail touching base and let her know of 2-3 week delay due to hurricane Hanna (07/31/2020 02:24 PM - ocovarrubias) |  |  | (08) * Scheduled & Ready to Start | Completed | 2020-07-28 | 2020-09-17 |  | ctostado | ctostado |  | 2021-11-01 | ctostado | egomez | Cindy Castillo | (956) 240-1580
1545 | C2767 | Sea Breeze 1 | Sea Breeze 1 | 4300 Gulf Boulevard | South Padre Island | TX | 78597 | wmitchell | Low Slope Roof Systems | B. Roof Replacement; A. TPO; D. Retail Contract | (09) IN PRODUCTION | 2021-06-10 | wmitchell | 2019-11-20 | 2021-11-15 | bbuffamonte | 58685 | 0 | 0 | 0 | 0 | this was an old will project i have sent needed info and contact was waiting on a board meeting to present bid. | 0 |  |  |  | 0 | [5 empty] | Gary Solis |  |  | Commercial | n | [8 empty] | pending change order (10/26/2021 02:01 PM - klopez) called client to let know we will be expected to work on project tomorrow. (10/06/2021 10:47 AM - officestaff) CRANE AND MATERIALS ARE ARRIVING ON PROPERTY OCT 5, START DATE (10/04/2021 08:56 AM - kelizondo) tentative date for beto on 10/6-10/8. (09/28/2021 11:08 AM - officestaff) permit submitted (08/11/2021 04:19 PM - klopez) as per p.m will be starting around October (08/02/2021 09:59 AM - klopez) disregard the previous message (06/29/2021 03:26 PM - klopez) Permit has been approved, will pick up tomorrow. (06/29/2021 01:25 PM - klopez) called client giving her update on permit status . didnt pick up left voice mail (06/23/2021 05:30 PM - klopez) Heard back and the board is not in position to move forward right now. (03/17/2020 09:55 AM - gsolis) |  |  | (09) * Work In Progress | [7 empty] | 2021-11-15 |  | bbuffamonte
1526 | R1788 | Stillman, Valerie Residence | Stillman, Valerie Residence | 124 Stillman Rd | Brownsville | TX | 78523 | bcalderon | Low Slope Roof Systems | C. Addtional Exterior Work | (09) IN PRODUCTION | 2021-03-25 | bcalderon | 2019-11-18 | 2021-09-29 | officestaff | 68862.49; 69132.49; 69132.49 | 69132.49 | 69132.49 | 34566.24 | 100 |  | 0 | ctostado | 2020-10-10 | Repeat | 0 |  |  | contact | Valerie Stillman |  | Juan Estrada |  |  | Residential | n | [6 empty] | 2020-02-27 |  | pending response from customer about project. (09/29/2021 08:56 AM - officestaff) juan will communicate with the client and will get back to production on whats going to happen. (09/15/2021 10:11 AM - klopez) as per Client has outside consultation, now we will be waiting for them to finish to go back (07/28/2021 09:31 AM - klopez) Pending Interior paint (07/10/2020 08:45 AM - egomez) as per cust. on hold until further notice due to COVID-19 (04/03/2020 11:02 AM - jcoronado) tarp up attic before any roof work. (04/03/2020 11:01 AM - jcoronado) 956-350-9697 Stillman Residence number. (03/31/2020 10:57 AM - jcoronado) Cedar shakes where shipped today - Need to get ETA from Noe (03/20/2020 03:32 PM - egomez) left a voicemail in regards to reroof. (02/28/2020 02:13 PM - jcoronado) |  |  | (11) Punchout - Corrections | Completed | 2020-02-27 | 2020-10-10 |  | ctostado | ctostado |  | 2021-03-25 | ctostado | ctostado | Valerie Stillman | (956) 639-1117
1146 | R2669 | Freed, R Residence | Freed, R Residence | 7202 Lake Victoria | Laredo | TX | 78041 | dvazquez | Steep Slope Roof Systems | A. Tile (Concrete); B. Roof Repair; D. Retail Contract | (09) IN PRODUCTION | 2021-11-18 | dvazquez | 2019-09-06 | 2021-11-24 | lteniente | 2262 | 0 | 0 | 0 | 0 | Leak source is power vent. Unable to locate leak source so need to wait for rain for attic inspection. | 0 |  |  | Referral | 0 | Material QTY Price Total Rag Sets 2 $10 $20 Battens 12 $1.78 $21.36 OSB 1 $36.37 $36.37 Framing Nails Box 1 $24.67 $24.67 Synthetic Underlayment 1 $98.66 $98.66 Self-Adhesive Underlayment1 $95.54 $95.54 12 in. x 25 ft. Lead Roll 1 $153.95 $153.95 S-Barrel Tile Fastening Nails1 $33.35 $33.35 Tile Adhesive Tube 2 $15 $30 Delivery Fee $250 Total Allotted for Material $763.90+ Tax $63.02 = $826.92 Labor 1 Days @ $400/day = $400 1 OSB Replacement X $25 = $25 12 Batten Replacements X $1 = $12 Total Allotted for Labor $437 Equipment/Other Permit $86 Total Allotted for Equipment/Other $86 + Tax $7.10 = $93.10 TOTAL EXPENSES ALLOTTED FOR $1357.02 CONTRACT PRICE $2262-- (1357.02 / .60 = $2261.70) |  |  |  |  | Ed Vazquez |  |  | Residential | n | [8 empty] | left a voicemail (11/24/2021 02:20 PM - lteniente) no longer pending payment (11/18/2021 01:36 PM - lteniente) pending payment (11/16/2021 07:36 PM - lteniente) 11/08/2021 Leak source is power vent: OSB water staining under power vent, insulation/sheet rot wet along with torn/weathered felt around power vent. Ed informed customer verbally and working on estimate. (11/08/2021 06:53 PM - dvazquez) |  |  | (02) Create Material List (Gary) | [7 empty] | 2021-11-24 |  | lteniente | R Freed | (956) 723-6292
1051 | C2674 | Immaculate Conception RGC Main Church Building | Convent - Immaculate Conception | 101 E 3rd Street | Rio Grande City | TX | 78572 | tthirlwall | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; A. Synthetic Material; D. Retail Contract | (09) IN PRODUCTION | 2021-05-06 | tthirlwall | 2019-08-22 | 2021-10-14 | rlerma |  | 67125.76 | 67125.76 | 30700.37 | 100 |  | 0 |  | 2021-04-20 | Self Generated | 0 |  |  | company | Immaculate Conception | Brownsville, TX Office | Philip Westerman |  |  | Commercial | n | [6 empty] | 2021-04-20 |  | P.O southern shingles QC-62770 (10/11/2021 02:46 PM - klopez) material shortage on shingles. waiting on transfer from ABC supply from San Antonio to mcallen. client is aware. (10/01/2021 07:29 AM - rlerma) sub ran out of underlayment. As per Alfredo Villalobos we are to use starwrap underlayment to cover the remaining areas that need to be finished. (09/24/2021 02:36 PM - rlerma) Spoke to PM; asbestos report that was sent is not the full report. PM is looking through all files to find correct report to upload. (07/26/2021 03:50 PM - anovack) talked to pm about the asbestos report, the one uploaded on data forma is not a full report but a bill from analysis company. pm will check hard files and call back ramiro or brian. (07/26/2021 08:24 AM - rlerma) put on hold waiting on philip to get an asbestos test that is required by the city of edinburg landfill (07/23/2021 09:09 AM - gsolis) city of edinburg requires an asbestos report in order to dispose. A tech must be hired. Philip has been advised that he must take care of this for his project (07/23/2021 09:07 AM - gsolis) materials have been ordered with PO QR-62127, client and pm, have be made aware (07/19/2021 11:29 AM - rlerma) COLOR CHANGE: Colonial Slate (07/19/2021 08:58 AM - pwesterman) project has been put on hold by PM, client has changed their mind on the material and will make a change order (06/18/2021 10:07 AM - rlerma) permit uploaded (05/26/2021 08:33 AM - klopez) Permit has been approved. (05/25/2021 09:51 AM - klopez) received an email from the city Hello This is Maddie, we have received the information for the Roof Repair for the Immaculate Church . At the moment the only issue is that the Building Inspectors won't be in the office until Monday. I can try having the process approved faster but without them here to review it might take longer. I will thoroughly appreciate it if you can be patient until they return back. Sincerely Ms.Morin (05/19/2021 04:14 PM - klopez) submitted permit (05/19/2021 09:34 AM - klopez) color teak owens corning as per philip (05/04/2021 02:39 PM - lteniente) pending payment (04/20/2021 03:49 PM - lteniente) New totals:1. Parish: $59,880.57 + Asbestos Survey $550= $60,430.572. Offices: $12,420.19These are for the Owens Corning shingles with regular galvanized drip edge and you will provide tax-free paperwork. I know you are tax-free but we just have to have them for our files. (04/01/2021 09:02 AM - pwesterman) |  |  | (09) * Work In Progress | Open | 2021-04-20 |  |  | lteniente |  |  | 2021-10-14 | lteniente | rlerma | Clint Brown | (956) 781-5323 | cbrown@cdob.org
521 | C1465 | Interamerican Food Corporation | Interamerican Food Corporation | 8419 San Gabriel Dr | laredo | TX | 78045 | egomez | Low Slope Roof Systems | B. Roof Replacement; D. Retail Contract | (09) IN PRODUCTION | 2020-11-07 | egomez | 2019-05-20 | 2021-08-02 | klopez |  | 184025 | 184025 | 18402.44 | 100 |  | 0 | ctostado | 2020-01-27 |  | 0 |  |  | company | Interamerican Food Corporation | Laredo, TX Office | Ed Vazquez |  |  | Commercial | n | [6 empty] | 2018-09-10 |  | WE NEED TO GET WITH ED FOR THIS PRJ. (06/18/2021 12:59 PM - klopez) waiting until it rains so primo and ed can go by to inspect. (03/30/2021 12:01 PM - klopez) erica will check with primo to schedule him for this week. (01/26/2021 02:27 PM - klopez) need to schedule a conference call with Erica, Ed, and the client. (01/21/2021 10:46 AM - klopez) needing a sub for this project. (01/12/2021 09:40 AM - klopez) punch out pending, leak (11/07/2020 09:55 AM - mmolano) Replacing skylights (05/21/2019 09:37 AM - egomez) |  |  | (08) * Scheduled & Ready to Start | Completed | 2019-05-20 | 2020-01-27 |  | egomez | ctostado |  | 2021-08-02 | ctostado | klopez | Carlos Alvarez | (956) 712-4133
37 | C1324 | San Pedro Apartments | Bldg 15 San Pedro Apartments | 4206 San Gabriel, Bldg 15 | Mission | TX | 78572 | pwesterman | Steep Slope Roof Systems | B. Roof Replacement; A. Metal | (09) IN PRODUCTION | 2021-07-22 | pwesterman | 2019-03-13 | 2021-10-01 | egomez |  | 504925.74 | 514275.95 | 57924.87 | 100 | GATE CODE 1703 | 0 | ctostado | 2021-04-30 | Google | 0 |  |  | company | 1st Choice Management | 1st Choice Management | Philip Westerman |  | Material Amount : 184,500 Material Tax: 15,221.25 change Order : 11,403 Change Order Tax : 940.75 | Commercial | n | [6 empty] | 2018-05-18 |  | Pending interior repairs (10/01/2021 11:55 AM - egomez) spoke with the client to let her know that materials will be getting dropped off today and we will be also dropping off the skytrack as well. (09/23/2021 02:14 PM - klopez) scheduled aurelio 9/21 - 9/24 (09/15/2021 10:08 AM - klopez) ***disregard previous message*** rosalio was able to locate several cracks and sealed them up. (06/02/2021 03:53 PM - klopez) rosalio went by today sealed some cracks that he found he advised the client that the leaks mught be coming from the bricks from the building due to the membrane it has its absorbing the water when it rains causing leakage to happen. (06/02/2021 03:51 PM - klopez) Roof has been completed only thing pending is Paint. Scheduled for 4/23/21 to paint wood that was replaced (04/19/2021 11:45 AM - egomez) need to paint wood (04/16/2021 10:03 AM - klopez) 25% left (03/30/2021 12:33 PM - klopez) rescheduled randy and ruben to work on this prj. (03/15/2021 02:51 PM - klopez) still pending coils, will schedule joe for 03/15 - 03/16 (03/10/2021 04:28 PM - klopez) pending 25% of the roof waiting on the coils to arrive (03/05/2021 10:44 AM - klopez) need to move sky track (01/26/2021 04:48 PM - klopez) pending building #2 (01/21/2021 11:03 AM - klopez) uploaded Eagle view (01/07/2021 11:38 AM - klopez) Skytrack ordered, materials ordered. Good to start on 11/23 (11/17/2020 11:26 AM - mmolano) Rosalio Gomez is working on interior repairs for building 6302 (02/12/2020 11:05 AM - egomez) Spoke to Miguel he finished installing trim and was going to start working on he field but there is rain for tomorrow and Thursday he doesn't want to open up and risk water from going in. he will be at San Pedro Wednesday but will send some of his workers to go check everything is clean an make sure everything is ok around job site (11/11/2019 08:29 AM - egomez) Sandra Reported possible damage to AC unit pending pictures (09/18/2019 10:50 AM - avillalobos) |  |  | (06) Schedule Labor | Completed | 2019-03-19 | 2021-04-30 |  | ctostado | ctostado |  | 2021-10-01 | ctostado | egomez | Carmen Major | (210) 690-2550 | cmajor@1stchoice.com