## General
PROJECT ID | NUMBER ALT | PROJECT NAME | TYPE | SUBTYPE | PRODUCTION STATUS | PRODUCTION STATUS DATE | SALES PERSON NAME | BUILDING NAME | BUILDING ADDRESS | BUILDING CITY | BUILDING STATE | BUILDING ZIP | ORIGINAL CONTRACT AMOUNT | REVISED CONTRACT AMOUNT | DIVISION
7498 | R2676 | MUNOZ, CIRIA Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; A. Metal ; B. Roof Repair; D. Insurance Proceeds | (01) Validate Info - (Leila) | 2021-11-23 | Flavio Padron | MUNOZ, CIRIA Residence | 803 S. STANDARD AVE | SAN JUAN | TX | 78589 | 3916.15 | 3916.15 | Residential
7107 | R2677 | Ornelas, Miguel Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (01) Validate Info - (Leila) | 2021-11-23 | Roel Cantu | Ornelas, Miguel Residence | 2432 Quince Ave, | McAllen | TX | 78501 | 5250 | 5250 | Residential
7996 | R2672 | Gonzalez, Mario Residence | Exterior | Gutters | (02) Create Material List (Gary) | 2021-11-24 | Juan Estrada | Gonzalez, Mario Residence | 2804 Seve Ln | Laredo | TX | 78045 | 3098.75 | 3098.75 | Residential
7980 | R2666 | HALL, BILLIE Residence | Exterior | Gutters | (02) Create Material List (Gary) | 2021-11-24 | Juan Estrada | HALL, BILLIE Residence | 2205 Daffodil Ave | MCALLEN | TX | 78501 | 700 | 700 | Residential
8092 | C2961 | Green Gate Grove | Exterior | Woodwork | (02) Create Material List (Gary) | 2021-11-24 | Juan Estrada | Green Gate Grove | 700 N. Bentsen Palm Dr. | Palmview | TX | 78572 | 16237.5 | 16237.5 | Commercial
8091 | C2962 | Green Gate Grove | Exterior | Gutters | (02) Create Material List (Gary) | 2021-11-24 | Juan Estrada | Green Gate Grove | 700 N. Bentsen Palm Dr. | Palmview | TX | 78572 | 9195.84 | 9195.84 | Commercial
1146 | R2669 | Freed, R Residence | Steep Slope Roof Systems | A. Tile (Concrete); B. Roof Repair; D. Retail Contract | (02) Create Material List (Gary) | 2021-11-24 | Ed Vazquez | Freed, R Residence | 7202 Lake Victoria | Laredo | TX | 78041 | 0 | 0 | Residential
7956 | R2662 | BOCANEGRA, LINDA Residence | Low Slope Roof Systems | C. Addtional Interior Work; C. Addtional Exterior Work; B.Roof Repair; D. Retail Contract; A. Tile | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-12 | Roel Cantu | BOCANEGRA, LINDA Residence | 729 KIKA DE LA GARZA BLVD | LA JOYA | TX | 78560 | 10540 | 10540 | Residential
7931 | C2932 | GoodWill Flashing | Low Slope Roof Systems | A. TPO; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-10-29 | Will Mitchell | Goodwill Dixieland | 702 Dixieland rd | Harlingen | TX | 78550 | 1829.17 | 1829.17 | Commercial
7918 | R2661 | GARZA, OLGA Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-10 | Victor Perez | GARZA, OLGA Residence | 118 PARK LANE WEST | HARLINGEN | TX | 78552 | 7581.67 | 8506.67 | Residential
7911 | R2664 | Martin, Matthew Residence | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-11 | Orlando Marquez | Martin, Matthew Residence | 14003 Red Maple Wood | SAN ANTONIO | TX | 78249 | 3289.45 | 3289.45 | Residential
7870 | C2933 | Gonzalez Auto Parts #1 4220 San Bernardo | Low Slope Roof Systems | A. Metal; B.Roof Repair | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-01 | Philip Westerman | Gonzalez Auto Parts | 4220 San Bernardo Ave | LAREDO | TX | 78041 | 3445.25 | 3445.25 | Commercial
7640 | C2907 | Lazy A Ranch Beeville: SKIDMORE | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-10-28 | Philip Westerman | Lazy A Ranch Beeville: SKIDMORE | 2785 GUAJOLOTE ROAD | SKIDMORE | TX | 78389 | 6307.86 | 6307.86 | Commercial
7631 | R2624 | Ayala, Hilda Residence | Exterior |  | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-10-07 | Roel Cantu | Ayala, Hilda Residence | 133 Sunflower Ave. | McAllen | TX | 78504 | 0 | 0 | Residential
7537 | C2912 | Alfredo Casso & Co Inc | Low Slope Roof Systems | A. Coating Acylic Based; A. Coating Silicone Based; B.Roof Repair; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-10-18 | Ed Vazquez | Alfredo Casso & Co Inc | 14101 Transportation Ave | Laredo | TX | 78041 | 9730.59 | 9730.59 | Commercial
8033 | C2958 | O'Hanlon Law Firm 2 | Steep Slope Roof Systems | A. Metal ; B. Roof Repair; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-18 | Will Mitchell | O'Hanlon Law Firm | 426 West Caffery Ave. | Pharr | TX | 78577 | 5119.6 | 5119.6 | Commercial
7461 | C2955 | TITLEMAX LAREDO (by Gonzalez Auto Parts) | Low Slope Roof Systems | B. Roof Over Construction; A. Modified; D. Insurance Proceeds; E. Special Order | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-23 | Philip Westerman | TITLEMAX LAREDO | 4316 SAN BERNARDO AVE | LAREDO | TX | 78041 | 51183.87 | 51183.87 | Commercial
7425 | C2936 | Gonzalez Auto Parts- #9 Laredo | Low Slope Roof Systems | B. Roof Replacement; B. Roof Over Construction; A. Metal; A. Modified; A. Coating Silicone Based; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-04 | Philip Westerman | Gonzalez Auto Parts | 3518 Culebra Rd | San Antonio | TX | 78228 | 42695.33 | 42695.33 | Commercial
8019 | C2957 | SOUTHEASTERN FREIGHT LINES: RYAN KORTHAUER | Exterior | Gutters | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-17 | Will Mitchell | SOUTHEASTERN FREIGHT LINES: RYAN KORTHAUER | 1800 VOTECH DRIVE | WESLACO | TX | 78596 | 2021.56 | 2021.56 | Commercial
5871 | C2919 | Move it Storage Austin | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-10-13 | Philip Westerman | Move it Storage Austin | 9311 N FM 620, | Austin | TX | 78726 | 3231.42 | 3231.42 | Commercial
2703 | C2934 | Gonzalez Auto Parts- San Antonio #11 Culebra | Low Slope Roof Systems | B. Roof Over Construction; A. EPDM; A. Coating Acylic Based; D. Insurance Proceeds; E. Special Order | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-08 | Philip Westerman | Gonzalez Auto Parts | 3518 Culebra Rd | San Antonio | TX | 78228 | 0 | 0 | Commercial
2702 | C2937 | Gonzalez Auto Parts- San Antonio #8- Rigsby | Low Slope Roof Systems | B. Roof Over Construction; A. Modified; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-01 | Philip Westerman | Gonzalez Auto Parts | 3518 Culebra Rd | San Antonio | TX | 78228 | 45203.43 | 45203.43 | Commercial
2700 | C2935 | Gonzalez Auto Parts- Pleasanton #17 | Low Slope Roof Systems | A. Coating Acylic Based; B.Roof Repair; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-01 | Philip Westerman | Gonzalez Auto Parts | 3518 Culebra Rd | San Antonio | TX | 78228 | 7193.56 | 7193.56 | Commercial
7972 | C2941 | DOLLAR GENERAL | Low Slope Roof Systems | C. Addtional Exterior Work; A. Metal; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-19 | Juan Estrada | DOLLAR GENERAL | 1300 W Ruben M Torres Blvd | BROWNSVILLE | TX | 78520 | 3117.6 | 3117.6 | Commercial
7804 | R2646 | ROHR, AL Residence | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-11-05 | Juan Estrada | ROHR, AL Residence | 1510 E BUS HWY 83, LEMON TREE ESTATES UNIT C5 | MISSION | TX | 78572 | 2100 | 2100 | Residential
7790 | C2927 | SILVER SANDS RENTALS (2727 11th St. U.24) | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract; E. Special Order | (05) Order and Schedule Material | 2021-11-12 | Philip Westerman | SILVER SANDS VACATION RENTALS | 732 SAND CASTLE DRIVE, UNIT 3 | PORT ARANSAS | TX | 78373 | 1577.48 | 1577.48 | Commercial
7784 | C2917 | T-Mobile Mobile Skylights | Low Slope Roof Systems | A. BUR; B.Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-10-12 | Will Mitchell | T-Mobile | 3711 San Gabriel | Mission | TX | 78572 | 9394.47 | 9394.47 | Commercial
7271 | R2573 | Daniels, John Residence | Exterior | Gutters | (05) Order and Schedule Material | 2021-08-26 | Juan Estrada | Daniels, John Residence | 104 NW Augusta Square, | McAllen | TX | 78503 | 1000 | 1000 | Residential
7759 | C2920 | SILVER SANDS RENTALS (732 Sand Castle Dr) | Steep Slope Roof Systems | B. Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-11-12 | Philip Westerman | SILVER SANDS VACATION RENTALS | 732 SAND CASTLE DRIVE, UNIT 3 | PORT ARANSAS | TX | 78373 | 1631.6 | 1631.6 | Commercial
6599 | C2817 | Mission Consolidated Independent School District | Low Slope Roof Systems | A. Modified; B.Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-08-26 | Gary Solis | Mission Consolidated Independent School District | 1201 bryce | mission | TX | 78572 | 57145.18 | 57145.18 | Commercial
6409 | R2465 | Gonzalez, Sergio Residence | Exterior | Windows | (05) Order and Schedule Material | 2021-08-16 | Roel Cantu | Gonzalez, Sergio Residence | 3217 Sunbow Ln | McAllen | TX | 78504 | 2430 | 2430 | Residential
6340 | R2660 | Conner, David Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Tile (Concrete); D. Insurance Proceeds | (05) Order and Schedule Material | 2021-11-15 | Victor Perez | Conner, David Residence | 1318 Tierra Santa St | Weslaco | TX | 78596 | 59393 | 59393 | Residential
6224 | C2694 | Sea Vista Condominiums I | Low Slope Roof Systems | B. Roof Over Construction; A. Coating Silicone Based; D. Retail Contract; E. Special Order | (05) Order and Schedule Material | 2021-11-10 | Philip Westerman | Sea Vista Condominiums | 110 Padre Blvd, | South Padre Island | TX | 78597 | 70699.25 | 70699.25 | Commercial
7880 | R2665 | Flores, Molleigh Residence | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-11-17 | Victor Perez | Flores, Molleigh Residence | 84 Sunrise Rd | RIO GRANDE CITY | TX | 78582 | 1799.67 | 1799.67 | Residential
5644 | C2695 | Sea Vista Condominiums II | Low Slope Roof Systems | B. Roof Over Construction; A. Coating Silicone Based; D. Retail Contract; E. Special Order | (05) Order and Schedule Material | 2021-11-10 | Philip Westerman | Sea Vista Condominiums | 110 Padre Blvd, | South Padre Island | TX | 78597 | 82855.36 | 82855.36 | Commercial
7992 | R2663 | PALMA, MARISSA Residence | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-11-17 | Victor Perez | PALMA, MARISSA Residence | 819 W COSTA RICA AVE | PHARR | TX | 78577 | 1799.67 | 1799.67 | Residential
7862 | R2651 | ARAFAT, NANCY Residence | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-11-16 | Roel Cantu | ARAFAT, NANCY Residence | 3908 SUNDOWN DRIVE | MCALLEN | TX | 78503 | 11200 | 11200 | Residential
7520 | R2613 | PRUITT, SHELIA Residence | Exterior | Gutters | (05) Order and Schedule Material | 2021-10-06 | Philip Westerman | PRUITT, SHELIA Residence | 800 N 46TH | MCALLEN | TX | 78501 | 875 | 875 | Residential
7516 | C2900 | Specs | Exterior | Gutters | (05) Order and Schedule Material | 2021-11-10 | Will Mitchell | Specs | 822 Dixieland Rd | Harlingen | TX | 78552 | 2463.84 | 2463.84 | Commercial
7644 | R2619 | Eric Piater | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract | (06) Schedule Labor | 2021-10-12 | Victor Perez | Piater, Eric Residence | 1310 Tierra Encantada, Weslaco, TX 78596 | Weslaco | TX | 78596 | 1350 | 1350 | Residential
7437 | C2764 | RandR Ventures LLc Casa Padre | Low Slope Roof Systems | B. Roof Replacement; A. Coating Acylic Based; D. Retail Contract | (06) Schedule Labor | 2021-11-16 | Alfredo Villalobos | Casa Padre | 7480 Padre Island Hwy | Brownsville | TX | 78521 | 56895.12 | 56895.12 | Commercial
7779 | R2641 | Polley, Eric Residence 1631 | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (06) Schedule Labor | 2021-11-18 | Will Mitchell | Polley, Eric Residence | 1631 Throckmorton | Harlingen | TX | 78550 | 9456.25 | 13436.25 | Residential
7377 | C2881 | Aquiles Inc. (Clear Coat 3 exterior walls) | Exterior |  | (06) Schedule Labor | 2021-10-18 | Philip Westerman | Aquiles Inc. | 3201 International Blvd, | Hidalgo | TX | 78557 | 20420.58 | 20420.58 | Commercial
7327 | C2833 | 7-Eleven # 41871 | Low Slope Roof Systems | B. Roof Replacement; A. PVC; D. Retail Contract | (06) Schedule Labor | 2021-11-05 | Gary Solis | 7-Eleven # 41871 | 1327 E. Interstate 2 | Mission | TX | 78572 | 37616.88 | 37616.88 | Commercial
7892 | R2644 | Mario Rueda | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract; E. Special Order | (06) Schedule Labor | 2021-11-05 | Victor Perez | Rueda, Mario Residence | 1107 Helen Avenue | Mission | TX | 78572 | 1015 | 1015 | Residential
3290 | R2505 | Rivera, Mario Residence | Steep Slope Roof Systems | A. Metal ; B. Roof Repair; D. Insurance Proceeds; E. Special Order | (06) Schedule Labor | 2021-10-27 | Juan Estrada | Rivera, Mario Residence | 3701 W Hobbs Dr | Edinburg | TX | 78539 | 70387.65 | 70387.65 | Residential
7158 | R2592 | John Harper | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract | (06) Schedule Labor | 2021-10-12 | Orlando Marquez | HARPER, JOHN Residence | 19910 Encino Ridge St, | San Antonio | TX | 78259 | 2116.8 | 2116.8 | Residential
7589 | C2923 | LA PALABRA VIVIENTES MINISTRY | Low Slope Roof Systems | C. Addtional Exterior Work; A. Metal; A. Coating Acylic Based; B.Roof Repair; D. Retail Contract | (06) Schedule Labor | 2021-11-02 | Juan Estrada | LA PALABRA VIVIENTES MINISTRY | 171 DEANNA DR | SAN JUAN | TX | 78589 | 0 | 0 | Commercial
7086 | C2891 | Utility Trailer Sales South East Texas | Low Slope Roof Systems | A. Metal; A. TPO; B.Roof Repair; D. Retail Contract | (06) Schedule Labor | 2021-11-10 | Victor Perez | Utility Trailer Sales South East Texas | 4320 Trade Center | Laredo | TX | 78041 | 10294.71 | 10294.71 | Commercial
6935 | R2567 | Jester, William Residence | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (06) Schedule Labor | 2021-08-17 | Orlando Marquez | Jester, William Residence | 4910 Haven Oak, | San Antonio | TX | 78249 | 2972.59 | 2972.59 | Residential
37 | C1324 | San Pedro Apartments | Steep Slope Roof Systems | B. Roof Replacement; A. Metal | (06) Schedule Labor | 2021-10-01 | Philip Westerman | Bldg 15 San Pedro Apartments | 4206 San Gabriel, Bldg 15 | Mission | TX | 78572 | 504925.74 | 514275.95 | Commercial
6653 | R2480 | Cascos, Rebecca Residence | Exterior | Windows | (08) * Scheduled & Ready to Start | 2021-06-25 | Roel Cantu | Cascos, Rebecca Residence | 3 Ivy Lane | Brownsville | TX | 78521 | 3499 | 3499 | Residential
7997 | C2953 | Jehovah Witness Alton | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-21 | Gary Solis | Jehovah Witness Alton | 2613 W Main Ave | Alton | TX | 78573 | 37290 | 37290 | Commercial
6454 | R2574 | Salinas, Dana Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-01 | Victor Perez | Salinas, Dana Residence | 13502 23rd Lane | Ediburg | TX | 78541 | 16875.67 | 16875.67 | Residential
7826 | R2637 | Garza, Diane Residence | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair | (08) * Scheduled & Ready to Start | 2021-11-15 | Roel Cantu | Garza, Diane Residence | 815 Avenida Escandon | Rancho Viejo | TX | 78575 | 17128 | 17128 | Residential
7371 | C2846 | Atlas Restoration / Goodwill Store | Low Slope Roof Systems | A. TPO; B.Roof Repair; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-09-10 | Will Mitchell | Goodwill Store | 702 Dixieland Road | Harlingen | TX | 78552 | 3400 | 5100 | Commercial
7534 | R2636 | Jeremias Tezcucano 2018 E. 21st St. | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-09 | Philip Westerman | Tezcucano, Jerimias Residence | 2018 E. 21ST ST | MISSION | TX | 78574 | 3454.19 | 3454.19 | Residential
6088 | C2691 | Los Compadres | Low Slope Roof Systems | B. Roof Over Construction; A. Dura-Last; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-08-26 | Will Mitchell | Los Compadres | 1012 S Closner Blvd | Edinburg | TX | 78542 | 15958.83 | 15958.83 | Commercial
6010 | R2427 | Sharpless, Joshua Residence | Exterior | Windows | (08) * Scheduled & Ready to Start | 2021-06-26 | Juan Estrada | Sharpless, Joshua Residence | 1505 Goldcrest Ave | McAllen | TX | 78504 | 1632.78 | 1632.78 | Residential
7732 | C2914 | MCALLEN BIS ASSOCIATES | Low Slope Roof Systems | B. Roof Replacement; A. Metal; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-16 | Gary Solis | FD McAllen | 5901 S International Pkwy | McAllen | TX | 78503 | 1450 | 1450 | Commercial
5687 | R2374 | Garcia, Alejandro Residence | Exterior | Windows | (08) * Scheduled & Ready to Start | 2021-10-26 | Roel Cantu | Garcia, Alejandro Residence | 915 Navajo Drive | Rio Grande City | TX | 78582 | 9815 | 9815 | Residential
7659 | R2659 | FRED GOMEZ: LA FERIA | Low Slope Roof Systems | B. Roof Replacement; A. TPO; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-17 | Roel Cantu | FRED GOMEZ: LA FERIA | 103 S MAIN ST | LA FERIA | TX | 78559 | 28000 | 28000 | Commercial
5215 | C2693 | Rodd Field Congregation of Jehovah's Witness | Steep Slope Roof Systems | B. Roof Replacement; A. Metal ; C. Additional Exterior Work; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-08 | Gary Solis | Rodd Field Congregation of Jehovah's Witness | 2753 Rodd Field Road | Corpus Christi | TX | 78414 | 52500 | 52500 | Commercial
4958 | R2383 | Revisore, Sharon Interior and Garage | Steep Slope Roof Systems | C. Additional Interior Work; D. Retail Contract; C. Additional Carpentry | (08) * Scheduled & Ready to Start | 2021-11-16 | Philip Westerman |  | 3954 Dana Ave | Brownsville | TX | 78526 | 22488.22 | 22488.22 | Residential
4149 | R2085 | Jessie's Custom Airbrush | Low Slope Roof Systems | B. Roof Replacement; A. Metal; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-16 | Gonzalo Pena | Jesus Ramos | 1703 N Grant St | Roma | TX | 78584 | 20274.54 | 20274.54 | Residential
7938 | R2655 | VASQUEZ, JOHN Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-09 | Flavio Padron | VASQUEZ, JOHN Residence | 2701 N MCCOLL ROAD, LOT E14 | MCALLEN | TX | 78501 | 3925.32 | 3925.32 | Residential
7978 | R2657 | Luna, Mario Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract; E2. Solar Panel | (08) * Scheduled & Ready to Start | 2021-11-21 | Johnny Garza | Luna, Mario Residence | 11910 Manuel Acosta Drive | El Paso | TX | 79936 | 8625 | 8625 | Residential
7045 | R2558 | Kiscadon, Sharon Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Exterior Work; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-09-10 | Juan Estrada | Kiscadon, Sharon Residence | 27179 White Ranch Rd, | La Feria | TX | 78559 | 10215 | 10215 | Residential
7986 | C2956 | Acura of the Rio Grande Valley | Low Slope Roof Systems | B. Roof Replacement; A. TPO; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-24 | Will Mitchell | Acura of the Rio Grande Valley | 1201 E. EXP 83 | San Juan | TX | 78589 | 77593.82 | 77593.82 | Commercial
2403 | C2370 | USA Fireworks | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-01 | Roel Cantu | USA Fireworks | 6115 State Highway 107 | Mission | TX | 78573 | 10266.43 | 10266.43 | Commercial
6870 | R2516 | Martinez, Tammy Residence | Exterior | Windows | (08) * Scheduled & Ready to Start | 2021-07-20 | Roel Cantu | Martinez, Tammy Residence | 6205 N 32nd St, | McAllen | TX | 78504 | 5998 | 5998 | Residential
521 | C1465 | Interamerican Food Corporation | Low Slope Roof Systems | B. Roof Replacement; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-08-02 | Ed Vazquez | Interamerican Food Corporation | 8419 San Gabriel Dr | laredo | TX | 78045 | 184025 | 184025 | Commercial
6660 | R2532 | Anderson, Patrick Residence | Exterior | Windows | (08) * Scheduled & Ready to Start | 2021-07-27 | Roel Cantu | Anderson, Patrick Residence | 107 E. Resaca Dr. | Los Fresnos | TX | 78566 | 24456 | 24456 | Residential
5124 | C2627 | Esperanza Construction - Casita Lantana | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. New Roof Construction; D. Retail Contract | (09) * Work In Progress | 2021-03-15 | Gary Solis | Casita Lantana | 3954 Dana Ave | Brownsville | TX | 78526 | 293643.28 | 293643.28 | Commercial
6306 | C2747 | Motel 6 Del Rio | Low Slope Roof Systems | B. Roof Replacement; A. Coating Acylic Based; A. Dura-Last; D. Retail Contract | (09) * Work In Progress | 2021-10-08 | Ed Vazquez | Motel 6 Del Rio | 2115 Veterans Blvd | Del Rio | TX | 78840 | 235335.5 | 228241.6 | Commercial
6244 | R2448 | Alleen Koch | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (09) * Work In Progress | 2021-11-05 | Juan Estrada | Alleen Koch Residence | 1910 22nd St | Hondo | TX | 78861 | 0 | 0 | Residential
3430 | R2650 | Escobedo, Lilvia Residence | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (09) * Work In Progress | 2021-11-18 | Flavio Padron | Escobedo, Lilvia Residence | 839 Tierra Encantada Street | Alamo | TX | 78516 | 1500 | 1500 | Residential
7161 | C2874 | 7-11 Store # 42001 | Low Slope Roof Systems | B. New Roof Construction; A. Dura-Last; D. Retail Contract | (09) * Work In Progress | 2021-10-12 | Gary Solis | 7-11 Store # 42001 | redwood & hwy 83 | rio grande | TX | 78582 | 28699.38 | 28699.38 | Commercial
6583 | R2579 | Valdez, Henry Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds; C. Additional Carpentry | (09) * Work In Progress | 2021-10-06 | Juan Estrada | Valdez, Henry Residence | 520 Medford Ave | Brownsville | TX | 78521 | 9079.33 | 9079.33 | Residential
6574 | C2781 | Fort Ringgold | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) * Work In Progress | 2021-09-01 | Gary Solis | Fort Ringgold | 1 s Ringgold st | Rio Grande | TX | 78582 | 92147.81 | 92147.81 | Commercial
6789 | C2876 | Little Folks | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (09) * Work In Progress | 2021-11-01 | Victor Perez | Little Folks | 1233 Paseo Danubio | Laredo | TX | 78046 | 4769.13 | 5364.13 | Commercial
5861 | R2563 | Miltex Properties | Steep Slope Roof Systems | B. Roof Repair | (09) * Work In Progress | 2021-08-16 | Orlando Marquez | Miltex properties | 47 DODGE RD | Boerne | TX | 78006 | 819113.09 | 819113.09 | Residential
1545 | C2767 | Sea Breeze 1 | Low Slope Roof Systems | B. Roof Replacement; A. TPO; D. Retail Contract | (09) * Work In Progress | 2021-11-15 | Gary Solis | Sea Breeze 1 | 4300 Gulf Boulevard | South Padre Island | TX | 78597 | 0 | 0 | Commercial
6441 | C2845 | KEYSTONE APARTMENTS | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) * Work In Progress | 2021-10-11 | Philip Westerman | KEYSTONE APARTMENTS | 1409 W. Business 83 | Westlaco | TX | 78596 | 216243 | 216243 | Residential
1051 | C2674 | Immaculate Conception RGC Main Church Building | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; A. Synthetic Material; D. Retail Contract | (09) * Work In Progress | 2021-10-14 | Philip Westerman | Convent - Immaculate Conception | 101 E 3rd Street | Rio Grande City | TX | 78572 | 67125.76 | 67125.76 | Commercial
7396 | R2598 | ROGERS, CHARLES Residence | Steep Slope Roof Systems | C. Additional Exterior Work; A. Tile (Concrete); B. Roof Repair; D. Retail Contract; C. Additional Carpentry | (09) * Work In Progress | 2021-10-12 | Juan Estrada | ROGERS, CHARLES Residence | 212 E Cowan Terrace, | Brownsville | TX | 78521 | 10650 | 10650 | Residential
6871 | C2853 | Del Rio Board of Realtors | Low Slope Roof Systems | B. Roof Replacement; A. TPO; D. Retail Contract | (09) * Work In Progress | 2021-09-23 | Ed Vazquez | Del Rio Board of Realtors | 127 Foster Dr. | Del Rio | TX | 78840 | 36805 | 36805 | Commercial
7835 | R2638 | Lupita Munoz | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (10) Completed need to inspect ( PM, OC) | 2021-11-23 | Roel Cantu | Munoz, Lupita Residence | 2401 High Ridge Ln. | Edinburg | TX | 78539 | 6565 | 6565 | Residential
8034 | C2959 | Family Dollar 3913 Jaime Zapata | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (10) Completed need to inspect ( PM, OC) | 2021-11-22 | Ed Vazquez | Family Dollar 3913 Jaime Zapata | 3913 TX-20 Loop | Laredo | TX | 78043 | 1200 | 1200 | Commercial
7893 | C2926 | MERX Trade Inc. | Low Slope Roof Systems | A. TPO; B.Roof Repair; D. Retail Contract | (10) Completed need to inspect ( PM, OC) | 2021-11-22 | Ed Vazquez | MERX Trade Inc. | 6547 Star Court | Laredo | TX | 78041 | 1250 | 1250 | Commercial
7495 | C2908 | VINEYARD CHRISTIAN FELLOWSHIP | Low Slope Roof Systems | B. Roof Replacement; A. Metal; A. Coating Acylic Based; D. Retail Contract | (10) Completed need to inspect ( PM, OC) | 2021-11-22 | Roel Cantu | VINEYARD CHRISTIAN FELLOWSHIP | 1200 Mackintosh Dr | BROWNSVILLE | TX | 78521 | 28260 | 28260 | Commercial
3387 | C2875 | Our Lady of Refuge Church CCD Building | Steep Slope Roof Systems | B. Roof Replacement; A. Tile (Clay); C. Additional Exterior Work; D. Retail Contract | (10) Completed need to inspect ( PM, OC) | 2021-11-23 | Juan Estrada | Our Lady of Refuge Church CCD Building | 4 W Eugene De Mazenod Ave | Roma | TX | 78584 | 44462.08 | 44462.08 | Commercial
4440 | R2479 | Rueda, Mario Residence | Low Slope Roof Systems | A. TPO; B.Roof Repair; D. Retail Contract; E. Special Order | (11) Punchout - Corrections | 2021-10-18 | Victor Perez | Rueda, Mario Residence | 1107 Helen Avenue | Mission | TX | 78572 | 1475 | 1475 | Residential
4226 | C2843 | Country Pancake House, Pharr TX | Low Slope Roof Systems | B. Roof Replacement; A. Coating Silicone Based; A. Dura-Last; D. Retail Contract; E. Special Order | (11) Punchout - Corrections | 2021-11-02 | Philip Westerman | Country Pancake House, Pharr TX | 4325 N Cage Blvd | Pharr | TX | 78577 | 24875.85 | 24875.85 | Commercial
7414 | R2599 | Castillo, Candida Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Metal ; D. Retail Contract | (11) Punchout - Corrections | 2021-10-07 | José Rogelio Pina Miranda | Castillo, Candida Residence | 27432 White Ranch Rd | La Feria | TX | 78559 | 9350 | 10225 | Residential
6568 | R2488 | Gomez, Oscar Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (11) Punchout - Corrections | 2021-09-09 | Orlando Marquez | Gomez, Oscar Residence | 102 Odis St | San Antonio | TX | 78211 | 5372.85 | 5372.85 | Residential
5936 | R2403 | Wilke, Scott Residence | Exterior | Windows | (11) Punchout - Corrections | 2021-07-01 | Roel Cantu | Wilke, Scott Residence | 2412 Sterling Avenue | Edinburgh | TX | 78539 | 5085 | 5085 | Residential
7357 | C2860 | Burkett Dentistry | Low Slope Roof Systems | C. Addtional Interior Work; A. Modified; A. Coating Acylic Based; D. Retail Contract | (11) Punchout - Corrections | 2021-11-10 | Philip Westerman | Burkett Dentistry | 1421 N 10th St, | McAllen, | TX | 78501 | 15074.13 | 15074.13 | Commercial
3084 | C2849 | Florence 2- Condo in SPI | Low Slope Roof Systems | B.Roof Repair; A. Dura-Last; D. Retail Contract | (11) Punchout - Corrections | 2021-11-17 | Juan Estrada | Florence 2- Condo in SPI | 5570 Gulf Boulevard | South Padre Island | TX | 78597 | 4139.48 | 4139.48 | Commercial
2718 | R1936 | Norman, Robert Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract; E. Special Order | (11) Punchout - Corrections | 2021-07-22 | Philip Westerman | Norman, Robert Residence | 41344 Schafer Road | Los Fresnos | TX | 78566 | 16176.69 | 16176.69 | Residential
7501 | R2597 | PENA, LAURA Residence | Low Slope Roof Systems | B. Roof Replacement; C. Addtional Exterior Work; A. TPO; D. Retail Contract | (11) Punchout - Corrections | 2021-11-09 | Philip Westerman | PENA, LAURA Residence | 125 OLD ALICE ROAD | BROWNSVILLE | TX | 78552 | 10650 | 10650 | Residential
5787 | R2444 | KRAFT, JACKIE Residence | Exterior | Gutters | (11) Punchout - Corrections | 2021-09-23 | Juan Estrada | KRAFT, JACKIE Residence | 2314 Arthur Ave | Edinburg | TX | 78542 | 7795.26 | 8450.26 | Residential
7283 | R2552 | Lin, Rick Residence | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract | (11) Punchout - Corrections | 2021-10-20 | Joshua Rodriguez | Lin, Rick Residence | 1905 Hidden Pond Dr. | Palmhurst | TX | 78504 | 0 | 0 | Residential
2465 | C2239 | Sunny Produce | Low Slope Roof Systems | A. Metal; B.Roof Repair | (11) Punchout - Corrections | 2021-10-25 | Philip Westerman | Sunny Produce | 6500 S. 23rd. St. Suite 10 | McAllen | TX | 78503 | 2409.75 | 2409.75 | Commercial
7599 | R2648 | Evenson, Patricia Residence | Low Slope Roof Systems | B. Roof Replacement; B. Roof Over Construction; A. TPO; D. Retail Contract | (11) Punchout - Corrections | 2021-11-23 | Juan Estrada | Evenson, Patricia Residence | 7820 N 4th St. | McAllen | TX | 78504 | 11368 | 12618 | Residential
5573 | R2429 | Garza, David Residence | Steep Slope Roof Systems | A. Tile (Concrete); B. Roof Repair; D. Retail Contract; E. Special Order | (11) Punchout - Corrections | 2021-09-21 | Philip Westerman | Garza, David Residence | 3307 Pelican Lake Ave. | Edinburg | TX | 78539 | 3500 | 3500 | Residential
1526 | R1788 | Stillman, Valerie Residence | Low Slope Roof Systems | C. Addtional Exterior Work | (11) Punchout - Corrections | 2021-03-25 | Juan Estrada | Stillman, Valerie Residence | 124 Stillman Rd | Brownsville | TX | 78523 | 69132.49 | 69132.49 | Residential
6633 | R2467 | Forshage, Alta Residence | Low Slope Roof Systems | B. Roof Replacement; A. TPO | (11) Punchout - Corrections | 2021-08-31 | Roel Cantu | Forshage, Alta Residence | 4025 Burns Ct, | McAllen | TX | 78503 | 31500 | 31500 | Residential
5168 | R2280 | Cardenas, Betty Residence | Exterior | Windows | (11) Punchout - Corrections | 2021-03-17 | Roel Cantu | Cardenas, Betty Residence | 15475 E Farm To Market 2812 | Edinburg | TX | 78542 | 7975 | 7975 | Residential
7021 | R2541 | Abrego, Efren Residence | Low Slope Roof Systems | C. Addtional Exterior Work; A. Modified; B.Roof Repair | (11) Punchout - Corrections | 2021-11-02 |  | Abrego, Efren Residence | 5917 N 35th St | McAllen | TX | 78504 | 2450 | 2450 | Residential
7171 | R2633 | Guadalupe Prieto | Exterior | Windows | (11) Punchout - Corrections | 2021-11-19 | Roel Cantu | Guadalupe Prieto | 408 E Emory Ave, | McAllen | TX | 78504 | 6450 | 6450 | Residential
6059 | R2561 | Weber Trusty, Chelsea Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Interior Work; D. Insurance Proceeds | (12) Ready to Invoice (Crystal) | 2021-11-21 | Philip Westerman | Weber Trusty, Chelsea Residence | 1700 Casanova Ave, | Pflugerville, | TX | 78660 | 19964.02 | 19964.02 | Residential
6913 | R2507 | Estrada, Ruth & Uswaldo Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12) Ready to Invoice (Crystal) | 2021-09-07 | Philip Westerman | Estrada, Uswaldo Residence | 1400 Citrine Dr, | Weslaco | TX | 78596 | 8752.59 | 8752.59 | Residential
7397 | R2658 | Garza, Jorge Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12) Ready to Invoice (Crystal) | 2021-11-23 | Victor Perez | Garza, Jorge Residence | 1037 Washington St. | Mission | TX | 78572 | 5605.41 | 5605.41 | Residential
4823 | C2896 | Beacon Roofing Supply West End Garrison Construction | Low Slope Roof Systems | B. Roof Over Construction; A. Coating Silicone Based | (12) Ready to Invoice (Crystal) | 2021-11-23 | Philip Westerman | Beacon Roofing Supply | 1702 S. Expressway 281 | Edinburgh | TX | 78542 | 28074.35 | 28074.35 | Commercial
4676 | C2608 | Doctor's Clinic of Rio Grande City 210 N Britton | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Interior Work; D. Insurance Proceeds | (12) Ready to Invoice (Crystal) | 2021-11-05 |  | 210 N. Britton | 210 N. Britton | Rio Grande City | TX | 78582 | 16313.13 | 16313.13 | Commercial
6386 | R2503 | Edwards, Enedelia Residence | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Insurance Proceeds | (12) Ready to Invoice (Crystal) | 2021-10-19 | Juan Estrada | Edwards, Enedelia Residence | 508 N 13th St | Donna | TX | 78537 | 1598.21 | 1598.21 | Residential
5481 | C2757 | First Presbyterian Church McAllen Big One | Low Slope Roof Systems | C. Addtional Exterior Work; A. TPO; B.Roof Repair; D. Insurance Proceeds; A. Tile | (12) Ready to Invoice (Crystal) | 2021-10-12 | Philip Westerman | First Presbyterian Church | 104 S 12th St, | McAllen | TX | 78501 | 40096.33 | 40096.33 | Commercial
8100 | R2674 | Davis, Neil Residence | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract; E. Special Order | (12) Ready to Invoice (Crystal) | 2021-11-23 | Roel Cantu | Davis, Neil Residence | 416 Wichita | McAllen | TX | 78503 | 850 | 850 | Residential
4172 | R2486 | Garcia, Jessica Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Exterior Work; C. Additional Interior Work; D. Insurance Proceeds; C. Additional Carpentry | (12B) Ready to Invoice Insurance (Crystal) | 2021-11-16 | Juan Estrada | Garcia, Jessica Residence | 907 Cactus Ln | Edinburgh | TX | 78541 | 7508.38 | 7508.38 | Residential
7580 | R2643 | GARZA, MELISSA Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-11-15 | Flavio Padron | GARZA, MELISSA Residence | 733 N. 48TH | MCALLEN | TX | 78501 | 9663.66 | 9857.66 | Residential
6564 | R2504 | Trevino, Jose Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-11-16 | Juan Estrada | Trevino, Jose Residence | 1538 S Virginia Ave, | Mercedes | TX | 78570 | 5294.88 | 5294.88 | Residential
6540 | R2464 | Chavana, Romeo Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Metal ; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-11-15 | Philip Westerman | Chavana, Romeo Residence | 20005 Fallow Ln | Edinburg | TX | 78542 | 6750.94 | 6750.94 | Residential
6058 | R2528 | McNierney, Patrick Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-10-28 | Philip Westerman | McNierney, Patrick Residence | 16701 Dumas St. | patrick.mcnierney@gmail.com | TX | 78660 | 27099.86 | 27099.86 | Residential
6912 | R2544 | Padilla, Juanita Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-10-28 | Juan Estrada | Padilla, Juanita Residence | 2717 madrid ave | Brownsville | TX | 78520 | 8048.93 | 8048.93 | Residential
6740 | R2484 | Reynaldo Cantu | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-11-16 | Juan Estrada | Cantu, Reynaldo Residence | 410 E 8th St | Weslaco | TX | 78596 | 8447.83 | 8447.83 | Residential
4383 | R2349 | Groninger, Monique Residence | Steep Slope Roof Systems | A. Tile (Concrete); B. Roof Repair; D. Insurance Proceeds; E. Special Order | (12B) Ready to Invoice Insurance (Crystal) | 2021-11-01 | Juan Estrada | Groninger, Monique Residential | 23 Ocelot Trail Rd | Laguna Vista | TX | 78578 | 10530.18 | 10530.18 | Residential
6873 | R2534 | Celia Cadena Residential | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-10-28 | Diane Vazquez | Celia Cadena Residential | 2606 Vicente St | Laredo | TX | 78046-6531 | 4066.26 | 4366.26 | Residential
4547 | R2168 | Aurora Luna | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Exterior Work; C. Additional Interior Work; D. Insurance Proceeds | (14) Project on Hold | 2021-02-10 | Noah Sorrell | Aurora Luna Residence | 8179 E State HWY 107 | Edinburg | TX |  | 21136.71 | 18858.18 | Residential
5907 | C2756 | Move it Self Storage - Julian Perez | Low Slope Roof Systems | A. Metal; A. Coating Silicone Based; B.Roof Repair | (14) Project on Hold | 2021-06-23 |  | Move It Storage fredericksburg | 383 FM2093, | Fredericksburg | TX | 78624 | 2814.5 | 2814.5 | Commercial
4861 | R2229 | Perez, Javier Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Metal ; A. Cedar Shake; D. Insurance Proceeds | (14) Project on Hold | 2020-12-19 | Joshua Rodriguez | Perez, Javier Residence | 405 S. Woodland dr. | Pharr | TX | 78577 | 52820.4 | 52820.4 | Residential
5148 | R2345 | Long, Robert Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Tile (Clay); D. Retail Contract | (14) Project on Hold | 2021-06-09 | Orlando Marquez | Long, Robert Residence | 2700 Brazos Ct | McAllen | TX | 78504 | 39500 | 39500 | Residential
2653 | R2324 | Martin, David Residence | Steep Slope Roof Systems | A. Tile (Clay); C. Additional Exterior Work; B. Roof Repair; D. Retail Contract; C. Additional Carpentry | (14) Project on Hold | 2021-05-26 | Juan Estrada | Martin, David Residence | 4140 Las Floresta Avenue | Mercedes | TX | 78570 | 26563 | 26563 | Residential
2535 | R2330 | Garza, Roberta & Edgar Residence | Steep Slope Roof Systems | A. Tile (Concrete); B. Roof Repair; D. Retail Contract; E. Special Order | (14) Project on Hold | 2021-07-09 | Philip Westerman | Garza, Roberta Residence | 2601 Santa Ana | Mission | TX | 78572 | 18812.48 | 18812.48 | Residential
6204 | R2471 | Velez, Lesly & Frank | Exterior | Gutters | (14) Project on Hold | 2021-07-22 | Philip Westerman | Velez, Lesly Residence | 3501 Oak Ridge Ln. gate code: #5735 | Mission | TX | 78573 | 100 | 100 | Residential
5791 | R2375 | LUDWIG, DEREK Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (15) Archive | 2021-05-25 | Tim Parrish | LUDWIG, DEREK Residence | 8506 COLCHESTER | San Antonio | TX | 78254 | 8480 | 8480 | Residential

## Low Slope
PROJECT ID | NUMBER ALT | PROJECT NAME | TYPE | SUBTYPE | PRODUCTION STATUS | PRODUCTION STATUS DATE | SALES PERSON NAME | BUILDING NAME | BUILDING ADDRESS | BUILDING CITY | BUILDING STATE | BUILDING ZIP | ORIGINAL CONTRACT AMOUNT | REVISED CONTRACT AMOUNT | DIVISION
7956 | R2662 | BOCANEGRA, LINDA Residence | Low Slope Roof Systems | C. Addtional Interior Work; C. Addtional Exterior Work; B.Roof Repair; D. Retail Contract; A. Tile | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-12 | Roel Cantu | BOCANEGRA, LINDA Residence | 729 KIKA DE LA GARZA BLVD | LA JOYA | TX | 78560 | 10540 | 10540 | Residential
7931 | C2932 | GoodWill Flashing | Low Slope Roof Systems | A. TPO; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-10-29 | Will Mitchell | Goodwill Dixieland | 702 Dixieland rd | Harlingen | TX | 78550 | 1829.17 | 1829.17 | Commercial
7870 | C2933 | Gonzalez Auto Parts #1 4220 San Bernardo | Low Slope Roof Systems | A. Metal; B.Roof Repair | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-01 | Philip Westerman | Gonzalez Auto Parts | 4220 San Bernardo Ave | LAREDO | TX | 78041 | 3445.25 | 3445.25 | Commercial
7537 | C2912 | Alfredo Casso & Co Inc | Low Slope Roof Systems | A. Coating Acylic Based; A. Coating Silicone Based; B.Roof Repair; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-10-18 | Ed Vazquez | Alfredo Casso & Co Inc | 14101 Transportation Ave | Laredo | TX | 78041 | 9730.59 | 9730.59 | Commercial
7461 | C2955 | TITLEMAX LAREDO (by Gonzalez Auto Parts) | Low Slope Roof Systems | B. Roof Over Construction; A. Modified; D. Insurance Proceeds; E. Special Order | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-23 | Philip Westerman | TITLEMAX LAREDO | 4316 SAN BERNARDO AVE | LAREDO | TX | 78041 | 51183.87 | 51183.87 | Commercial
7425 | C2936 | Gonzalez Auto Parts- #9 Laredo | Low Slope Roof Systems | B. Roof Replacement; B. Roof Over Construction; A. Metal; A. Modified; A. Coating Silicone Based; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-04 | Philip Westerman | Gonzalez Auto Parts | 3518 Culebra Rd | San Antonio | TX | 78228 | 42695.33 | 42695.33 | Commercial
5871 | C2919 | Move it Storage Austin | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-10-13 | Philip Westerman | Move it Storage Austin | 9311 N FM 620, | Austin | TX | 78726 | 3231.42 | 3231.42 | Commercial
2703 | C2934 | Gonzalez Auto Parts- San Antonio #11 Culebra | Low Slope Roof Systems | B. Roof Over Construction; A. EPDM; A. Coating Acylic Based; D. Insurance Proceeds; E. Special Order | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-08 | Philip Westerman | Gonzalez Auto Parts | 3518 Culebra Rd | San Antonio | TX | 78228 | 0 | 0 | Commercial
2702 | C2937 | Gonzalez Auto Parts- San Antonio #8- Rigsby | Low Slope Roof Systems | B. Roof Over Construction; A. Modified; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-01 | Philip Westerman | Gonzalez Auto Parts | 3518 Culebra Rd | San Antonio | TX | 78228 | 45203.43 | 45203.43 | Commercial
2700 | C2935 | Gonzalez Auto Parts- Pleasanton #17 | Low Slope Roof Systems | A. Coating Acylic Based; B.Roof Repair; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-01 | Philip Westerman | Gonzalez Auto Parts | 3518 Culebra Rd | San Antonio | TX | 78228 | 7193.56 | 7193.56 | Commercial
7972 | C2941 | DOLLAR GENERAL | Low Slope Roof Systems | C. Addtional Exterior Work; A. Metal; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-19 | Juan Estrada | DOLLAR GENERAL | 1300 W Ruben M Torres Blvd | BROWNSVILLE | TX | 78520 | 3117.6 | 3117.6 | Commercial
7804 | R2646 | ROHR, AL Residence | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-11-05 | Juan Estrada | ROHR, AL Residence | 1510 E BUS HWY 83, LEMON TREE ESTATES UNIT C5 | MISSION | TX | 78572 | 2100 | 2100 | Residential
7784 | C2917 | T-Mobile Mobile Skylights | Low Slope Roof Systems | A. BUR; B.Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-10-12 | Will Mitchell | T-Mobile | 3711 San Gabriel | Mission | TX | 78572 | 9394.47 | 9394.47 | Commercial
6599 | C2817 | Mission Consolidated Independent School District | Low Slope Roof Systems | A. Modified; B.Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-08-26 | Gary Solis | Mission Consolidated Independent School District | 1201 bryce | mission | TX | 78572 | 57145.18 | 57145.18 | Commercial
6224 | C2694 | Sea Vista Condominiums I | Low Slope Roof Systems | B. Roof Over Construction; A. Coating Silicone Based; D. Retail Contract; E. Special Order | (05) Order and Schedule Material | 2021-11-10 | Philip Westerman | Sea Vista Condominiums | 110 Padre Blvd, | South Padre Island | TX | 78597 | 70699.25 | 70699.25 | Commercial
5644 | C2695 | Sea Vista Condominiums II | Low Slope Roof Systems | B. Roof Over Construction; A. Coating Silicone Based; D. Retail Contract; E. Special Order | (05) Order and Schedule Material | 2021-11-10 | Philip Westerman | Sea Vista Condominiums | 110 Padre Blvd, | South Padre Island | TX | 78597 | 82855.36 | 82855.36 | Commercial
7437 | C2764 | RandR Ventures LLc Casa Padre | Low Slope Roof Systems | B. Roof Replacement; A. Coating Acylic Based; D. Retail Contract | (06) Schedule Labor | 2021-11-16 | Alfredo Villalobos | Casa Padre | 7480 Padre Island Hwy | Brownsville | TX | 78521 | 56895.12 | 56895.12 | Commercial
7327 | C2833 | 7-Eleven # 41871 | Low Slope Roof Systems | B. Roof Replacement; A. PVC; D. Retail Contract | (06) Schedule Labor | 2021-11-05 | Gary Solis | 7-Eleven # 41871 | 1327 E. Interstate 2 | Mission | TX | 78572 | 37616.88 | 37616.88 | Commercial
7892 | R2644 | Mario Rueda | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract; E. Special Order | (06) Schedule Labor | 2021-11-05 | Victor Perez | Rueda, Mario Residence | 1107 Helen Avenue | Mission | TX | 78572 | 1015 | 1015 | Residential
7589 | C2923 | LA PALABRA VIVIENTES MINISTRY | Low Slope Roof Systems | C. Addtional Exterior Work; A. Metal; A. Coating Acylic Based; B.Roof Repair; D. Retail Contract | (06) Schedule Labor | 2021-11-02 | Juan Estrada | LA PALABRA VIVIENTES MINISTRY | 171 DEANNA DR | SAN JUAN | TX | 78589 | 0 | 0 | Commercial
7086 | C2891 | Utility Trailer Sales South East Texas | Low Slope Roof Systems | A. Metal; A. TPO; B.Roof Repair; D. Retail Contract | (06) Schedule Labor | 2021-11-10 | Victor Perez | Utility Trailer Sales South East Texas | 4320 Trade Center | Laredo | TX | 78041 | 10294.71 | 10294.71 | Commercial
7371 | C2846 | Atlas Restoration / Goodwill Store | Low Slope Roof Systems | A. TPO; B.Roof Repair; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-09-10 | Will Mitchell | Goodwill Store | 702 Dixieland Road | Harlingen | TX | 78552 | 3400 | 5100 | Commercial
6088 | C2691 | Los Compadres | Low Slope Roof Systems | B. Roof Over Construction; A. Dura-Last; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-08-26 | Will Mitchell | Los Compadres | 1012 S Closner Blvd | Edinburg | TX | 78542 | 15958.83 | 15958.83 | Commercial
7732 | C2914 | MCALLEN BIS ASSOCIATES | Low Slope Roof Systems | B. Roof Replacement; A. Metal; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-16 | Gary Solis | FD McAllen | 5901 S International Pkwy | McAllen | TX | 78503 | 1450 | 1450 | Commercial
7659 | R2659 | FRED GOMEZ: LA FERIA | Low Slope Roof Systems | B. Roof Replacement; A. TPO; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-17 | Roel Cantu | FRED GOMEZ: LA FERIA | 103 S MAIN ST | LA FERIA | TX | 78559 | 28000 | 28000 | Commercial
4149 | R2085 | Jessie's Custom Airbrush | Low Slope Roof Systems | B. Roof Replacement; A. Metal; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-16 | Gonzalo Pena | Jesus Ramos | 1703 N Grant St | Roma | TX | 78584 | 20274.54 | 20274.54 | Residential
7986 | C2956 | Acura of the Rio Grande Valley | Low Slope Roof Systems | B. Roof Replacement; A. TPO; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-24 | Will Mitchell | Acura of the Rio Grande Valley | 1201 E. EXP 83 | San Juan | TX | 78589 | 77593.82 | 77593.82 | Commercial
2403 | C2370 | USA Fireworks | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-01 | Roel Cantu | USA Fireworks | 6115 State Highway 107 | Mission | TX | 78573 | 10266.43 | 10266.43 | Commercial
521 | C1465 | Interamerican Food Corporation | Low Slope Roof Systems | B. Roof Replacement; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-08-02 | Ed Vazquez | Interamerican Food Corporation | 8419 San Gabriel Dr | laredo | TX | 78045 | 184025 | 184025 | Commercial
6306 | C2747 | Motel 6 Del Rio | Low Slope Roof Systems | B. Roof Replacement; A. Coating Acylic Based; A. Dura-Last; D. Retail Contract | (09) * Work In Progress | 2021-10-08 | Ed Vazquez | Motel 6 Del Rio | 2115 Veterans Blvd | Del Rio | TX | 78840 | 235335.5 | 228241.6 | Commercial
7161 | C2874 | 7-11 Store # 42001 | Low Slope Roof Systems | B. New Roof Construction; A. Dura-Last; D. Retail Contract | (09) * Work In Progress | 2021-10-12 | Gary Solis | 7-11 Store # 42001 | redwood & hwy 83 | rio grande | TX | 78582 | 28699.38 | 28699.38 | Commercial
6789 | C2876 | Little Folks | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (09) * Work In Progress | 2021-11-01 | Victor Perez | Little Folks | 1233 Paseo Danubio | Laredo | TX | 78046 | 4769.13 | 5364.13 | Commercial
1545 | C2767 | Sea Breeze 1 | Low Slope Roof Systems | B. Roof Replacement; A. TPO; D. Retail Contract | (09) * Work In Progress | 2021-11-15 | Gary Solis | Sea Breeze 1 | 4300 Gulf Boulevard | South Padre Island | TX | 78597 | 0 | 0 | Commercial
6871 | C2853 | Del Rio Board of Realtors | Low Slope Roof Systems | B. Roof Replacement; A. TPO; D. Retail Contract | (09) * Work In Progress | 2021-09-23 | Ed Vazquez | Del Rio Board of Realtors | 127 Foster Dr. | Del Rio | TX | 78840 | 36805 | 36805 | Commercial
8034 | C2959 | Family Dollar 3913 Jaime Zapata | Low Slope Roof Systems | A. Metal; B.Roof Repair; D. Retail Contract | (10) Completed need to inspect ( PM, OC) | 2021-11-22 | Ed Vazquez | Family Dollar 3913 Jaime Zapata | 3913 TX-20 Loop | Laredo | TX | 78043 | 1200 | 1200 | Commercial
7893 | C2926 | MERX Trade Inc. | Low Slope Roof Systems | A. TPO; B.Roof Repair; D. Retail Contract | (10) Completed need to inspect ( PM, OC) | 2021-11-22 | Ed Vazquez | MERX Trade Inc. | 6547 Star Court | Laredo | TX | 78041 | 1250 | 1250 | Commercial
7495 | C2908 | VINEYARD CHRISTIAN FELLOWSHIP | Low Slope Roof Systems | B. Roof Replacement; A. Metal; A. Coating Acylic Based; D. Retail Contract | (10) Completed need to inspect ( PM, OC) | 2021-11-22 | Roel Cantu | VINEYARD CHRISTIAN FELLOWSHIP | 1200 Mackintosh Dr | BROWNSVILLE | TX | 78521 | 28260 | 28260 | Commercial
4440 | R2479 | Rueda, Mario Residence | Low Slope Roof Systems | A. TPO; B.Roof Repair; D. Retail Contract; E. Special Order | (11) Punchout - Corrections | 2021-10-18 | Victor Perez | Rueda, Mario Residence | 1107 Helen Avenue | Mission | TX | 78572 | 1475 | 1475 | Residential
4226 | C2843 | Country Pancake House, Pharr TX | Low Slope Roof Systems | B. Roof Replacement; A. Coating Silicone Based; A. Dura-Last; D. Retail Contract; E. Special Order | (11) Punchout - Corrections | 2021-11-02 | Philip Westerman | Country Pancake House, Pharr TX | 4325 N Cage Blvd | Pharr | TX | 78577 | 24875.85 | 24875.85 | Commercial
7357 | C2860 | Burkett Dentistry | Low Slope Roof Systems | C. Addtional Interior Work; A. Modified; A. Coating Acylic Based; D. Retail Contract | (11) Punchout - Corrections | 2021-11-10 | Philip Westerman | Burkett Dentistry | 1421 N 10th St, | McAllen, | TX | 78501 | 15074.13 | 15074.13 | Commercial
3084 | C2849 | Florence 2- Condo in SPI | Low Slope Roof Systems | B.Roof Repair; A. Dura-Last; D. Retail Contract | (11) Punchout - Corrections | 2021-11-17 | Juan Estrada | Florence 2- Condo in SPI | 5570 Gulf Boulevard | South Padre Island | TX | 78597 | 4139.48 | 4139.48 | Commercial
7501 | R2597 | PENA, LAURA Residence | Low Slope Roof Systems | B. Roof Replacement; C. Addtional Exterior Work; A. TPO; D. Retail Contract | (11) Punchout - Corrections | 2021-11-09 | Philip Westerman | PENA, LAURA Residence | 125 OLD ALICE ROAD | BROWNSVILLE | TX | 78552 | 10650 | 10650 | Residential
2465 | C2239 | Sunny Produce | Low Slope Roof Systems | A. Metal; B.Roof Repair | (11) Punchout - Corrections | 2021-10-25 | Philip Westerman | Sunny Produce | 6500 S. 23rd. St. Suite 10 | McAllen | TX | 78503 | 2409.75 | 2409.75 | Commercial
7599 | R2648 | Evenson, Patricia Residence | Low Slope Roof Systems | B. Roof Replacement; B. Roof Over Construction; A. TPO; D. Retail Contract | (11) Punchout - Corrections | 2021-11-23 | Juan Estrada | Evenson, Patricia Residence | 7820 N 4th St. | McAllen | TX | 78504 | 11368 | 12618 | Residential
1526 | R1788 | Stillman, Valerie Residence | Low Slope Roof Systems | C. Addtional Exterior Work | (11) Punchout - Corrections | 2021-03-25 | Juan Estrada | Stillman, Valerie Residence | 124 Stillman Rd | Brownsville | TX | 78523 | 69132.49 | 69132.49 | Residential
6633 | R2467 | Forshage, Alta Residence | Low Slope Roof Systems | B. Roof Replacement; A. TPO | (11) Punchout - Corrections | 2021-08-31 | Roel Cantu | Forshage, Alta Residence | 4025 Burns Ct, | McAllen | TX | 78503 | 31500 | 31500 | Residential
7021 | R2541 | Abrego, Efren Residence | Low Slope Roof Systems | C. Addtional Exterior Work; A. Modified; B.Roof Repair | (11) Punchout - Corrections | 2021-11-02 |  | Abrego, Efren Residence | 5917 N 35th St | McAllen | TX | 78504 | 2450 | 2450 | Residential
4823 | C2896 | Beacon Roofing Supply West End Garrison Construction | Low Slope Roof Systems | B. Roof Over Construction; A. Coating Silicone Based | (12) Ready to Invoice (Crystal) | 2021-11-23 | Philip Westerman | Beacon Roofing Supply | 1702 S. Expressway 281 | Edinburgh | TX | 78542 | 28074.35 | 28074.35 | Commercial
5481 | C2757 | First Presbyterian Church McAllen Big One | Low Slope Roof Systems | C. Addtional Exterior Work; A. TPO; B.Roof Repair; D. Insurance Proceeds; A. Tile | (12) Ready to Invoice (Crystal) | 2021-10-12 | Philip Westerman | First Presbyterian Church | 104 S 12th St, | McAllen | TX | 78501 | 40096.33 | 40096.33 | Commercial
5907 | C2756 | Move it Self Storage - Julian Perez | Low Slope Roof Systems | A. Metal; A. Coating Silicone Based; B.Roof Repair | (14) Project on Hold | 2021-06-23 |  | Move It Storage fredericksburg | 383 FM2093, | Fredericksburg | TX | 78624 | 2814.5 | 2814.5 | Commercial

## Steep Slope
PROJECT ID | NUMBER ALT | PROJECT NAME | TYPE | SUBTYPE | PRODUCTION STATUS | PRODUCTION STATUS DATE | SALES PERSON NAME | BUILDING NAME | BUILDING ADDRESS | BUILDING CITY | BUILDING STATE | BUILDING ZIP | ORIGINAL CONTRACT AMOUNT | REVISED CONTRACT AMOUNT | DIVISION
7498 | R2676 | MUNOZ, CIRIA Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; A. Metal ; B. Roof Repair; D. Insurance Proceeds | (01) Validate Info - (Leila) | 2021-11-23 | Flavio Padron | MUNOZ, CIRIA Residence | 803 S. STANDARD AVE | SAN JUAN | TX | 78589 | 3916.15 | 3916.15 | Residential
7107 | R2677 | Ornelas, Miguel Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (01) Validate Info - (Leila) | 2021-11-23 | Roel Cantu | Ornelas, Miguel Residence | 2432 Quince Ave, | McAllen | TX | 78501 | 5250 | 5250 | Residential
1146 | R2669 | Freed, R Residence | Steep Slope Roof Systems | A. Tile (Concrete); B. Roof Repair; D. Retail Contract | (02) Create Material List (Gary) | 2021-11-24 | Ed Vazquez | Freed, R Residence | 7202 Lake Victoria | Laredo | TX | 78041 | 0 | 0 | Residential
7918 | R2661 | GARZA, OLGA Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-10 | Victor Perez | GARZA, OLGA Residence | 118 PARK LANE WEST | HARLINGEN | TX | 78552 | 7581.67 | 8506.67 | Residential
7911 | R2664 | Martin, Matthew Residence | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-11 | Orlando Marquez | Martin, Matthew Residence | 14003 Red Maple Wood | SAN ANTONIO | TX | 78249 | 3289.45 | 3289.45 | Residential
7640 | C2907 | Lazy A Ranch Beeville: SKIDMORE | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-10-28 | Philip Westerman | Lazy A Ranch Beeville: SKIDMORE | 2785 GUAJOLOTE ROAD | SKIDMORE | TX | 78389 | 6307.86 | 6307.86 | Commercial
8033 | C2958 | O'Hanlon Law Firm 2 | Steep Slope Roof Systems | A. Metal ; B. Roof Repair; D. Retail Contract | (04) Pre-Construction Meeting (PM,IS,OS) Call | 2021-11-18 | Will Mitchell | O'Hanlon Law Firm | 426 West Caffery Ave. | Pharr | TX | 78577 | 5119.6 | 5119.6 | Commercial
7790 | C2927 | SILVER SANDS RENTALS (2727 11th St. U.24) | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract; E. Special Order | (05) Order and Schedule Material | 2021-11-12 | Philip Westerman | SILVER SANDS VACATION RENTALS | 732 SAND CASTLE DRIVE, UNIT 3 | PORT ARANSAS | TX | 78373 | 1577.48 | 1577.48 | Commercial
7759 | C2920 | SILVER SANDS RENTALS (732 Sand Castle Dr) | Steep Slope Roof Systems | B. Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-11-12 | Philip Westerman | SILVER SANDS VACATION RENTALS | 732 SAND CASTLE DRIVE, UNIT 3 | PORT ARANSAS | TX | 78373 | 1631.6 | 1631.6 | Commercial
6340 | R2660 | Conner, David Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Tile (Concrete); D. Insurance Proceeds | (05) Order and Schedule Material | 2021-11-15 | Victor Perez | Conner, David Residence | 1318 Tierra Santa St | Weslaco | TX | 78596 | 59393 | 59393 | Residential
7880 | R2665 | Flores, Molleigh Residence | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-11-17 | Victor Perez | Flores, Molleigh Residence | 84 Sunrise Rd | RIO GRANDE CITY | TX | 78582 | 1799.67 | 1799.67 | Residential
7992 | R2663 | PALMA, MARISSA Residence | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-11-17 | Victor Perez | PALMA, MARISSA Residence | 819 W COSTA RICA AVE | PHARR | TX | 78577 | 1799.67 | 1799.67 | Residential
7862 | R2651 | ARAFAT, NANCY Residence | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract | (05) Order and Schedule Material | 2021-11-16 | Roel Cantu | ARAFAT, NANCY Residence | 3908 SUNDOWN DRIVE | MCALLEN | TX | 78503 | 11200 | 11200 | Residential
7644 | R2619 | Eric Piater | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract | (06) Schedule Labor | 2021-10-12 | Victor Perez | Piater, Eric Residence | 1310 Tierra Encantada, Weslaco, TX 78596 | Weslaco | TX | 78596 | 1350 | 1350 | Residential
7779 | R2641 | Polley, Eric Residence 1631 | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (06) Schedule Labor | 2021-11-18 | Will Mitchell | Polley, Eric Residence | 1631 Throckmorton | Harlingen | TX | 78550 | 9456.25 | 13436.25 | Residential
3290 | R2505 | Rivera, Mario Residence | Steep Slope Roof Systems | A. Metal ; B. Roof Repair; D. Insurance Proceeds; E. Special Order | (06) Schedule Labor | 2021-10-27 | Juan Estrada | Rivera, Mario Residence | 3701 W Hobbs Dr | Edinburg | TX | 78539 | 70387.65 | 70387.65 | Residential
7158 | R2592 | John Harper | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract | (06) Schedule Labor | 2021-10-12 | Orlando Marquez | HARPER, JOHN Residence | 19910 Encino Ridge St, | San Antonio | TX | 78259 | 2116.8 | 2116.8 | Residential
6935 | R2567 | Jester, William Residence | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (06) Schedule Labor | 2021-08-17 | Orlando Marquez | Jester, William Residence | 4910 Haven Oak, | San Antonio | TX | 78249 | 2972.59 | 2972.59 | Residential
37 | C1324 | San Pedro Apartments | Steep Slope Roof Systems | B. Roof Replacement; A. Metal | (06) Schedule Labor | 2021-10-01 | Philip Westerman | Bldg 15 San Pedro Apartments | 4206 San Gabriel, Bldg 15 | Mission | TX | 78572 | 504925.74 | 514275.95 | Commercial
7997 | C2953 | Jehovah Witness Alton | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-21 | Gary Solis | Jehovah Witness Alton | 2613 W Main Ave | Alton | TX | 78573 | 37290 | 37290 | Commercial
6454 | R2574 | Salinas, Dana Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-01 | Victor Perez | Salinas, Dana Residence | 13502 23rd Lane | Ediburg | TX | 78541 | 16875.67 | 16875.67 | Residential
7826 | R2637 | Garza, Diane Residence | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair | (08) * Scheduled & Ready to Start | 2021-11-15 | Roel Cantu | Garza, Diane Residence | 815 Avenida Escandon | Rancho Viejo | TX | 78575 | 17128 | 17128 | Residential
7534 | R2636 | Jeremias Tezcucano 2018 E. 21st St. | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-09 | Philip Westerman | Tezcucano, Jerimias Residence | 2018 E. 21ST ST | MISSION | TX | 78574 | 3454.19 | 3454.19 | Residential
5215 | C2693 | Rodd Field Congregation of Jehovah's Witness | Steep Slope Roof Systems | B. Roof Replacement; A. Metal ; C. Additional Exterior Work; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-08 | Gary Solis | Rodd Field Congregation of Jehovah's Witness | 2753 Rodd Field Road | Corpus Christi | TX | 78414 | 52500 | 52500 | Commercial
4958 | R2383 | Revisore, Sharon Interior and Garage | Steep Slope Roof Systems | C. Additional Interior Work; D. Retail Contract; C. Additional Carpentry | (08) * Scheduled & Ready to Start | 2021-11-16 | Philip Westerman |  | 3954 Dana Ave | Brownsville | TX | 78526 | 22488.22 | 22488.22 | Residential
7938 | R2655 | VASQUEZ, JOHN Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-11-09 | Flavio Padron | VASQUEZ, JOHN Residence | 2701 N MCCOLL ROAD, LOT E14 | MCALLEN | TX | 78501 | 3925.32 | 3925.32 | Residential
7978 | R2657 | Luna, Mario Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract; E2. Solar Panel | (08) * Scheduled & Ready to Start | 2021-11-21 | Johnny Garza | Luna, Mario Residence | 11910 Manuel Acosta Drive | El Paso | TX | 79936 | 8625 | 8625 | Residential
7045 | R2558 | Kiscadon, Sharon Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Exterior Work; D. Retail Contract | (08) * Scheduled & Ready to Start | 2021-09-10 | Juan Estrada | Kiscadon, Sharon Residence | 27179 White Ranch Rd, | La Feria | TX | 78559 | 10215 | 10215 | Residential
5124 | C2627 | Esperanza Construction - Casita Lantana | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. New Roof Construction; D. Retail Contract | (09) * Work In Progress | 2021-03-15 | Gary Solis | Casita Lantana | 3954 Dana Ave | Brownsville | TX | 78526 | 293643.28 | 293643.28 | Commercial
6244 | R2448 | Alleen Koch | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (09) * Work In Progress | 2021-11-05 | Juan Estrada | Alleen Koch Residence | 1910 22nd St | Hondo | TX | 78861 | 0 | 0 | Residential
3430 | R2650 | Escobedo, Lilvia Residence | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Retail Contract | (09) * Work In Progress | 2021-11-18 | Flavio Padron | Escobedo, Lilvia Residence | 839 Tierra Encantada Street | Alamo | TX | 78516 | 1500 | 1500 | Residential
6583 | R2579 | Valdez, Henry Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds; C. Additional Carpentry | (09) * Work In Progress | 2021-10-06 | Juan Estrada | Valdez, Henry Residence | 520 Medford Ave | Brownsville | TX | 78521 | 9079.33 | 9079.33 | Residential
6574 | C2781 | Fort Ringgold | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) * Work In Progress | 2021-09-01 | Gary Solis | Fort Ringgold | 1 s Ringgold st | Rio Grande | TX | 78582 | 92147.81 | 92147.81 | Commercial
5861 | R2563 | Miltex Properties | Steep Slope Roof Systems | B. Roof Repair | (09) * Work In Progress | 2021-08-16 | Orlando Marquez | Miltex properties | 47 DODGE RD | Boerne | TX | 78006 | 819113.09 | 819113.09 | Residential
6441 | C2845 | KEYSTONE APARTMENTS | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (09) * Work In Progress | 2021-10-11 | Philip Westerman | KEYSTONE APARTMENTS | 1409 W. Business 83 | Westlaco | TX | 78596 | 216243 | 216243 | Residential
1051 | C2674 | Immaculate Conception RGC Main Church Building | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; A. Synthetic Material; D. Retail Contract | (09) * Work In Progress | 2021-10-14 | Philip Westerman | Convent - Immaculate Conception | 101 E 3rd Street | Rio Grande City | TX | 78572 | 67125.76 | 67125.76 | Commercial
7396 | R2598 | ROGERS, CHARLES Residence | Steep Slope Roof Systems | C. Additional Exterior Work; A. Tile (Concrete); B. Roof Repair; D. Retail Contract; C. Additional Carpentry | (09) * Work In Progress | 2021-10-12 | Juan Estrada | ROGERS, CHARLES Residence | 212 E Cowan Terrace, | Brownsville | TX | 78521 | 10650 | 10650 | Residential
7835 | R2638 | Lupita Munoz | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (10) Completed need to inspect ( PM, OC) | 2021-11-23 | Roel Cantu | Munoz, Lupita Residence | 2401 High Ridge Ln. | Edinburg | TX | 78539 | 6565 | 6565 | Residential
3387 | C2875 | Our Lady of Refuge Church CCD Building | Steep Slope Roof Systems | B. Roof Replacement; A. Tile (Clay); C. Additional Exterior Work; D. Retail Contract | (10) Completed need to inspect ( PM, OC) | 2021-11-23 | Juan Estrada | Our Lady of Refuge Church CCD Building | 4 W Eugene De Mazenod Ave | Roma | TX | 78584 | 44462.08 | 44462.08 | Commercial
7414 | R2599 | Castillo, Candida Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Metal ; D. Retail Contract | (11) Punchout - Corrections | 2021-10-07 | José Rogelio Pina Miranda | Castillo, Candida Residence | 27432 White Ranch Rd | La Feria | TX | 78559 | 9350 | 10225 | Residential
6568 | R2488 | Gomez, Oscar Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (11) Punchout - Corrections | 2021-09-09 | Orlando Marquez | Gomez, Oscar Residence | 102 Odis St | San Antonio | TX | 78211 | 5372.85 | 5372.85 | Residential
2718 | R1936 | Norman, Robert Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract; E. Special Order | (11) Punchout - Corrections | 2021-07-22 | Philip Westerman | Norman, Robert Residence | 41344 Schafer Road | Los Fresnos | TX | 78566 | 16176.69 | 16176.69 | Residential
7283 | R2552 | Lin, Rick Residence | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract | (11) Punchout - Corrections | 2021-10-20 | Joshua Rodriguez | Lin, Rick Residence | 1905 Hidden Pond Dr. | Palmhurst | TX | 78504 | 0 | 0 | Residential
5573 | R2429 | Garza, David Residence | Steep Slope Roof Systems | A. Tile (Concrete); B. Roof Repair; D. Retail Contract; E. Special Order | (11) Punchout - Corrections | 2021-09-21 | Philip Westerman | Garza, David Residence | 3307 Pelican Lake Ave. | Edinburg | TX | 78539 | 3500 | 3500 | Residential
6059 | R2561 | Weber Trusty, Chelsea Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Interior Work; D. Insurance Proceeds | (12) Ready to Invoice (Crystal) | 2021-11-21 | Philip Westerman | Weber Trusty, Chelsea Residence | 1700 Casanova Ave, | Pflugerville, | TX | 78660 | 19964.02 | 19964.02 | Residential
6913 | R2507 | Estrada, Ruth & Uswaldo Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12) Ready to Invoice (Crystal) | 2021-09-07 | Philip Westerman | Estrada, Uswaldo Residence | 1400 Citrine Dr, | Weslaco | TX | 78596 | 8752.59 | 8752.59 | Residential
7397 | R2658 | Garza, Jorge Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12) Ready to Invoice (Crystal) | 2021-11-23 | Victor Perez | Garza, Jorge Residence | 1037 Washington St. | Mission | TX | 78572 | 5605.41 | 5605.41 | Residential
4676 | C2608 | Doctor's Clinic of Rio Grande City 210 N Britton | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Interior Work; D. Insurance Proceeds | (12) Ready to Invoice (Crystal) | 2021-11-05 |  | 210 N. Britton | 210 N. Britton | Rio Grande City | TX | 78582 | 16313.13 | 16313.13 | Commercial
6386 | R2503 | Edwards, Enedelia Residence | Steep Slope Roof Systems | A. Asphalt Compostion Shingle; B. Roof Repair; D. Insurance Proceeds | (12) Ready to Invoice (Crystal) | 2021-10-19 | Juan Estrada | Edwards, Enedelia Residence | 508 N 13th St | Donna | TX | 78537 | 1598.21 | 1598.21 | Residential
8100 | R2674 | Davis, Neil Residence | Steep Slope Roof Systems | A. Tile (Clay); B. Roof Repair; D. Retail Contract; E. Special Order | (12) Ready to Invoice (Crystal) | 2021-11-23 | Roel Cantu | Davis, Neil Residence | 416 Wichita | McAllen | TX | 78503 | 850 | 850 | Residential
4172 | R2486 | Garcia, Jessica Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Exterior Work; C. Additional Interior Work; D. Insurance Proceeds; C. Additional Carpentry | (12B) Ready to Invoice Insurance (Crystal) | 2021-11-16 | Juan Estrada | Garcia, Jessica Residence | 907 Cactus Ln | Edinburgh | TX | 78541 | 7508.38 | 7508.38 | Residential
7580 | R2643 | GARZA, MELISSA Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-11-15 | Flavio Padron | GARZA, MELISSA Residence | 733 N. 48TH | MCALLEN | TX | 78501 | 9663.66 | 9857.66 | Residential
6564 | R2504 | Trevino, Jose Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-11-16 | Juan Estrada | Trevino, Jose Residence | 1538 S Virginia Ave, | Mercedes | TX | 78570 | 5294.88 | 5294.88 | Residential
6540 | R2464 | Chavana, Romeo Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Metal ; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-11-15 | Philip Westerman | Chavana, Romeo Residence | 20005 Fallow Ln | Edinburg | TX | 78542 | 6750.94 | 6750.94 | Residential
6058 | R2528 | McNierney, Patrick Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-10-28 | Philip Westerman | McNierney, Patrick Residence | 16701 Dumas St. | patrick.mcnierney@gmail.com | TX | 78660 | 27099.86 | 27099.86 | Residential
6912 | R2544 | Padilla, Juanita Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-10-28 | Juan Estrada | Padilla, Juanita Residence | 2717 madrid ave | Brownsville | TX | 78520 | 8048.93 | 8048.93 | Residential
6740 | R2484 | Reynaldo Cantu | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-11-16 | Juan Estrada | Cantu, Reynaldo Residence | 410 E 8th St | Weslaco | TX | 78596 | 8447.83 | 8447.83 | Residential
4383 | R2349 | Groninger, Monique Residence | Steep Slope Roof Systems | A. Tile (Concrete); B. Roof Repair; D. Insurance Proceeds; E. Special Order | (12B) Ready to Invoice Insurance (Crystal) | 2021-11-01 | Juan Estrada | Groninger, Monique Residential | 23 Ocelot Trail Rd | Laguna Vista | TX | 78578 | 10530.18 | 10530.18 | Residential
6873 | R2534 | Celia Cadena Residential | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Insurance Proceeds | (12B) Ready to Invoice Insurance (Crystal) | 2021-10-28 | Diane Vazquez | Celia Cadena Residential | 2606 Vicente St | Laredo | TX | 78046-6531 | 4066.26 | 4366.26 | Residential
4547 | R2168 | Aurora Luna | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; C. Additional Exterior Work; C. Additional Interior Work; D. Insurance Proceeds | (14) Project on Hold | 2021-02-10 | Noah Sorrell | Aurora Luna Residence | 8179 E State HWY 107 | Edinburg | TX |  | 21136.71 | 18858.18 | Residential
4861 | R2229 | Perez, Javier Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Metal ; A. Cedar Shake; D. Insurance Proceeds | (14) Project on Hold | 2020-12-19 | Joshua Rodriguez | Perez, Javier Residence | 405 S. Woodland dr. | Pharr | TX | 78577 | 52820.4 | 52820.4 | Residential
5148 | R2345 | Long, Robert Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Tile (Clay); D. Retail Contract | (14) Project on Hold | 2021-06-09 | Orlando Marquez | Long, Robert Residence | 2700 Brazos Ct | McAllen | TX | 78504 | 39500 | 39500 | Residential
2653 | R2324 | Martin, David Residence | Steep Slope Roof Systems | A. Tile (Clay); C. Additional Exterior Work; B. Roof Repair; D. Retail Contract; C. Additional Carpentry | (14) Project on Hold | 2021-05-26 | Juan Estrada | Martin, David Residence | 4140 Las Floresta Avenue | Mercedes | TX | 78570 | 26563 | 26563 | Residential
2535 | R2330 | Garza, Roberta & Edgar Residence | Steep Slope Roof Systems | A. Tile (Concrete); B. Roof Repair; D. Retail Contract; E. Special Order | (14) Project on Hold | 2021-07-09 | Philip Westerman | Garza, Roberta Residence | 2601 Santa Ana | Mission | TX | 78572 | 18812.48 | 18812.48 | Residential
5791 | R2375 | LUDWIG, DEREK Residence | Steep Slope Roof Systems | B. Roof Replacement; A. Asphalt Compostion Shingle; D. Retail Contract | (15) Archive | 2021-05-25 | Tim Parrish | LUDWIG, DEREK Residence | 8506 COLCHESTER | San Antonio | TX | 78254 | 8480 | 8480 | Residential